## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION & RETROFITTING OF DEULI (ZONE-I & II) PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15088 | Augmentation | Interconnection & rising main with supply of specials from Head work site to PH-III for Zone-I & Head work site to PH-III for Zone-II of Deuli (Zone - I & II) W/S Scheme, Block-Canning-II under Canning Sub-Division of Alipore Division,PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000291/2023-2024 | 1435/AD | 13/07/2023 | 11/10/2023 | UNIVERSAL CORPORATION | 236.64 | 28.35 | 11.98 | 35
2 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION & RETROFITTING OF DEULI (ZONE-I & II) PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15088 | Augmentation | Additional work for retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to additional households (1600 nos.) in excess of IMIS in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Deuli (Zone - I & II) Water Supply Scheme including one year Operation & Maintenance of scheme, Block - Canning-II South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000324/2023-2024 | 1550/AD | 17/07/2023 | 15/10/2023 | J.D.J. ENTERPRISE (A UNIT OF JDJ TRADERS PVT. LTD.) | 105.02 | 0 | 0 | 0
3 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION & RETROFITTING OF DEULI (ZONE-I & II) PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15088 | Augmentation | Laying of pipe line in place of existing damage line at Deuli W/S Scheme (Zone-II), Block - Canning-II under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000338/2023-2024 | 1555/AD | 17/07/2023 | 15/10/2023 | SOMA CONSTRUCTION | 106.44 | 0 | 0 | 0
4 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION & RETROFITTING OF DEULI (ZONE-I & II) PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15088 | Augmentation | Surging of 1no. Big dia Tubewell of Deuli (Zone - I) W/S Scheme under JJM, Block - Canning-II under Canning Sub-Division under Alipore Division P.H.Engg. Dte. (TW-1) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000414/2023-2024 | 773/CSD | 02/08/2023 | 11/09/2023 | S.K.GOLUI | 2.3 | 2.3 | 100 | 99
5 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION & RETROFITTING OF DEULI (ZONE-I & II) PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15088 | Augmentation | Laying damage pipe line from Akkashia Madrasa to H/O Chandika Show at Deuli W/S Scheme (Zone-II), Block - Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division |  | ORD/001644/2021-2022 | 1512/CSD | 15/02/2022 | 07/03/2022 | M/S. TAPAS MONDAL | 4.81 | 4.6 | 95.6 | 0
6 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION & RETROFITTING OF DEULI (ZONE-I & II) PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15088 | Augmentation | Sinking of 02 (two) nos. 250mm x 150mm dia. 360 mtr. deep Tubewell (New) by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter at Tube Well No. - 3 for each zone of Augmentation of Deuli (Zone - I & II) W/S Scheme, Block - Canning-II under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/001669/2022-2023 | 11480/AD | 15/02/2023 | 01/04/2023 | ELECTROMECH | 39.19 | 9.24 | 23.57 | 50
7 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION & RETROFITTING OF DEULI (ZONE-I & II) PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15088 | Augmentation | Sinking of 250mm x 150mm dia. 360 mtr. deep Tubewell (New) by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter at Tube Well No. - 3 of Augmentation of Deuli (Zone - II) W/S Scheme, Block - Canning-II under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/001672/2022-2023 | 11483/AD | 15/02/2023 | 17/03/2023 | B.K. ENTERPRISE. | 19.99 | 0 | 0 | 0
8 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION & RETROFITTING OF DEULI (ZONE-I & II) PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15088 | Augmentation | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Deuli W/S Scheme (Zone - II), Block-Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. (PH - 3) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/001688/2022-2023 | 11495/AD | 15/02/2023 | 01/04/2023 | ARFIN CONSTRUCTION | 7.09 | 0 | 0 | 0
9 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION & RETROFITTING OF DEULI (ZONE-I & II) PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15088 | Augmentation | Laying damage rising main from Panchayat More to PH-II and other distribution lines at Deuli W/S Scheme (Zone-II), Block-Canning-II under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division |  | ORD/002162/2020-2021 | 1594/CSD | 23/02/2021 | 25/03/2021 | M/S. TAPAS MONDAL | 3.85 | 2.45 | 63.62 | 0
10 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION & RETROFITTING OF DEULI (ZONE-I & II) PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15088 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000019/2023-2024 | 225/AD | 22/04/2023 |  | Resource Division | 117.02 | 0 | 0 | 0
11 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | AUGMENTATION & RETROFITTING OF DEULI (ZONE-I & II) PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15088 | Augmentation | Quotation for new service( power) connection at Deuli Zone-II PH-3 Water supply scheme under Canning-II block. Reference ID:-106579689, Application No :-1007690738 |  |  | BILL/00374/2024-2025 | BP-2024-25-97 | 10/06/2024 |  | WBSEDCL | 7.29 | 0 | 0 | null
12 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | AUGMENTATION & RETROFITTING OF DEULI (ZONE-I & II) PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15088 | Augmentation | Quotation for new service( power) connection at Deuli Zone-I PH-3 Water supply scheme under Canning-II block. Reference ID:-106676154, Application No :-1007943446 |  |  | BILL/01365/2024-2025 | BP-2024-25-294 | 22/08/2024 |  | WBSEDCL | 8.18 | 0 | 0 | null
13 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | AUGMENTATION & RETROFITTING OF DEULI (ZONE-I & II) PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15088 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H.1 & 2 for Augmentation of Deuli (Zone-1 & 2) water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Canning-II] | Assistant Engineer | Junior Engineer | ORD/000042/2023-2024 | 1003/SMD | 10/04/2023 | 09/07/2023 | JECLAT ENGINEERING CO-OPERATIVE SOCIETY LTD. | 22.21 | 0 | 0 | 0
14 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | AUGMENTATION & RETROFITTING OF DEULI (ZONE-I & II) PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15088 | Augmentation | Supply, delivery and installation of 20 KVA servo motor operated Copper wound line voltage stabilizer at P.H. No. 2, Zone-Ii of Deuli Water Supply Scheme under SMD, PHE Dte. [Block: Canning-II] | Assistant Engineer | Junior Engineer | ORD/000241/2024-2025 | 2507/SMD | 06/08/2024 | 20/09/2024 | M/S. S.R. ENTERPRISE | 0 | 0 | NAN | 0
15 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | AUGMENTATION & RETROFITTING OF DEULI (ZONE-I & II) PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15088 | Augmentation | Supply, delivery and installation of 20 KVA servo motor operated Copper wound line voltage stabilizer at P.H. No. 2, Zone-Ii of Deuli Water Supply Scheme under SMD, PHE Dte. [Block: Canning-II] | Assistant Engineer | Junior Engineer | ORD/000243/2024-2025 | 2507/SMD | 06/08/2024 | 20/09/2024 | M/S. S.R. ENTERPRISE | 2.97 | 0 | 0 | 0
Total | [13 empty] | 682.98 | 46.93 | 6.87