## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION OF DISTRIBUTION SYSTEM UNDER ZONE-II, MATHURAPUR-I BLOCK DEBIPUR PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) IN CONNECTION WITH JAL JEEVAN MISSION (JJM) UNDER MEGA SURFACE WATER BASED WATER SUPPLY SCHEME | SM/15470 | Augmentation | Providing FHTC including distribution system and other allied works at Zone- II of Mathurapur -I Block for ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ in connection with Jal Jeevan Mission (JJM) under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/000120/2023-2024 | 591/AD | 15/05/2023 | 13/08/2023 | DIPTI ENTERPRISE | 140.01 | 22.97 | 16.41 | 40
2 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION OF DISTRIBUTION SYSTEM UNDER ZONE-II, MATHURAPUR-I BLOCK DEBIPUR PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) IN CONNECTION WITH JAL JEEVAN MISSION (JJM) UNDER MEGA SURFACE WATER BASED WATER SUPPLY SCHEME | SM/15470 | Augmentation | Filling in foundation of Overhead Reservoir (Mathurapur - I, Zone -II ) by silver sand filling for Mega Surface Water Based Water Supply Scheme of Falta - Mathurapur, South 24 Paraganas under Raidighi Sub - Division of Alipore Division, PHE Dte. | Assistant Engineer, Raidighi sub division |  | ORD/000241/2022-2023 | 74/RSD | 18/05/2022 | 17/07/2022 | G.B. CONSTRUCTION & CO. | 2.79 | 2.74 | 98.27 | 0
3 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION OF DISTRIBUTION SYSTEM UNDER ZONE-II, MATHURAPUR-I BLOCK DEBIPUR PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) IN CONNECTION WITH JAL JEEVAN MISSION (JJM) UNDER MEGA SURFACE WATER BASED WATER SUPPLY SCHEME | SM/15470 | Augmentation | Providing Functional Household Tap Connection (FHTC) to all the households in Debipur piped water supply scheme ( Mathurapur-I, Zone-II) including Operation and Maintenance of scheme for 1 (one) year , District South 24 Parganas, Block - Mathurapur-I under Raidighi Sub-Division of Alipore Division, P.H.E.Dte. (Phase-I) (2nd call) | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/001197/2021-2022 | 5724/AD | 31/01/2022 | 31/01/2023 | M/S. JHARNA ENTERPRISE | 101.84 | 13.48 | 13.24 | 85
4 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION OF DISTRIBUTION SYSTEM UNDER ZONE-II, MATHURAPUR-I BLOCK DEBIPUR PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) IN CONNECTION WITH JAL JEEVAN MISSION (JJM) UNDER MEGA SURFACE WATER BASED WATER SUPPLY SCHEME | SM/15470 | Augmentation | Laying distribution system of piped water supply at Zone-II of Mathurapur - I Block for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. (2nd call) | Assistant Engineer, Raidighi sub division |  | ORD/001339/2021-2022 | 6033/AD | 16/02/2022 | 17/05/2022 | DIPTI ENTERPRISE | 123.9 | 49.78 | 40.18 | 95
5 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION OF DISTRIBUTION SYSTEM UNDER ZONE-II, MATHURAPUR-I BLOCK DEBIPUR PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) IN CONNECTION WITH JAL JEEVAN MISSION (JJM) UNDER MEGA SURFACE WATER BASED WATER SUPPLY SCHEME | SM/15470 | Augmentation | Inter connection between tubewells and Rising Main system of piped water supply at Zone - II of Mathurapur - I Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/001963/2022-2023 | 12717/AD | 14/03/2023 | 13/04/2023 | MONCON INDIA | 10.98 | 9.96 | 90.74 | 95
6 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION OF DISTRIBUTION SYSTEM UNDER ZONE-II, MATHURAPUR-I BLOCK DEBIPUR PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) IN CONNECTION WITH JAL JEEVAN MISSION (JJM) UNDER MEGA SURFACE WATER BASED WATER SUPPLY SCHEME | SM/15470 | Augmentation | Construction of 500 cum capacity 20 M. staging height RCC Over Head Water Reservoir as per departmental drawing & specification incl. RCC Bored Pile & Pile Cap upto pedestal at Mathurapur - I Block (Zn. - II) for Mega Surface Water Based Water Supply Scheme of Falta - Mathurapur South 24 Pgs. under Raidighi Sub Divn. of Alipore Division, PHE dte. |  |  | ORD/002025/2019-2020 | 7721/AD | 26/02/2020 | 24/02/2025 | G.B. CONSTRUCTION & CO. | 64.12 | 11.15 | 17.4 | 75
7 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION OF DISTRIBUTION SYSTEM UNDER ZONE-II, MATHURAPUR-I BLOCK DEBIPUR PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) IN CONNECTION WITH JAL JEEVAN MISSION (JJM) UNDER MEGA SURFACE WATER BASED WATER SUPPLY SCHEME | SM/15470 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000632/2023-2024 | 268/AD | 15/01/2024 |  | Resource Division | 6.71 | 0 | 0 | 0
Total | [13 empty] | 450.34 | 110.1 | 24.45