## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF DARIA PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15475 | Augmentation | Additional work for retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to additional households (1400 nos.) in excess of IMIS in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Daria Water Supply Scheme including one year Operation & Maintenance of scheme, Block - Canning-I South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000335/2023-2024 | 1552/AD | 17/07/2023 | 15/10/2023 | M/S. ROY CHOWDHURY & CO. | 156.75 | 19.48 | 12.43 | 40
2 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF DARIA PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15475 | Augmentation | Relaying and repairing of pipeline Daria W/S Scheme (NP-11-12,12-14,14-18), Block-Canning -I under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division |  | ORD/001565/2020-2021 | 972/CSD | 09/11/2020 | 09/12/2020 | GANGA TUBEWELL AND HARDWARE | 4.82 | 4.82 | 100 | 0
3 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF DARIA PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15475 | Augmentation | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Daria W/S Scheme, Block-Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. (PH - 5) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001693/2022-2023 | 11624/AD | 18/02/2023 | 04/04/2023 | THE TOWER CONSTRUCTION | 7.09 | 0 | 0 | 0
4 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF DARIA PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15475 | Augmentation | Sinking of 250mm x 150mm dia. 360 mtr. deep Tubewell (New) by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter at Tube Well No. - 5 of Augmentation of Daria W/S Scheme, Block - Canning-I under Canning Sub Division of Alipore Division, PHE Dte. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001769/2022-2023 | 12042/AD | 27/02/2023 | 29/03/2023 | ZINARUL ISLAM | 19.6 | 8.37 | 42.69 | 100
5 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF DARIA PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15475 | Augmentation | Rising main & Inter connection from pump house no. 1,2,3 & 4 to distribution line and supply of materials at Daria W/S Scheme block Canning I under Canning Sub Division of Alipore Division, PHE Dte. |  |  | ORD/002187/2017-2018 | 1070/CSD | 28/03/2018 |  | GANGA TUBEWELL AND HARDWARE | 4.84 | 1.88 | 38.82 | 95
6 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF DARIA PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15475 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000730/2023-2024 | 553/AD | 25/01/2024 |  | Resource Division | 87.75 | 0 | 0 | 0
7 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | AUGMENTATION AND RETROFITTING OF DARIA PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15475 | Augmentation | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/01718/2023-2024 | BP-2023-24-192 | 09/08/2023 |  | WBSEDCL | 5.41 | 0 | 0 | 0
8 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | AUGMENTATION AND RETROFITTING OF DARIA PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15475 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H.1 for Augmentation of Daria water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Canning-I] | Assistant Engineer | Junior Engineer | ORD/000026/2023-2024 | 960/SMD | 04/04/2023 | 03/07/2023 | M/S. MA KALI ELECTRIC LIGHT CORPORATION | 11.11 | 0 | 0 | 0
Total | [13 empty] | 297.37 | 34.55 | 11.62