## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION OF SONAKHALI (ZONE-II) PIPED WATER SUPPLY SCHEME. | SM/16116 | Augmentation | Sinking of 250mm x 150mm dia. 350 mtr. deep Tubewell (New) by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter at Tube Well No. -3 of Sonakhali Water Supply Scheme (Zone-II), Block - Basanti under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000056/2022-2023 | 792/AD | 12/05/2022 | 11/06/2022 | G. B. CONSTRUCTION | 17.99 | 16.86 | 93.72 | 94
2 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION OF SONAKHALI (ZONE-II) PIPED WATER SUPPLY SCHEME. | SM/16116 | Augmentation | Laying Distribution System, Providing Functional Household Tap Connection for Ground Water Based Augmentation Piped Water Supply Scheme for the Sonakhali (Zone-II), Block-Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [No. of FHTC = 1220] | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000256/2023-2024 | 1444/AD | 13/07/2023 | 11/09/2023 | RIVER BENZ CONSTRUCTION | 265.52 | 75.08 | 28.28 | 40
3 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION OF SONAKHALI (ZONE-II) PIPED WATER SUPPLY SCHEME. | SM/16116 | Augmentation | onstruction of 1 (one) no. switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Sonakhali W/S Scheme (Zone-II), Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House No. III] | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000313/2024-2025 | 2694/AD | 24/06/2024 | 08/08/2024 | SAHANA ENTERPRISE | 7.08 | 0 | 0 | 0
4 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION OF SONAKHALI (ZONE-II) PIPED WATER SUPPLY SCHEME. | SM/16116 | Augmentation | Additional laying of pipeline at Sonakhali (Zone-II) W/S Scheme, Block-Basanti under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000487/2024-2025 | 3546/AD | 02/09/2024 | 01/11/2024 | MONDAL ENTERPRISE (MURSHIDABAD) | 43.98 | 0 | 0 | 0
5 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION OF SONAKHALI (ZONE-II) PIPED WATER SUPPLY SCHEME. | SM/16116 | Augmentation | Inter connection in between the replacement tubewell towards distribution system for Sonakhali W/S Scheme (Zone-II), Block - Basanti under Canning Sub-Division of Alipore Division, P.H.E. Dte. (TW-2) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/001255/2023-2024 | 1203/CSD | 10/11/2023 | 10/12/2023 | C.S. CONSTRUCTION | 1.01 | 0 | 0 | 0
6 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION OF SONAKHALI (ZONE-II) PIPED WATER SUPPLY SCHEME. | SM/16116 | Augmentation | Conducting route survey, design distribution network and preparation & submission of DPR for Sonakhali (Zone-II) Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Basanti Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division |  | ORD/001852/2022-2023 | 11818/AD | 23/02/2023 | 09/04/2023 | TECH VISION | 4.56 | 4.56 | 100 | 0
7 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION OF SONAKHALI (ZONE-II) PIPED WATER SUPPLY SCHEME. | SM/16116 | Augmentation | Construction of 23 Nos. different capacity R.C.C OHR (based on Departmental Design & Drawing ) with 20 mtr. staging height including Geo-Technical investigation, foundation, pipeline connection and cost of pipes , specials etc. for augmentation of different piped water supply scheme of Canning-I, Canning-II & Basanti Block under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/002461/2023-2024 | 1512/AD | 13/03/2024 | 07/01/2025 | NATIONAL PROJECTS CONSTRUCTION CORPORATION LTD | 2624.49 | 0 | 0 | 30
8 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION OF SONAKHALI (ZONE-II) PIPED WATER SUPPLY SCHEME. | SM/16116 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000036/2023-2024 | 241/AD | 24/04/2023 |  | Resource Division | 85.44 | 0 | 0 | 0
9 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION OF SONAKHALI (ZONE-II) PIPED WATER SUPPLY SCHEME. | SM/16116 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000393/2023-2024 | 334/AD | 19/01/2024 |  | Resource Division | 7.52 | 0 | 0 | 0
Total | [13 empty] | 3057.59 | 96.5 | 3.16