## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF NETRA PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/17225 | Augmentation | Additional work for retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to additional households (700 nos.) in excess of IMIS in connection with Jal Jeevan Mission (JJM) for Netra Water Supply Scheme including one year Operation & Maintenance of scheme, Block - Canning-II South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000223/2023-2024 | 1028/AD | 13/06/2023 | 28/07/2023 | SAHANA ENTERPRISE | 50.78 | 16.42 | 32.32 | 66
2 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF NETRA PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/17225 | Augmentation | Construction of 1 (one) no. switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Netra Water Supply Scheme, Block-Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. (Pump House - III) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000256/2022-2023 | 3490/AD | 26/07/2022 | 09/09/2022 | R.G. ENTERPRISE (I) | 6.69 | 2.91 | 43.45 | 98
3 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF NETRA PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/17225 | Augmentation | Bamboo pilling and earth work in embankment for protection of boundary wall at head work site of Netra W/S Scheme, under Canning-II Block, South 24 Parganas District of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division |  | ORD/000326/2022-2023 | 267/CSD | 19/05/2022 | 18/06/2022 | RSA ENTERPRISE | 4.71 | 2.15 | 45.6 | 98
4 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF NETRA PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/17225 | Augmentation | Construction of 1 (one) no. switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Netra W/S Scheme, Block - Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. (Pump House No. V) (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000483/2024-2025 | 3542/AD | 02/09/2024 | 17/10/2024 | ZUBIN CONSTRUCTION | 7.07 | 0 | 0 | 0
5 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF NETRA PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/17225 | Augmentation | Inter connection & rising main with supply of specials of Augmentation of Netra W/S Scheme, Block-Canning-II under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/002491/2023-2024 | 1615/CSD | 29/02/2024 | 30/03/2024 | SAHANA ENTERPRISE | 4.82 | 0 | 0 | 0
6 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION AND RETROFITTING OF NETRA PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/17225 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000080/2023-2024 | 3054/AD | 28/09/2023 |  | Resource Division | 79.38 | 0 | 0 | 0
7 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | AUGMENTATION AND RETROFITTING OF NETRA PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/17225 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H.1 for Augmentation of Netra water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Canning-II] | Assistant Engineer | Junior Engineer | ORD/000036/2023-2024 | 991/SMD | 06/04/2023 | 05/07/2023 | SUDIP PRADHAN | 10.76 | 10.15 | 94.36 | 100
8 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | AUGMENTATION AND RETROFITTING OF NETRA PIPED WATER SUPPLY SCHEME FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/17225 | Augmentation | Supply & installation of LED board at PH-1 OF Tambuldaha & PH-1 of Netra Augmentation w/s scheme under South 24-Pgs Mechanical Division PHE Dte. [Block:Canning-II] |  |  | ORD/000893/2023-2024 | 1O65/SMSD | 10/08/2023 | 20/08/2023 | T.S. CONSTRUCTION | 0.78 | 0.78 | 100 | 100
Total | [13 empty] | 164.99 | 32.4 | 19.64