## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARAGANAS | Namkhana | Alipore Division | DAKSHIN CHANDRANAGAR PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER ALIPORE DIVISION, PHE DTE. | SM/18394 | New | Construction 02 nos. Pump House (5.40m. x 3.60m.) for providing FHTC at Dakshin Chandranagar Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000134/2024-2025 | 2471/AD | 14/06/2024 | 13/08/2024 | SUGANDHIT SUNDARBAN ENTERPRISE PVT. LTD. | 11.25 | 0 | 0 | 0
2 | SOUTH 24 PARAGANAS | Namkhana | Alipore Division | DAKSHIN CHANDRANAGAR PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER ALIPORE DIVISION, PHE DTE. | SM/18394 | New | Construction, placing and fixing of FHTC platform at every individual beneficiary, pump connections etc at Dakshin Chandranagar PWSS, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (SM/18394) (Part-B) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000157/2024-2025 | 2508/AD | 15/06/2024 | 29/08/2024 | M/S. MIHIR KUMAR NASKAR | 89.74 | 0 | 0 | 0
3 | SOUTH 24 PARAGANAS | Namkhana | Alipore Division | DAKSHIN CHANDRANAGAR PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER ALIPORE DIVISION, PHE DTE. | SM/18394 | New | Construction, placing and fixing of FHTC platform at every individual beneficiary, pump connections, pile and pile cap for OHR etc at Dakshin Chandranagar PWSS, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (SM/18394) (Part-A) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000366/2024-2025 | 2915/AD | 10/07/2024 | 08/09/2024 | GARGO TRADERS | 98.12 | 0 | 0 | 0
4 | SOUTH 24 PARAGANAS | Namkhana | Alipore Division | DAKSHIN CHANDRANAGAR PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER ALIPORE DIVISION, PHE DTE. | SM/18394 | New | Construction of 300 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) including design & drawing of pile foundation & pile cap after soil investigation along with Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including O & M for Dakshin Chandranagar Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000369/2023-2024 | 1570/AD | 17/07/2023 | 12/05/2024 | GARGO TRADERS | 473.26 | 146.26 | 30.9 | 20
5 | SOUTH 24 PARAGANAS | Namkhana | Alipore Division | DAKSHIN CHANDRANAGAR PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER ALIPORE DIVISION, PHE DTE. | SM/18394 | New | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site of Dakshin Chandranagar W/S scheme, Block : Namkhana under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (SM/18394) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000391/2024-2025 | 3059/AD | 25/07/2024 | 24/08/2024 | SK SAKIL AHAMED | 9.6 | 0 | 0 | 0
6 | SOUTH 24 PARAGANAS | Namkhana | Alipore Division | DAKSHIN CHANDRANAGAR PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER ALIPORE DIVISION, PHE DTE. | SM/18394 | New | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site of Dakshin Chandranagar W/S scheme, Block : Namkhana under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (SM/18394) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000401/2024-2025 | 3184/AD | 31/07/2024 | 14/09/2024 | RABIUL GAZI | 28.61 | 0 | 0 | 0
7 | SOUTH 24 PARAGANAS | Namkhana | Alipore Division | DAKSHIN CHANDRANAGAR PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER ALIPORE DIVISION, PHE DTE. | SM/18394 | New | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 3rd & 4th Tubewell Site of Dakshin Chandranagar W/S scheme, Block : Namkhana under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (SM/18394) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000453/2024-2025 | 3060/AD | 25/07/2024 | 08/09/2024 | ANANDA MAITY | 19.09 | 0 | 0 | 0
8 | SOUTH 24 PARAGANAS | Namkhana | Alipore Division | DAKSHIN CHANDRANAGAR PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER ALIPORE DIVISION, PHE DTE. | SM/18394 | New | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Dakshin Chandranagar Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-D) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000567/2023-2024 | 1807/AD | 26/07/2023 | 25/08/2023 | FORTUNE ENGINEERING | 16.93 | 0 | 0 | 0
9 | SOUTH 24 PARAGANAS | Namkhana | Alipore Division | DAKSHIN CHANDRANAGAR PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER ALIPORE DIVISION, PHE DTE. | SM/18394 | New | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 1st and 2nd Tubewell Site of Dakshin Chandranagar Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000574/2023-2024 | 1828/AD | 27/07/2023 | 10/09/2023 | MEGA SOLAR ENERGY | 36.66 | 18.32 | 49.97 | 100
10 | SOUTH 24 PARAGANAS | Namkhana | Alipore Division | DAKSHIN CHANDRANAGAR PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER ALIPORE DIVISION, PHE DTE. | SM/18394 | New | Laying distribution system, Functional Household Tap Connection (FHTC) to all households and Construction 02 nos. Pump House (5.40m. x 3.60m.) for Dakshin Chandranagar Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000579/2023-2024 | 2266/AD | 14/08/2023 | 28/09/2023 | B.S.ENTERPRISE (II) | 60.58 | 17.63 | 29.11 | 40
11 | SOUTH 24 PARAGANAS | Namkhana | Alipore Division | DAKSHIN CHANDRANAGAR PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER ALIPORE DIVISION, PHE DTE. | SM/18394 | New | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Dakshin Chandranagar Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-C) [No. of FHTC =650] | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/001014/2023-2024 | 3205/AD | 04/10/2023 | 02/01/2024 | M/S. MIHIR KUMAR NASKAR | 105.31 | 31.19 | 29.62 | 30
12 | SOUTH 24 PARAGANAS | Namkhana | Alipore Division | DAKSHIN CHANDRANAGAR PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER ALIPORE DIVISION, PHE DTE. | SM/18394 | New | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 3rd and 4th Tubewell Site of Dakshin Chandranagar W/S Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/001835/2023-2024 | 123/AD | 05/01/2024 | 19/02/2024 | SARADA CONSTRUCTION | 39.88 | 0 | 0 | 0
13 | SOUTH 24 PARAGANAS | Namkhana | Alipore Division | DAKSHIN CHANDRANAGAR PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER ALIPORE DIVISION, PHE DTE. | SM/18394 | New | Making and fixing of permanent display board at headwork site of Dakshin Chandranagar, Haripur Zone - I & II, Amarabati PWSS under JJM at Namkhana Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/002131/2023-2024 | 937/KSD | 19/12/2023 | 24/12/2023 | M/S B. ENTERPRISE | 0.63 | 0 | 0 | 100
14 | SOUTH 24 PARAGANAS | Namkhana | Alipore Division | DAKSHIN CHANDRANAGAR PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER ALIPORE DIVISION, PHE DTE. | SM/18394 | New | Material Requisition To Resource Division |  |  | RTOR000559/2023-2024 | 47/AD | 03/01/2024 |  | Resource Division | 11.33 | 0 | 0 | 0
15 | SOUTH 24 PARAGANAS | Namkhana | Alipore Division | DAKSHIN CHANDRANAGAR PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER ALIPORE DIVISION, PHE DTE. | SM/18394 | New | Material Requisition To Resource Division |  |  | RTOR000789/2023-2024 | 633/AD | 30/01/2024 |  | Resource Division | 4.74 | 0 | 0 | 0
16 | SOUTH 24 PARAGANAS | Namkhana | Alipore Division | DAKSHIN CHANDRANAGAR PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER ALIPORE DIVISION, PHE DTE. | SM/18394 | New | Material Requisition To Resource Division |  |  | RTOR000989/2023-2024 | 1782/AD | 27/03/2024 |  | Resource Division | 45.43 | 0 | 0 | 0
17 | SOUTH 24 PARAGANAS | Namkhana | S24 Pgns Mechanical | DAKSHIN CHANDRANAGAR PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER ALIPORE DIVISION, PHE DTE. | SM/18394 | New | Payment for New Service connection of Dakshin Chandranagar PH-2 W/S Scheme Application No- 1007183473 Reference ID:- 106222546 |  |  | BILL/00213/2024-2025 | BP-2024-25-61 | 16/05/2024 |  | WBSEDCL | 3.55 | 0 | 0 | null
18 | SOUTH 24 PARAGANAS | Namkhana | S24 Pgns Mechanical | DAKSHIN CHANDRANAGAR PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER ALIPORE DIVISION, PHE DTE. | SM/18394 | New | PAYMENT OF ELECTRICITY BILL FOR NEW SERVICE CONNECTION UNDER SMD PHE DTE. |  |  | BILL/05392/2023-2024 | BP-2023-24-596 | 28/03/2024 |  | WBSEDCL | 8.06 | 0 | 0 | 0
19 | SOUTH 24 PARAGANAS | Namkhana | S24 Pgns Mechanical | DAKSHIN CHANDRANAGAR PIPED WATER SUPPLY SCHEME IN NAMKHANA BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER ALIPORE DIVISION, PHE DTE. | SM/18394 | New | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Dakshin Chandranagar water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Namkhana] | Assistant Engineer -I | Junior Engineer | ORD/001511/2022-2023 | 3837/SMD | 29/12/2022 | 29/03/2023 | BINAPANI ENTERPRISE | 23.4 | 0 | 0 | 0
Total | [13 empty] | 1086.16 | 213.4 | 19.65