## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION OF JAMALPUR W/S SCHEME UNDER ALIPORE DIVISION P.H.E DTE. (PHASE-II) | SM/18868 | Augmentation | Construction of Chlorination Room at OHR Site of Jamalpur Water Supply Scheme, Block: Budge Budge-I under Diamond Harbour Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Diamond Harbour sub division |  | ORD/000060/2022-2023 | 841/AD | 13/05/2022 | 12/06/2022 | BANGA NIRMAN | 5.15 | 4.97 | 96.58 | 98
2 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION OF JAMALPUR W/S SCHEME UNDER ALIPORE DIVISION P.H.E DTE. (PHASE-II) | SM/18868 | Augmentation | Construction of 200 cum. capacity 20 mtr. staging height R.C.C. Over Head Water Reservoir as per departmental design, drawing and specification including R.C.C. Bored Pile & Pile Cap upto pedestal at JAMALPUR Water Supply Scheme, Block - Budge-Budge-I under Diamond Harbour Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division |  | ORD/000069/2021-2022 | 834/AD | 18/06/2021 | 18/06/2022 | M/S. S.S. ENTERPRISE | 63.1 | 15.78 | 25 | 5
3 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION OF JAMALPUR W/S SCHEME UNDER ALIPORE DIVISION P.H.E DTE. (PHASE-II) | SM/18868 | Augmentation | Development and strengthening of earthen approach road from Jamalpur Health Centre to proposed OHR site of Jamalpur W/S Scheme and allied works in Budge Budge-I Block under Diamond Harbour Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Diamond Harbour sub division |  | ORD/000215/2022-2023 | 3002/AD | 11/07/2022 | 26/07/2022 | M/S. S.S. ENTERPRISE | 10.89 | 10.77 | 98.95 | 95
Total | [13 empty] | 79.14 | 31.52 | 39.83