## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Basanti, Canning-I/II, Baruipur, Mograhat & Sonarpur, Mathurapur-I/II and Kultali Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical | SM/09196 | Disaster | Supply and delivery of gunny bag at Sagar Island in connection with preparedness of cyclonic storm "YAAS" under SMD, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000440/2021-2022 | 98/YAAS/SMD | 26/05/2021 | 15/06/2021 | S.P. CONSTRUCTION | 4.94 | 4.94 | 100 | 0
2 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Basanti, Canning-I/II, Baruipur, Mograhat & Sonarpur, Mathurapur-I/II and Kultali Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical | SM/09196 | Disaster | Cont. order for Carriage of packaged drinking water bottle & self contained water pouches from Dakshin Roypur to different loacations in connection with preparedness of cyclonic storm YAAS under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000441/2021-2022 | 157/YAAS/SMD | 30/05/2021 | 19/06/2021 | M/S. S.S. ENTERPRISE | 2.74 | 2.74 | 100 | 0
3 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Basanti, Canning-I/II, Baruipur, Mograhat & Sonarpur, Mathurapur-I/II and Kultali Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical | SM/09196 | Disaster | Cont. order for Carriage of packaged drinking water bottle & self contained water pouches from Dakshin Roypur to different loacations in connection with preparedness of cyclonic storm YAAS under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000442/2021-2022 | 154/YAAS/SMD | 29/05/2021 | 18/06/2021 | M/S. S.S. ENTERPRISE | 2.74 | 2.74 | 100 | 0
4 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Basanti, Canning-I/II, Baruipur, Mograhat & Sonarpur, Mathurapur-I/II and Kultali Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical | SM/09196 | Disaster | Cont. order for Carriage of packaged drinking water bottle & self contained water pouches from Dakshin Roypur to different loacations in connection with preparedness of cyclonic storm YAAS under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000443/2021-2022 | 131/YAAS/SMD | 27/05/2021 | 16/06/2021 | M/S. S.S. ENTERPRISE | 4.21 | 4.21 | 100 | 0
5 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Basanti, Canning-I/II, Baruipur, Mograhat & Sonarpur, Mathurapur-I/II and Kultali Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical | SM/09196 | Disaster | Cont. order for Carriage of packaged drinking water bottle & self contained water pouches from Dakshin Roypur to different loacations in connection with preparedness of cyclonic storm YAAS under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000444/2021-2022 | 133/YAAS/SMD | 27/05/2021 | 16/06/2021 | M/S. S.S. ENTERPRISE | 4.21 | 4.21 | 100 | 0
6 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Basanti, Canning-I/II, Baruipur, Mograhat & Sonarpur, Mathurapur-I/II and Kultali Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical | SM/09196 | Disaster | Cont. order for Carriage of packaged drinking water bottle & self contained water pouches from Dakshin Roypur to different loacations in connection with preparedness of cyclonic storm YAAS under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000445/2021-2022 | 153/YAAS/SMD | 29/05/2021 | 18/06/2021 | M/S. S.S. ENTERPRISE | 2.74 | 2.74 | 100 | 0
7 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Basanti, Canning-I/II, Baruipur, Mograhat & Sonarpur, Mathurapur-I/II and Kultali Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical | SM/09196 | Disaster | Cont. order for Carriage of packaged drinking water bottle & self contained water pouches from Dakshin Roypur to different loacations in connection with preparedness of cyclonic storm YAAS under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000446/2021-2022 | 151/YAAS/SMD | 29/05/2021 | 18/06/2021 | M/S. S.S. ENTERPRISE | 2.74 | 2.74 | 100 | 0
8 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Basanti, Canning-I/II, Baruipur, Mograhat & Sonarpur, Mathurapur-I/II and Kultali Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical | SM/09196 | Disaster | Cont. order for Carriage of packaged drinking water bottle & self contained water pouches from Dakshin Roypur to different loacations in connection with preparedness of cyclonic storm YAAS under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000447/2021-2022 | 158/YAAS/SMD | 30/05/2021 | 19/06/2021 | M/S. S.S. ENTERPRISE | 2.74 | 2.74 | 100 | 0
9 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Basanti, Canning-I/II, Baruipur, Mograhat & Sonarpur, Mathurapur-I/II and Kultali Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical | SM/09196 | Disaster | Cont. order for Carriage of packaged drinking water bottle & self contained water pouches from Dakshin Roypur to different loacations in connection with preparedness of cyclonic storm YAAS under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000448/2021-2022 | 162/YAAS/SMD | 30/05/2021 | 19/06/2021 | M/S. S.S. ENTERPRISE | 2.74 | 2.74 | 100 | 0
10 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Basanti, Canning-I/II, Baruipur, Mograhat & Sonarpur, Mathurapur-I/II and Kultali Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical | SM/09196 | Disaster | Cont. order for Carriage of packaged drinking water bottle & self contained water pouches from Dakshin Roypur to different loacations in connection with preparedness of cyclonic storm YAAS under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000449/2021-2022 | 140/YAAS/SMD | 28/05/2021 | 17/06/2021 | M/S. S.S. ENTERPRISE | 3.2 | 3.2 | 100 | 0
11 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Basanti, Canning-I/II, Baruipur, Mograhat & Sonarpur, Mathurapur-I/II and Kultali Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical | SM/09196 | Disaster | Cont. order for Carriage of packaged drinking water bottle & self contained water pouches from Dakshin Roypur to different loacations in connection with preparedness of cyclonic storm YAAS under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000450/2021-2022 | 161/YAAS/SMD | 30/05/2021 | 19/06/2021 | M/S. S.S. ENTERPRISE | 2.74 | 2.74 | 100 | 0
12 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Basanti, Canning-I/II, Baruipur, Mograhat & Sonarpur, Mathurapur-I/II and Kultali Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical | SM/09196 | Disaster | Cont. order for Carriage of packaged drinking water bottle & self contained water pouches from Dakshin Roypur to different loacations in connection with preparedness of cyclonic storm YAAS under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000451/2021-2022 | 128/YAAS/SMD | 27/05/2021 | 16/06/2021 | M/S. S.S. ENTERPRISE | 4.74 | 4.74 | 100 | 0
13 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Basanti, Canning-I/II, Baruipur, Mograhat & Sonarpur, Mathurapur-I/II and Kultali Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical | SM/09196 | Disaster | Cont. order for Carriage of packaged drinking water bottle & self contained water pouches from Dakshin Roypur to different loacations in connection with preparedness of cyclonic storm YAAS under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000452/2021-2022 | 130/YAAS/SMD | 27/05/2021 | 16/06/2021 | M/S. S.S. ENTERPRISE | 4.45 | 4.45 | 100 | 0
14 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Basanti, Canning-I/II, Baruipur, Mograhat & Sonarpur, Mathurapur-I/II and Kultali Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical | SM/09196 | Disaster | Cont. order for Carriage of packaged drinking water bottle & self contained water pouches from Dakshin Roypur to different loacations in connection with preparedness of cyclonic storm YAAS under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000453/2021-2022 | 138/YAAS/SMD | 28/05/2021 | 17/06/2021 | M/S. S.S. ENTERPRISE | 4.21 | 4.21 | 100 | 0
15 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Basanti, Canning-I/II, Baruipur, Mograhat & Sonarpur, Mathurapur-I/II and Kultali Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical | SM/09196 | Disaster | Cont. order for Carriage of packaged drinking water bottle & self contained water pouches from Dakshin Roypur to different loacations in connection with preparedness of cyclonic storm YAAS under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000454/2021-2022 | 164/YAAS/SMD | 30/05/2021 | 19/06/2021 | M/S. S.S. ENTERPRISE | 1.24 | 1.24 | 100 | 0
16 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Basanti, Canning-I/II, Baruipur, Mograhat & Sonarpur, Mathurapur-I/II and Kultali Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical | SM/09196 | Disaster | Supply and delivery of Polyfilm roll for MTU at Sagar Island in connection with preparedness of cyclonic storm YAAS under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000455/2021-2022 | 99/YAAS/SMD | 26/05/2021 | 15/06/2021 | M/S. S.S. ENTERPRISE | 4.69 | 4.69 | 100 | 0
17 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Basanti, Canning-I/II, Baruipur, Mograhat & Sonarpur, Mathurapur-I/II and Kultali Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical | SM/09196 | Disaster | Cont order for Supply and delivery of Polyfilm roll for MTU at Sagar Island in connection with preparedness of cyclonic storm YAAS under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000456/2021-2022 | 175/YAAS/SMD | 04/06/2021 | 24/06/2021 | M/S. S.S. ENTERPRISE | 2.98 | 2.98 | 100 | 0
18 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Basanti, Canning-I/II, Baruipur, Mograhat & Sonarpur, Mathurapur-I/II and Kultali Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical | SM/09196 | Disaster | Cont order for Supply and delivery of Polyfilm roll for MTU at Sagar Island in connection with preparedness of cyclonic storm YAAS under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000457/2021-2022 | 165/YAAS/SMD | 30/05/2021 | 19/06/2021 | M/S. S.S. ENTERPRISE | 4.69 | 4.69 | 100 | 0
19 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Basanti, Canning-I/II, Baruipur, Mograhat & Sonarpur, Mathurapur-I/II and Kultali Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical | SM/09196 | Disaster | Cont order for Supply and delivery of Polyfilm roll for MTU at Sagar Island in connection with preparedness of cyclonic storm YAAS under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000458/2021-2022 | 142/YAAS/SMD | 28/05/2021 | 17/06/2021 | M/S. S.S. ENTERPRISE | 4.69 | 4.69 | 100 | 0
20 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Basanti, Canning-I/II, Baruipur, Mograhat & Sonarpur, Mathurapur-I/II and Kultali Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical | SM/09196 | Disaster | Cont order for Supply and delivery of Polyfilm roll for MTU at Sagar Island in connection with preparedness of cyclonic storm YAAS under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000459/2021-2022 | 132/YAAS/SMD | 27/05/2021 | 16/06/2021 | M/S. S.S. ENTERPRISE | 4.69 | 4.69 | 100 | 0
21 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Basanti, Canning-I/II, Baruipur, Mograhat & Sonarpur, Mathurapur-I/II and Kultali Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical | SM/09196 | Disaster | Cont order for Supply and delivery of Polyfilm roll for MTU at Sagar Island in connection with preparedness of cyclonic storm YAAS under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000460/2021-2022 | 156/YAAS/SMD | 29/05/2021 | 18/06/2021 | M/S. S.S. ENTERPRISE | 4.69 | 4.69 | 100 | 0
22 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Basanti, Canning-I/II, Baruipur, Mograhat & Sonarpur, Mathurapur-I/II and Kultali Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical | SM/09196 | Disaster | Cont. order for Carriage of packaged drinking water bottle & self contained water pouches from MTU at Kakdwip / Sagar to different loacations in connection with preparedness of cyclonic storm YAAS under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000461/2021-2022 | 171/YAAS/SMD | 02/06/2021 | 22/06/2021 | M/S. S.S. ENTERPRISE | 4.88 | 4.88 | 100 | 0
23 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Basanti, Canning-I/II, Baruipur, Mograhat & Sonarpur, Mathurapur-I/II and Kultali Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical | SM/09196 | Disaster | Cont. order for Carriage of packaged drinking water bottle & self contained water pouches from MTU at Kakdwip / Sagar to different loacations in connection with preparedness of cyclonic storm YAAS under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000462/2021-2022 | 173/YAAS/SMD | 03/06/2021 | 23/06/2021 | M/S. S.S. ENTERPRISE | 4.88 | 4.88 | 100 | 0
24 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Basanti, Canning-I/II, Baruipur, Mograhat & Sonarpur, Mathurapur-I/II and Kultali Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical | SM/09196 | Disaster | Cont. order for Carriage of packaged drinking water bottle & self contained water pouches from MTU at Kakdwip / Sagar to different loacations in connection with preparedness of cyclonic storm YAAS under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000463/2021-2022 | 176/YAAS/SMD | 04/06/2021 | 24/06/2021 | M/S. S.S. ENTERPRISE | 4.88 | 4.88 | 100 | 0
25 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Basanti, Canning-I/II, Baruipur, Mograhat & Sonarpur, Mathurapur-I/II and Kultali Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical | SM/09196 | Disaster | Providing diesel generator set at PH-2 of Dakshin Shibganj water supply scheme under Kakdwip Sub-Division for preparedness of super cyclonic storm YAAS to maintain uninterrupted drinking water supply under SMD, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000465/2021-2022 | 48-Yaas/SMD | 26/05/2021 | 15/06/2021 | NITESH MANAGEMENT | 3.11 | 3.11 | 100 | 0
26 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Basanti, Canning-I/II, Baruipur, Mograhat & Sonarpur, Mathurapur-I/II and Kultali Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical | SM/09196 | Disaster | Providing diesel generator set at PH-1 of Ramratanpur water supply scheme under Kakdwip Sub-Division for preparedness of super cyclonic storm YAAS to maintain uninterrupted drinking water supply under SMD, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000467/2021-2022 | 39-Yaas/SMD | 26/05/2021 | 15/06/2021 | NITESH MANAGEMENT | 2.38 | 2.38 | 100 | 0
27 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Basanti, Canning-I/II, Baruipur, Mograhat & Sonarpur, Mathurapur-I/II and Kultali Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical | SM/09196 | Disaster | Providing diesel generator set at PH-2 of Dakshin Shibganj water supply scheme under Kakdwip Sub-Division for preparedness of super cyclonic storm YAAS to maintain uninterrupted drinking water supply under SMD, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000468/2021-2022 | 43-Yaas/SMD | 26/05/2021 | 15/06/2021 | NITESH MANAGEMENT | 2.27 | 2.27 | 100 | 0
28 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Basanti, Canning-I/II, Baruipur, Mograhat & Sonarpur, Mathurapur-I/II and Kultali Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical | SM/09196 | Disaster | Providing diesel generator set at PH-2 of Kalinagar Ganeshpur water supply scheme under Kakdwip Sub-Division for preparedness of super cyclonic storm YAAS to maintain uninterrupted drinking water supply under SMD, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000469/2021-2022 | 38-Yaas/SMD | 26/05/2021 | 15/06/2021 | NITESH MANAGEMENT | 2.38 | 0 | 0 | 0
29 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Basanti, Canning-I/II, Baruipur, Mograhat & Sonarpur, Mathurapur-I/II and Kultali Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical | SM/09196 | Disaster | Providing diesel generator set at PH-2 of Kalinagar Ganeshpur water supply scheme under Kakdwip Sub-Division for preparedness of super cyclonic storm YAAS to maintain uninterrupted drinking water supply under SMD, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000471/2021-2022 | 38-Yaas/A/SMD | 26/05/2021 | 15/06/2021 | NITESH MANAGEMENT | 2.38 | 2.38 | 100 | 0
30 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Basanti, Canning-I/II, Baruipur, Mograhat & Sonarpur, Mathurapur-I/II and Kultali Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical | SM/09196 | Disaster | Providing diesel generator set at PH-1 of Haripur water supply scheme under Kakdwip Sub-Division for preparedness of super cyclonic storm YAAS to maintain uninterrupted drinking water supply under SMD, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000472/2021-2022 | 44-Yaas/SMD | 26/05/2021 | 15/06/2021 | NITESH MANAGEMENT | 2.52 | 2.52 | 100 | 0
31 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Basanti, Canning-I/II, Baruipur, Mograhat & Sonarpur, Mathurapur-I/II and Kultali Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical | SM/09196 | Disaster | Providing diesel generator set at PH-3 of Akshaynagar water supply scheme under Kakdwip Sub-Division for preparedness of super cyclonic storm YAAS to maintain uninterrupted drinking water supply under SMD, PHE Dte | Assistant Engineer | Junior Engineer | ORD/000474/2021-2022 | 27-Yaas/SMD | 26/05/2021 | 15/06/2021 | NITESH MANAGEMENT | 4.12 | 4.12 | 100 | 0
32 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Basanti, Canning-I/II, Baruipur, Mograhat & Sonarpur, Mathurapur-I/II and Kultali Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical | SM/09196 | Disaster | Providing diesel generator set at PH-3 of Akshaynagar water supply scheme under Kakdwip Sub-Division for preparedness of super cyclonic storm YAAS to maintain uninterrupted drinking water supply under SMD, PHE Dte. (Part-B) | Assistant Engineer | Junior Engineer | ORD/000475/2021-2022 | 28-Yaas/SMD | 26/05/2021 | 15/06/2021 | NITESH MANAGEMENT | 4.12 | 4.12 | 100 | 0
33 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Basanti, Canning-I/II, Baruipur, Mograhat & Sonarpur, Mathurapur-I/II and Kultali Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical | SM/09196 | Disaster | Providing diesel generator set at PH-1 of Rajnagar water supply scheme under Kakdwip Sub-Division for preparedness of super cyclonic storm YAAS to maintain uninterrupted drinking water supply under SMD, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000477/2021-2022 | 46-Yaas/SMD | 26/05/2021 | 15/06/2021 | NITESH MANAGEMENT | 2.22 | 2.22 | 100 | 0
34 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Basanti, Canning-I/II, Baruipur, Mograhat & Sonarpur, Mathurapur-I/II and Kultali Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical | SM/09196 | Disaster | Providing diesel generator set at PH-1 of Shibpur water supply scheme under Kakdwip Sub-Division for preparedness of super cyclonic storm YAAS to maintain uninterrupted drinking water supply under SMD, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000479/2021-2022 | 45-Yaas/SMD | 26/05/2021 | 15/06/2021 | NITESH MANAGEMENT | 2.09 | 2.09 | 100 | 0
35 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Basanti, Canning-I/II, Baruipur, Mograhat & Sonarpur, Mathurapur-I/II and Kultali Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical | SM/09196 | Disaster | Providing diesel generator set at PH-1 of Namkhana water supply scheme under Kakdwip Sub-Division for preparedness of super cyclonic storm YAAS to maintain uninterrupted drinking water supply under SMD, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000480/2021-2022 | 40-Yaas/SMD | 26/05/2021 | 15/06/2021 | NITESH MANAGEMENT | 2.38 | 2.38 | 100 | 0
36 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Basanti, Canning-I/II, Baruipur, Mograhat & Sonarpur, Mathurapur-I/II and Kultali Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical | SM/09196 | Disaster | Providing diesel generator set at PH-1 of Kusumtala water supply scheme under Kakdwip Sub-Division for preparedness of super cyclonic storm YAAS to maintain uninterrupted drinking water supply under SMD, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000481/2021-2022 | 42-Yaas/SMD | 26/05/2021 | 15/06/2021 | NITESH MANAGEMENT | 3.79 | 3.79 | 100 | 0
37 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Basanti, Canning-I/II, Baruipur, Mograhat & Sonarpur, Mathurapur-I/II and Kultali Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical | SM/09196 | Disaster | Providing diesel generator set at PH-2 of Namkhana water supply scheme under Kakdwip Sub-Division for preparedness of super cyclonic storm YAAS to maintain uninterrupted drinking water supply under SMD, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000482/2021-2022 | 41-Yaas/SMD | 26/05/2021 | 15/06/2021 | NITESH MANAGEMENT | 2.38 | 2.38 | 100 | 0
38 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Basanti, Canning-I/II, Baruipur, Mograhat & Sonarpur, Mathurapur-I/II and Kultali Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical | SM/09196 | Disaster | Providing diesel generator set at PH-1 of Dakshin Shibganj water supply scheme under Kakdwip Sub-Division for preparedness of super cyclonic storm YAAS to maintain uninterrupted drinking water supply under SMD, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000483/2021-2022 | 47-Yaas/SMD | 26/05/2021 | 15/06/2021 | NITESH MANAGEMENT | 2.78 | 2.78 | 100 | 0
39 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Basanti, Canning-I/II, Baruipur, Mograhat & Sonarpur, Mathurapur-I/II and Kultali Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical | SM/09196 | Disaster | Providing diesel generator set at PH-I of Taktipur water supply scheme under Kakdwip sub-Division for prepardness of cyclonic storm YAAS to maintain uninterruptred drinking water supply under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000530/2021-2022 | 33/YAAS/SMD | 26/05/2021 | 15/06/2021 | M/S.UTTAM KUMAR CHATTERJEE | 2.03 | 2.03 | 100 | 0
40 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Basanti, Canning-I/II, Baruipur, Mograhat & Sonarpur, Mathurapur-I/II and Kultali Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical | SM/09196 | Disaster | Providing diesel generator set at PH-I of Nebutala Abad water supply scheme under Kakdwip sub-Division for prepardness of cyclonic storm YAAS to maintain uninterruptred drinking water supply under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000533/2021-2022 | 34/YAAS/SMD | 26/05/2021 | 15/06/2021 | M/S.UTTAM KUMAR CHATTERJEE | 2.38 | 2.38 | 100 | 0
41 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Basanti, Canning-I/II, Baruipur, Mograhat & Sonarpur, Mathurapur-I/II and Kultali Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical | SM/09196 | Disaster | Providing diesel generator set at PH-I of Ramchandranagar water supply scheme under Kakdwip sub-Division for prepardness of cyclonic storm YAAS to maintain uninterruptred drinking water supply under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000536/2021-2022 | 35/YAAS/SMD | 26/05/2021 | 15/06/2021 | M/S.UTTAM KUMAR CHATTERJEE | 2.03 | 2.03 | 100 | 0
42 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Basanti, Canning-I/II, Baruipur, Mograhat & Sonarpur, Mathurapur-I/II and Kultali Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical | SM/09196 | Disaster | Providing diesel generator set at PH-I of Dakshin Gangadharpur water supply scheme under Kakdwip sub-Division for prepardness of cyclonic storm YAAS to maintain uninterruptred drinking water supply under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000538/2021-2022 | 37/YAAS/SMD | 26/05/2021 | 15/06/2021 | M/S.UTTAM KUMAR CHATTERJEE | 2.03 | 2.03 | 100 | 0
43 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Basanti, Canning-I/II, Baruipur, Mograhat & Sonarpur, Mathurapur-I/II and Kultali Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical | SM/09196 | Disaster | Providing diesel generator set at PH-I of Hesamabad water supply scheme under Kakdwip sub-Division for prepardness of cyclonic storm YAAS to maintain uninterruptred drinking water supply under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000541/2021-2022 | 26/YAAS/SMD | 26/05/2021 | 15/06/2021 | M/S.UTTAM KUMAR CHATTERJEE | 4.8 | 4.8 | 100 | 0
44 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Basanti, Canning-I/II, Baruipur, Mograhat & Sonarpur, Mathurapur-I/II and Kultali Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical | SM/09196 | Disaster | Providing diesel generator set at PH-I of Chandipur water supply scheme under Kakdwip sub-Division for prepardness of cyclonic storm YAAS to maintain uninterruptred drinking water supply under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000544/2021-2022 | 32/YAAS/SMD | 26/05/2021 | 15/06/2021 | M/S.UTTAM KUMAR CHATTERJEE | 2.03 | 2.03 | 100 | 0
45 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Basanti, Canning-I/II, Baruipur, Mograhat & Sonarpur, Mathurapur-I/II and Kultali Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical | SM/09196 | Disaster | Providing diesel generator set at PH-I of Koaberia water supply scheme under Kakdwip sub-Division for prepardness of cyclonic storm YAAS to maintain uninterruptred drinking water supply under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000550/2021-2022 | 29/YAAS/SMD | 26/05/2021 | 15/06/2021 | S.P. CONSTRUCTION | 2.52 | 2.52 | 100 | 0
46 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Basanti, Canning-I/II, Baruipur, Mograhat & Sonarpur, Mathurapur-I/II and Kultali Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical | SM/09196 | Disaster | Providing diesel generator set at PH-I of Ramganga water supply scheme under Kakdwip sub-Division for prepardness of cyclonic storm YAAS to maintain uninterruptred drinking water supply under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000552/2021-2022 | 50/YAAS/SMD | 26/05/2021 | 15/06/2021 | S.P. CONSTRUCTION | 2.27 | 2.27 | 100 | 0
47 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Basanti, Canning-I/II, Baruipur, Mograhat & Sonarpur, Mathurapur-I/II and Kultali Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical | SM/09196 | Disaster | Providing diesel generator set at PH-I of Gurudaspur water supply scheme under Kakdwip sub-Division for prepardness of cyclonic storm YAAS to maintain uninterruptred drinking water supply under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000554/2021-2022 | 49/YAAS/SMD | 26/05/2021 | 15/06/2021 | S.P. CONSTRUCTION | 2.27 | 2.27 | 100 | 0
48 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Basanti, Canning-I/II, Baruipur, Mograhat & Sonarpur, Mathurapur-I/II and Kultali Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical | SM/09196 | Disaster | Providing diesel generator set at PH-I of Gangadharpur water supply scheme under Kakdwip sub-Division for prepardness of cyclonic storm YAAS to maintain uninterruptred drinking water supply under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000555/2021-2022 | 30/YAAS/SMD | 26/05/2021 | 15/06/2021 | S.P. CONSTRUCTION | 2.03 | 2.03 | 100 | 0
49 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Basanti, Canning-I/II, Baruipur, Mograhat & Sonarpur, Mathurapur-I/II and Kultali Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical | SM/09196 | Disaster | Providing diesel generator set at GBDA office under Kakdwip sub-Division for prepardness of cyclonic storm YAAS to maintain uninterruptred drinking water supply under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000566/2021-2022 | 51/YAAS/SMD | 26/05/2021 | 15/06/2021 | M/S. BABUSONA ENTERPRISE | 0.97 | 0.97 | 100 | 0
50 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Basanti, Canning-I/II, Baruipur, Mograhat & Sonarpur, Mathurapur-I/II and Kultali Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical | SM/09196 | Disaster | Providing diesel generator set at PH-2 of Shibpur & PH-I of Mrityunjaynagar w/s scheme under Kakdwip sub-Division for prepardness of cyclonic storm YAAS to maintain uninterruptred drinking water supply under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000567/2021-2022 | 61/YAAS/SMD | 26/05/2021 | 15/06/2021 | M/S. BABUSONA ENTERPRISE | 2.11 | 2.11 | 100 | 0
51 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Basanti, Canning-I/II, Baruipur, Mograhat & Sonarpur, Mathurapur-I/II and Kultali Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical | SM/09196 | Disaster | Providing diesel generator set at PH-2 of Dhaspara & PH-I of Companirchar & PH-2 of Mahishamari w/s scheme under Kakdwip sub-Division for prepardness of cyclonic storm YAAS to maintain uninterruptred drinking water supply under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000569/2021-2022 | 58/YAAS/SMD | 26/05/2021 | 15/06/2021 | M/S. BABUSONA ENTERPRISE | 1.29 | 1.29 | 100 | 0
52 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Basanti, Canning-I/II, Baruipur, Mograhat & Sonarpur, Mathurapur-I/II and Kultali Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical | SM/09196 | Disaster | Providing diesel generator set at PH-2 of Nagendraganj & PH-2 of Krishnanagar w/s scheme under Kakdwip sub-Division for prepardness of cyclonic storm YAAS to maintain uninterruptred drinking water supply under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000575/2021-2022 | 59/YAAS/SMD | 26/05/2021 | 15/06/2021 | M/S. BABUSONA ENTERPRISE | 1.04 | 1.04 | 100 | 0
53 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Basanti, Canning-I/II, Baruipur, Mograhat & Sonarpur, Mathurapur-I/II and Kultali Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical | SM/09196 | Disaster | Providing diesel generator set at PH-1 of Kamalpur Rudranagar & PH-2 of Kamalpur Rudranagar Aug. w/s scheme under Kakdwip sub-Division for prepardness of cyclonic storm YAAS to maintain uninterruptred drinking water supply under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000576/2021-2022 | 57/YAAS/SMD | 26/05/2021 | 15/06/2021 | M/S. BABUSONA ENTERPRISE | 0.95 | 0.95 | 100 | 0
54 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Basanti, Canning-I/II, Baruipur, Mograhat & Sonarpur, Mathurapur-I/II and Kultali Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical | SM/09196 | Disaster | Providing diesel generator set at PH-1&1, Zone-I of Mandirtala w/s scheme under Kakdwip sub-Division for prepardness of cyclonic storm YAAS to maintain uninterruptred drinking water supply under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000577/2021-2022 | 56/YAAS/SMD | 26/05/2021 | 15/06/2021 | M/S. BABUSONA ENTERPRISE | 1.14 | 1.14 | 100 | 0
55 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Basanti, Canning-I/II, Baruipur, Mograhat & Sonarpur, Mathurapur-I/II and Kultali Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical | SM/09196 | Disaster | Providing diesel generator set at PH-1of Haradhanpur & PH-2 of Radhakrishnapur w/s scheme under Kakdwip sub-Division for prepardness of cyclonic storm YAAS to maintain uninterruptred drinking water supply under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000578/2021-2022 | 60/YAAS/SMD | 26/05/2021 | 15/06/2021 | M/S. BABUSONA ENTERPRISE | 2.01 | 2.01 | 100 | 0
56 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Basanti, Canning-I/II, Baruipur, Mograhat & Sonarpur, Mathurapur-I/II and Kultali Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical | SM/09196 | Disaster | Providing diesel generator set at Basanti MTU Yard water supply scheme under Canning sub-Division for prepardness of cyclonic storm YAAS to maintain uninterruptred drinking water supply under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000579/2021-2022 | 23/YAAS/SMD | 26/05/2021 | 15/06/2021 | DEPALI CONSTRUCTION | 3.55 | 3.55 | 100 | 0
57 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Basanti, Canning-I/II, Baruipur, Mograhat & Sonarpur, Mathurapur-I/II and Kultali Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical | SM/09196 | Disaster | Providing diesel generator set at OHR - 26 water supply scheme under Baruipur sub-Division for prepardness of cyclonic storm YAAS to maintain uninterruptred drinking water supply under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000580/2021-2022 | 66/YAAS/SMD | 26/05/2021 | 15/06/2021 | DEPALI CONSTRUCTION | 1.47 | 1.47 | 100 | 0
58 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Basanti, Canning-I/II, Baruipur, Mograhat & Sonarpur, Mathurapur-I/II and Kultali Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical | SM/09196 | Disaster | Providing diesel generator set at OHR - 27 water supply scheme under Baruipur sub-Division for prepardness of cyclonic storm YAAS to maintain uninterruptred drinking water supply under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000581/2021-2022 | 67/YAAS/SMD | 26/05/2021 | 15/06/2021 | DEPALI CONSTRUCTION | 2.44 | 2.44 | 100 | 0
59 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Basanti, Canning-I/II, Baruipur, Mograhat & Sonarpur, Mathurapur-I/II and Kultali Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical | SM/09196 | Disaster | Providing diesel generator set at PH-2 of Mollapukur water supply scheme under Diamond Harbour sub-Division for prepardness of cyclonic storm YAAS to maintain uninterruptred drinking water supply under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000582/2021-2022 | 121/YAAS/SMD | 26/05/2021 | 15/06/2021 | SHIVAM ENTERPRISE | 1.54 | 1.54 | 100 | 0
60 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Basanti, Canning-I/II, Baruipur, Mograhat & Sonarpur, Mathurapur-I/II and Kultali Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical | SM/09196 | Disaster | Providing diesel generator set at PH-1 of Hasimnagar water supply scheme under Diamond Harbour sub-Division for prepardness of cyclonic storm YAAS to maintain uninterruptred drinking water supply under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000583/2021-2022 | 122/YAAS/SMD | 26/05/2021 | 15/06/2021 | SHIVAM ENTERPRISE | 2.78 | 2.78 | 100 | 0
61 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Basanti, Canning-I/II, Baruipur, Mograhat & Sonarpur, Mathurapur-I/II and Kultali Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical | SM/09196 | Disaster | Providing diesel generator set at PH-4 of Diamond Harbour Municipality Aug. water supply scheme under Diamond Harbour sub-Division for prepardness of cyclonic storm YAAS to maintain uninterruptred drinking water supply under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000584/2021-2022 | 106/YAAS/SMD | 26/05/2021 | 15/06/2021 | SHIVAM ENTERPRISE | 2.67 | 2.67 | 100 | 0
62 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Basanti, Canning-I/II, Baruipur, Mograhat & Sonarpur, Mathurapur-I/II and Kultali Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical | SM/09196 | Disaster | Providing diesel generator set at PH-2 of Mosat water supply scheme under Diamond Harbour sub-Division for prepardness of cyclonic storm YAAS to maintain uninterruptred drinking water supply under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000585/2021-2022 | 116/YAAS/SMD | 26/05/2021 | 15/06/2021 | SHIVAM ENTERPRISE | 3.12 | 3.12 | 100 | 0
63 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Basanti, Canning-I/II, Baruipur, Mograhat & Sonarpur, Mathurapur-I/II and Kultali Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical | SM/09196 | Disaster | Providing diesel generator set at PH-2 of Lakhipur water supply scheme under Diamond Harbour sub-Division for prepardness of cyclonic storm YAAS to maintain uninterruptred drinking water supply under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000586/2021-2022 | 112/YAAS/SMD | 26/05/2021 | 15/06/2021 | SHIVAM ENTERPRISE | 2.11 | 2.11 | 100 | 0
64 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Basanti, Canning-I/II, Baruipur, Mograhat & Sonarpur, Mathurapur-I/II and Kultali Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical | SM/09196 | Disaster | Providing diesel generator set at PH-2 of Kanpur water supply scheme under Diamond Harbour sub-Division for prepardness of cyclonic storm YAAS to maintain uninterruptred drinking water supply under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000587/2021-2022 | 114/YAAS/SMD | 26/05/2021 | 15/06/2021 | SHIVAM ENTERPRISE | 1.28 | 1.28 | 100 | 0
65 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Basanti, Canning-I/II, Baruipur, Mograhat & Sonarpur, Mathurapur-I/II and Kultali Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical | SM/09196 | Disaster | Providing diesel generator set at PH-I, Zone-I of Gosaba (Sonagaon) water supply scheme under Canning sub-Division for prepardness of cyclonic storm YAAS to maintain uninterruptred drinking water supply under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000588/2021-2022 | 08/YAAS/SMD | 26/05/2021 | 15/06/2021 | AVINABA ENGINEERING CONCERN | 4.13 | 4.13 | 100 | 0
66 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Basanti, Canning-I/II, Baruipur, Mograhat & Sonarpur, Mathurapur-I/II and Kultali Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical | SM/09196 | Disaster | Providing diesel generator set at PH-2, Zone-II of Gosaba (Rajapur) water supply scheme under Canning sub-Division for prepardness of cyclonic storm YAAS to maintain uninterruptred drinking water supplyas and when required as per direction of EIC under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000589/2021-2022 | 11/YAAS/SMD | 26/05/2021 | 15/06/2021 | AVINABA ENGINEERING CONCERN | 4.13 | 4.13 | 100 | 0
67 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Basanti, Canning-I/II, Baruipur, Mograhat & Sonarpur, Mathurapur-I/II and Kultali Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical | SM/09196 | Disaster | Providing diesel generator set at PH-3, Zone-I of Gosaba (Sonagaon) water supply scheme under Canning sub-Division for prepardness of cyclonic storm YAAS to maintain uninterruptred drinking water supplyas and when required as per direction of EIC under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000590/2021-2022 | 10/YAAS/SMD | 26/05/2021 | 15/06/2021 | AVINABA ENGINEERING CONCERN | 2.63 | 2.42 | 91.92 | 0
68 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Basanti, Canning-I/II, Baruipur, Mograhat & Sonarpur, Mathurapur-I/II and Kultali Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical | SM/09196 | Disaster | Providing diesel generator set at PH-2, Zone-I of Gosaba (Sonagaon) water supply scheme under Canning sub-Division for prepardness of cyclonic storm YAAS to maintain uninterruptred drinking water supplyas and when required as per direction of EIC under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000591/2021-2022 | 09/YAAS/SMD | 26/05/2021 | 15/06/2021 | AVINABA ENGINEERING CONCERN | 4.13 | 4.13 | 100 | 0
69 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Basanti, Canning-I/II, Baruipur, Mograhat & Sonarpur, Mathurapur-I/II and Kultali Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical | SM/09196 | Disaster | Providing diesel generator set at PH-3, Zone-II of Gosaba (Rajapur) water supply scheme under Canning sub-Division for prepardness of cyclonic storm YAAS to maintain uninterruptred drinking water supplyas and when required as per direction of EIC under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000592/2021-2022 | 12/YAAS/SMD | 26/05/2021 | 15/06/2021 | AVINABA ENGINEERING CONCERN | 4.13 | 4.13 | 100 | 0
70 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Basanti, Canning-I/II, Baruipur, Mograhat & Sonarpur, Mathurapur-I/II and Kultali Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical | SM/09196 | Disaster | Providing diesel generator set at PH-1, Zone-II of Dakshin Ramkrishnapur water supply scheme under Diamond Harbour sub-Division for prepardness of cyclonic storm YAAS to maintain uninterruptred drinking water supply under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000593/2021-2022 | 103/YAAS/SMD | 26/05/2021 | 15/06/2021 | R.K. CONSTRUCTION | 3.12 | 3.12 | 100 | 0
71 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Basanti, Canning-I/II, Baruipur, Mograhat & Sonarpur, Mathurapur-I/II and Kultali Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical | SM/09196 | Disaster | Providing diesel generator set at PH-1 of Kulpi water supply scheme under Diamond Harbour sub-Division for prepardness of cyclonic storm YAAS to maintain uninterruptred drinking water supply under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000594/2021-2022 | 102/YAAS/SMD | 26/05/2021 | 15/06/2021 | R.K. CONSTRUCTION | 3.12 | 3.12 | 100 | 0
72 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Basanti, Canning-I/II, Baruipur, Mograhat & Sonarpur, Mathurapur-I/II and Kultali Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical | SM/09196 | Disaster | Providing diesel generator set at PH-2 of Diamond Harbour Municipality Aug. water supply scheme under Diamond Harbour sub-Division for prepardness of cyclonic storm YAAS to maintain uninterruptred drinking water supply under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000595/2021-2022 | 105/YAAS/SMD | 26/05/2021 | 15/06/2021 | SRI KRISHNA NIRMAN | 0.68 | 0.68 | 100 | 0
73 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Basanti, Canning-I/II, Baruipur, Mograhat & Sonarpur, Mathurapur-I/II and Kultali Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical | SM/09196 | Disaster | Providing diesel generator set at PH-2 of Diamond Harbour Municipality water supply scheme under Diamond Harbour sub-Division for prepardness of cyclonic storm YAAS to maintain uninterruptred drinking water supply under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000596/2021-2022 | 108/YAAS/SMD | 26/05/2021 | 15/06/2021 | SRI KRISHNA NIRMAN | 0.68 | 0.68 | 100 | 0
74 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Basanti, Canning-I/II, Baruipur, Mograhat & Sonarpur, Mathurapur-I/II and Kultali Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical | SM/09196 | Disaster | Providing diesel generator set at PH-4 of Diamond Harbour Municipality water supply scheme under Diamond Harbour sub-Division for prepardness of cyclonic storm YAAS to maintain uninterruptred drinking water supply under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000597/2021-2022 | 110/YAAS/SMD | 26/05/2021 | 15/06/2021 | SIPRA ENTERPRISE | 1.3 | 1.3 | 100 | 0
75 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Basanti, Canning-I/II, Baruipur, Mograhat & Sonarpur, Mathurapur-I/II and Kultali Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical | SM/09196 | Disaster | Providing diesel generator set at PH-3 of Diamond Harbour Municipality water supply scheme under Diamond Harbour sub-Division for prepardness of cyclonic storm YAAS to maintain uninterruptred drinking water supply under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000598/2021-2022 | 109/YAAS/SMD | 26/05/2021 | 15/06/2021 | SIPRA ENTERPRISE | 1.3 | 1.3 | 100 | 0
76 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Basanti, Canning-I/II, Baruipur, Mograhat & Sonarpur, Mathurapur-I/II and Kultali Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical | SM/09196 | Disaster | Providing diesel generator set at PH-1, Zone-I of Moukhali Kumarkhali water supply scheme under Canning sub-Division for prepardness of cyclonic storm YAAS to maintain uninterruptred drinking water supply as and when required as per direction of EIC under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000599/2021-2022 | 24/YAAS/SMD | 26/05/2021 | 15/06/2021 | M/S. PS & ASSOCIATES | 1.56 | 1.56 | 100 | 0
77 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Basanti, Canning-I/II, Baruipur, Mograhat & Sonarpur, Mathurapur-I/II and Kultali Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical | SM/09196 | Disaster | Providing diesel generator set at PH-1, Zone-II of Moukhali Kumarkhali water supply scheme under Canning sub-Division for prepardness of cyclonic storm YAAS to maintain uninterruptred drinking water supply as and when required as per direction of EIC under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000600/2021-2022 | 25/YAAS/SMD | 26/05/2021 | 15/06/2021 | M/S. PS & ASSOCIATES | 1.58 | 1.58 | 100 | 0
78 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Basanti, Canning-I/II, Baruipur, Mograhat & Sonarpur, Mathurapur-I/II and Kultali Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical | SM/09196 | Disaster | Providing diesel generator set at PH-1 of Dhola water supply scheme under Kakdwip sub-Division for prepardness of cyclonic storm YAAS to maintain uninterruptred drinking water supply under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000601/2021-2022 | 36/YAAS/SMD | 26/05/2021 | 15/06/2021 | M/S.UTTAM KUMAR CHATTERJEE | 2.03 | 2.03 | 100 | 0
79 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Basanti, Canning-I/II, Baruipur, Mograhat & Sonarpur, Mathurapur-I/II and Kultali Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical | SM/09196 | Disaster | Providing diesel generator set at OHR No-17 under Diamond Harbour sub-Division for prepardness of cyclonic storm YAAS to maintain uninterruptred drinking water supply under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000602/2021-2022 | 104-YAAS/SMD | 26/05/2021 | 15/06/2021 | S.P. CONSTRUCTION | 1.3 | 1.3 | 100 | 0
80 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Basanti, Canning-I/II, Baruipur, Mograhat & Sonarpur, Mathurapur-I/II and Kultali Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical | SM/09196 | Disaster | Providing diesel generator set at PH-1 of Diamond Harbour Municipality water shceme under Diamond Harbour sub-Division for prepardness of cyclonic storm YAAS to maintain uninterruptred drinking water supply under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000603/2021-2022 | 107-YAAS/SMD | 26/05/2021 | 15/06/2021 | S.P. CONSTRUCTION | 1.79 | 1.79 | 100 | 0
81 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Basanti, Canning-I/II, Baruipur, Mograhat & Sonarpur, Mathurapur-I/II and Kultali Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical | SM/09196 | Disaster | Providing diesel generator set at PH-1 of Kanpur water supply shceme under Diamond Harbour sub-Division for prepardness of cyclonic storm YAAS to maintain uninterruptred drinking water supply under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000604/2021-2022 | 113-YAAS/SMD | 26/05/2021 | 15/06/2021 | S.P. CONSTRUCTION | 1.06 | 1.06 | 100 | 0
82 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Basanti, Canning-I/II, Baruipur, Mograhat & Sonarpur, Mathurapur-I/II and Kultali Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical | SM/09196 | Disaster | Providing diesel generator set at PH-1 of Mosat water supply shceme under Diamond Harbour sub-Division for prepardness of cyclonic storm YAAS to maintain uninterruptred drinking water supply under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000605/2021-2022 | 115-Yaas/SMD | 26/05/2021 | 15/06/2021 | S.P. CONSTRUCTION | 2.78 | 2.78 | 100 | 0
83 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Basanti, Canning-I/II, Baruipur, Mograhat & Sonarpur, Mathurapur-I/II and Kultali Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical | SM/09196 | Disaster | Providing diesel generator set at PH-1 of Darikrishnanagar water supply shceme under Diamond Harbour sub-Division for prepardness of cyclonic storm YAAS to maintain uninterruptred drinking water supply under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000606/2021-2022 | 117-Yaas/SMD | 26/05/2021 | 15/06/2021 | S.P. CONSTRUCTION | 1.79 | 1.79 | 100 | 0
84 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Basanti, Canning-I/II, Baruipur, Mograhat & Sonarpur, Mathurapur-I/II and Kultali Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical | SM/09196 | Disaster | Providing diesel generator set at PH-1 of Khordanala water supply shceme under Diamond Harbour sub-Division for prepardness of cyclonic storm YAAS to maintain uninterruptred drinking water supply under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000607/2021-2022 | 120-Yaas/SMD | 26/05/2021 | 15/06/2021 | S.P. CONSTRUCTION | 1.54 | 1.54 | 100 | 0
85 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Basanti, Canning-I/II, Baruipur, Mograhat & Sonarpur, Mathurapur-I/II and Kultali Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical | SM/09196 | Disaster | Providing diesel generator set at PH-2 of Khandalia water supply shceme under Diamond Harbour sub-Division for prepardness of cyclonic storm YAAS to maintain uninterruptred drinking water supply under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000608/2021-2022 | 119-Yaas/SMD | 26/05/2021 | 15/06/2021 | S.P. CONSTRUCTION | 1.79 | 1.79 | 100 | 0
86 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Basanti, Canning-I/II, Baruipur, Mograhat & Sonarpur, Mathurapur-I/II and Kultali Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical | SM/09196 | Disaster | Providing diesel generator set at PH-1 of Atkrishnarampur water supply shceme under Diamond Harbour sub-Division for prepardness of cyclonic storm YAAS to maintain uninterruptred drinking water supply under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000609/2021-2022 | 118-Yaas/SMD | 26/05/2021 | 15/06/2021 | S.P. CONSTRUCTION | 1.79 | 1.79 | 100 | 0
87 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Basanti, Canning-I/II, Baruipur, Mograhat & Sonarpur, Mathurapur-I/II and Kultali Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical | SM/09196 | Disaster | Providing diesel generator set at PH-1 of Lakhipur water supply shceme under Diamond Harbour sub-Division for prepardness of cyclonic storm YAAS to maintain uninterruptred drinking water supply under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000610/2021-2022 | 111-Yaas/SMD | 26/05/2021 | 15/06/2021 | S.P. CONSTRUCTION | 1.54 | 1.54 | 100 | 0
88 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Basanti, Canning-I/II, Baruipur, Mograhat & Sonarpur, Mathurapur-I/II and Kultali Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical | SM/09196 | Disaster | Providing diesel generator set at PH-2 of Purba Radhanagar water supply shceme under Diamond Harbour sub-Division for prepardness of cyclonic storm YAAS to maintain uninterruptred drinking water supply under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000611/2021-2022 | 21/YAAS/SMD | 26/05/2021 | 15/06/2021 | AVINABA ENGINEERING CONCERN | 3.46 | 3.46 | 100 | 0
89 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Basanti, Canning-I/II, Baruipur, Mograhat & Sonarpur, Mathurapur-I/II and Kultali Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical | SM/09196 | Disaster | Providing diesel generator set at PH-1 of Lahiripur water supply shceme under Diamond Harbour sub-Division for prepardness of cyclonic storm YAAS to maintain uninterruptred drinking water supply under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000612/2021-2022 | 19-Yaas/SMD | 26/05/2021 | 15/06/2021 | AVINABA ENGINEERING CONCERN | 4.13 | 4.13 | 100 | 0
90 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Basanti, Canning-I/II, Baruipur, Mograhat & Sonarpur, Mathurapur-I/II and Kultali Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical | SM/09196 | Disaster | Providing diesel generator set at PH-1 of Bijoynagar water supply shceme under Diamond Harbour sub-Division for prepardness of cyclonic storm YAAS to maintain uninterruptred drinking water supply under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000613/2021-2022 | 17/YASS/SMD | 26/05/2021 | 15/06/2021 | AVINABA ENGINEERING CONCERN | 4.19 | 4.19 | 100 | 0
91 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Basanti, Canning-I/II, Baruipur, Mograhat & Sonarpur, Mathurapur-I/II and Kultali Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical | SM/09196 | Disaster | Providing diesel generator set at PH-2 of Pathankhali water supply shceme under Diamond Harbour sub-Division for prepardness of cyclonic storm YAAS to maintain uninterruptred drinking water supply under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000614/2021-2022 | 16/YASS/SMD | 26/05/2021 | 15/06/2021 | AVINABA ENGINEERING CONCERN | 2.63 | 2.63 | 100 | 0
92 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Basanti, Canning-I/II, Baruipur, Mograhat & Sonarpur, Mathurapur-I/II and Kultali Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical | SM/09196 | Disaster | Providing diesel generator set at PH-1 of Satjelia water supply shceme under Diamond Harbour sub-Division for prepardness of cyclonic storm YAAS to maintain uninterruptred drinking water supply under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000615/2021-2022 | 14/YASS/SMD | 26/05/2021 | 15/06/2021 | AVINABA ENGINEERING CONCERN | 4.13 | 4.13 | 100 | 0
93 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Basanti, Canning-I/II, Baruipur, Mograhat & Sonarpur, Mathurapur-I/II and Kultali Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical | SM/09196 | Disaster | Providing diesel generator set at Zone-II, PH-4 of Gosaba ( Rajapur) water supply shceme under Diamond Harbour sub-Division for prepardness of cyclonic storm YAAS to maintain uninterruptred drinking water supply as and when required per direction of EIC under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000616/2021-2022 | 13/YASS/SMD | 26/05/2021 | 15/06/2021 | AVINABA ENGINEERING CONCERN | 2.63 | 2.63 | 100 | 0
94 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Basanti, Canning-I/II, Baruipur, Mograhat & Sonarpur, Mathurapur-I/II and Kultali Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical | SM/09196 | Disaster | Providing diesel generator set at PH-3 of Lahiripur water supply shceme under Cannong sub-Division for prepardness of super cyclonic storm YAAS to maintain uninterruptred drinking water supply as and when required per direction of EIC under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000617/2021-2022 | 20/YASS/SMD | 26/05/2021 | 15/06/2021 | AVINABA ENGINEERING CONCERN | 3.46 | 3.46 | 100 | 0
95 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Basanti, Canning-I/II, Baruipur, Mograhat & Sonarpur, Mathurapur-I/II and Kultali Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical | SM/09196 | Disaster | Providing diesel generator set at PH-2 of Satjelia water supply shceme under Cannong sub-Division for prepardness of super cyclonic storm YAAS to maintain uninterruptred drinking water supply as and when required per direction of EIC under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000618/2021-2022 | 15/YASS/SMD | 26/05/2021 | 15/06/2021 | AVINABA ENGINEERING CONCERN | 2.23 | 2.23 | 100 | 0
96 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Basanti, Canning-I/II, Baruipur, Mograhat & Sonarpur, Mathurapur-I/II and Kultali Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical | SM/09196 | Disaster | Providing diesel generator set at PH-2 of Luxbagan water supply shceme under Cannong sub-Division for prepardness of super cyclonic storm YAAS to maintain uninterruptred drinking water supply as and when required per direction of EIC under South 24-Pgs Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000619/2021-2022 | 18/YASS/SMD | 26/05/2021 | 15/06/2021 | AVINABA ENGINEERING CONCERN | 3.46 | 3.46 | 100 | 0
97 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Basanti, Canning-I/II, Baruipur, Mograhat & Sonarpur, Mathurapur-I/II and Kultali Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical | SM/09196 | Disaster | Supply & delivery of 10 sq.mm. 4 crore un-armored round copper conductor cable for restoration of power in connection with Cyclone YASH at Harindanga PH-1 w/s scheme of Falta Block under SMD, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000667/2021-2022 | 1518/A/AE-II/SMD | 27/05/2021 | 16/06/2021 | S.P. CONSTRUCTION | 0.9 | 0 | 0 | 0
98 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Basanti, Canning-I/II, Baruipur, Mograhat & Sonarpur, Mathurapur-I/II and Kultali Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical | SM/09196 | Disaster | Supply & delivery of 10 sq.mm. 4 crore un-armored round copper conductor cable for restoration of power in connection with Cyclone YASH at Harindanga PH-1 w/s scheme of Falta Block under SMD, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000668/2021-2022 | 1518/A/AE-II/SMD. | 27/05/2021 | 16/06/2021 | S.P. CONSTRUCTION | 0.9 | 0 | 0 | 0
99 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Basanti, Canning-I/II, Baruipur, Mograhat & Sonarpur, Mathurapur-I/II and Kultali Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical | SM/09196 | Disaster | Cont. order for Hiring and running of DG set for running of pumping machinery towards the augmentation of water supply from Zone-13, Tentulberia water supply scheme under SMD, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000683/2021-2022 | 48/AE-II/SMD | 10/01/2022 | 20/01/2022 | M/S.UTTAM KUMAR CHATTERJEE | 0.87 | 0.87 | 100 | 0
100 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Basanti, Canning-I/II, Baruipur, Mograhat & Sonarpur, Mathurapur-I/II and Kultali Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical | SM/09196 | Disaster | Cont. order for Hiring and running of DG set for running of pumping machinery towards the augmentation of water supply from Zone-13, Tentulberia water supply scheme under SMD, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000685/2021-2022 | 2465/AE-II/SMD | 30/12/2021 | 09/01/2022 | M/S.UTTAM KUMAR CHATTERJEE | 0.87 | 0.87 | 100 | 0
101 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Basanti, Canning-I/II, Baruipur, Mograhat & Sonarpur, Mathurapur-I/II and Kultali Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical | SM/09196 | Disaster | Cont. order for Hiring and running of DG set for running of pumping machinery towards the augmentation of water supply from Zone-13, Tentulberia water supply scheme under SMD, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000687/2021-2022 | 120/AE-II/SMD | 20/01/2022 | 30/01/2022 | M/S.UTTAM KUMAR CHATTERJEE | 0.87 | 0.87 | 100 | 0
102 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Basanti, Canning-I/II, Baruipur, Mograhat & Sonarpur, Mathurapur-I/II and Kultali Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical | SM/09196 | Disaster | Cont. order for Hiring and running of DG set for running of pumping machinery towards the augmentation of water supply from Zone-13, Tentulberia water supply scheme under SMD, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000689/2021-2022 | 2386/AE-II/SMD | 10/12/2021 | 20/12/2021 | M/S.UTTAM KUMAR CHATTERJEE | 0.87 | 0.87 | 100 | 0
103 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Basanti, Canning-I/II, Baruipur, Mograhat & Sonarpur, Mathurapur-I/II and Kultali Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical | SM/09196 | Disaster | Cont. order for Hiring and running of DG set for running of pumping machinery towards the augmentation of water supply from Zone-13, Tentulberia water supply scheme under SMD, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000690/2021-2022 | 2430/AE-II/SMD | 23/12/2021 | 02/01/2022 | M/S.UTTAM KUMAR CHATTERJEE | 0.87 | 0.87 | 100 | 0
104 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Basanti, Canning-I/II, Baruipur, Mograhat & Sonarpur, Mathurapur-I/II and Kultali Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical | SM/09196 | Disaster | Cont. order for Hiring and running of DG set for running of pumping machinery towards the augmentation of water supply from Zone-13, Tentulberia water supply scheme under SMD, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000691/2021-2022 | 2353/AE-II/SMD | 02/12/2021 | 12/12/2021 | M/S.UTTAM KUMAR CHATTERJEE | 0.87 | 0.87 | 100 | 0
105 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Basanti, Canning-I/II, Baruipur, Mograhat & Sonarpur, Mathurapur-I/II and Kultali Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical | SM/09196 | Disaster | Cont. order for supply and delivery of Gunny bag at Sagar Island in connection with preparedness of cyclonic strom YAAS under SMD, PHE Dte. | Assistant Engineer ,Assistant Engineer -I | Junior Engineer | ORD/000696/2021-2022 | 155/YAAS/SMD | 29/05/2021 | 18/06/2021 | S.P. CONSTRUCTION | 4.94 | 0 | 0 | 0
106 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Basanti, Canning-I/II, Baruipur, Mograhat & Sonarpur, Mathurapur-I/II and Kultali Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical | SM/09196 | Disaster | Supply & delivery of electrical mechanical accessories in connection with withdrawing and lowering at PH-I of Rajapur under SMD, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001089/2021-2022 | 977/SMSD | 23/07/2021 | 07/08/2021 | SRI KRISHNA NIRMAN | 0.06 | 0.06 | 100 | 0
107 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Basanti, Canning-I/II, Baruipur, Mograhat & Sonarpur, Mathurapur-I/II and Kultali Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical | SM/09196 | Disaster | Supply & installation of automatic chlorinator for Tube Well No.-2 of Harbhangi W/S Scheme of Basanti Block under SMD, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001560/2018-2019 | 176/SMSD. | 20/02/2019 | 22/03/2019 | R.K. ENTERPRISES | 0.91 | 0.05 | 5.57 | 0
108 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Basanti, Canning-I/II, Baruipur, Mograhat & Sonarpur, Mathurapur-I/II and Kultali Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical | SM/09196 | Disaster | Supply and delivery of gunny bags for emergency carriage of drinking water pouch for Combat YAAS under SMD, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002495/2021-2022 | 6/YAAS/I/SMSD. | 27/05/2021 | 16/06/2021 | S.P. CONSTRUCTION | 0.91 | 0.24 | 26.59 | 0
109 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Basanti, Canning-I/II, Baruipur, Mograhat & Sonarpur, Mathurapur-I/II and Kultali Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical | SM/09196 | Disaster | Cont order for Emergency hiring charges of 50 KVA Mobile silent type diesel generator set on the situation of AMPHAN 2020 for PH-1 of Koaberia water supply scheme under SMD, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/003179/2020-2021 | 625/AMP/AE-I/SMD | 31/05/2020 | 20/06/2020 | GLACIER ENGINEERING CO. | 0.86 | 0.86 | 100 | 0
110 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Basanti, Canning-I/II, Baruipur, Mograhat & Sonarpur, Mathurapur-I/II and Kultali Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical | SM/09196 | Disaster | Cont order for Emergency hiring charges of 50 KVA Mobile silent type diesel generator set on the situation of AMPHAN 2020 for PH-1 of Koaberia water supply scheme under SMD, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/003180/2020-2021 | 776/AMP/AE-I/SMD | 09/06/2020 | 29/06/2020 | GLACIER ENGINEERING CO. | 0.86 | 0.86 | 100 | 0
111 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Basanti, Canning-I/II, Baruipur, Mograhat & Sonarpur, Mathurapur-I/II and Kultali Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical | SM/09196 | Disaster | Cont order for Emergency hiring charges of 50 KVA Mobile silent type diesel generator set on the situation of AMPHAN 2020 for PH-1 of Koaberia water supply scheme under SMD, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/003181/2020-2021 | 817/AMP/AE-I/SMD | 12/06/2020 | 02/07/2020 | GLACIER ENGINEERING CO. | 0.86 | 0.86 | 100 | 0
112 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Basanti, Canning-I/II, Baruipur, Mograhat & Sonarpur, Mathurapur-I/II and Kultali Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical | SM/09196 | Disaster | Cont order for Emergency hiring charges of 50 KVA Mobile silent type diesel generator set on the situation of AMPHAN 2020 for PH-1 of Koaberia water supply scheme under SMD, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/003182/2020-2021 | 892/AMP/AE-I/SMD | 12/06/2020 | 02/07/2020 | GLACIER ENGINEERING CO. | 0.86 | 0.86 | 100 | 0
113 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Basanti, Canning-I/II, Baruipur, Mograhat & Sonarpur, Mathurapur-I/II and Kultali Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical | SM/09196 | Disaster | Cont order for Emergency hiring charges of 50 KVA Mobile silent type diesel generator set on the situation of AMPHAN 2020 for PH-1 of Koaberia water supply scheme under SMD, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/003183/2020-2021 | 852/AMP/AE-I/SMD | 15/06/2020 | 05/07/2020 | GLACIER ENGINEERING CO. | 0.86 | 0.86 | 100 | 0
114 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Basanti, Canning-I/II, Baruipur, Mograhat & Sonarpur, Mathurapur-I/II and Kultali Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical | SM/09196 | Disaster | Cont order for Emergency hiring charges of 50 KVA Mobile silent type diesel generator set on the situation of AMPHAN 2020 for PH-1 of Koaberia water supply scheme under SMD, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/003184/2020-2021 | 882/AMP/AE-I/SMD | 18/06/2020 | 08/07/2020 | GLACIER ENGINEERING CO. | 0.86 | 0.86 | 100 | 0
115 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Basanti, Canning-I/II, Baruipur, Mograhat & Sonarpur, Mathurapur-I/II and Kultali Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical | SM/09196 | Disaster | Cont order for Emergency hiring charges of 50 KVA Mobile silent type diesel generator set on the situation of AMPHAN 2020 for PH-1 of Koaberia water supply scheme under SMD, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/003185/2020-2021 | 679/AMP/AE-I/SMD | 03/06/2020 | 23/06/2020 | GLACIER ENGINEERING CO. | 0.86 | 0.86 | 100 | 0
116 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Basanti, Canning-I/II, Baruipur, Mograhat & Sonarpur, Mathurapur-I/II and Kultali Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical | SM/09196 | Disaster | Cont order for Emergency hiring charges of 50 KVA Mobile silent type diesel generator set on the situation of AMPHAN 2020 for PH-1 of Koaberia water supply scheme under SMD, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/003186/2020-2021 | 734/AMP/AE-I/SMD | 06/06/2020 | 26/06/2020 | GLACIER ENGINEERING CO. | 0.86 | 0.86 | 100 | 0
117 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Basanti, Canning-I/II, Baruipur, Mograhat & Sonarpur, Mathurapur-I/II and Kultali Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical | SM/09196 | Disaster | Cont order for Emergency hiring charges of 50 KVA Mobile silent type diesel generator set on the situation of AMPHAN 2020 for PH-1 of Koaberia water supply scheme under SMD, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/003187/2020-2021 | 900/AMP/AE-I/SMD | 24/06/2020 | 14/07/2020 | GLACIER ENGINEERING CO. | 0.86 | 0.86 | 100 | 0
118 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Basanti, Canning-I/II, Baruipur, Mograhat & Sonarpur, Mathurapur-I/II and Kultali Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical | SM/09196 | Disaster | Cont order for Emergency hiring charges of 50 KVA Mobile silent type diesel generator set on the situation of AMPHAN 2020 for PH-1 of Koaberia water supply scheme under SMD, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/003188/2020-2021 | 410/AMP/AE-I/SMD | 21/05/2020 | 10/06/2020 | GLACIER ENGINEERING CO. | 0.86 | 0.86 | 100 | 0
119 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Basanti, Canning-I/II, Baruipur, Mograhat & Sonarpur, Mathurapur-I/II and Kultali Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical | SM/09196 | Disaster | Electric Bill |  |  | VCH/000149/2022-2023 | 04/PFMS | 08/04/2022 |  | WBSEDCL | 0.11 | 0 | 0 | 0
120 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water, DG sets and allied works at Basanti, Canning-I/II, Baruipur, Mograhat & Sonarpur, Mathurapur-I/II and Kultali Block in the district of South 24 Parganas in connection with the Cyclone Yaas under South 24 Pgns Mechanical | SM/09196 | Disaster | Contingency Payment |  |  | VCH/000212/2022-2023 | 19/PFMS | 18/04/2022 |  | MINATI GHOSH | 0.08 | 0 | 0 | 0
Total | [13 empty] | 288.09 | 277.06 | 96.17