## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water (Pouches / Bottles) to Alipore Sub-Division, Diamond Harbour Sub-Division, Kakdwip Sub-Division and some other places of South 24 Pgns district to combat Cyclone Yaas from Dakshin Roypur Bottling Plant under South 24 Pgns | SM/09197 | Disaster | Cont. order for Carriage of packaged drinking water bottle & self contained water pouches from MTU at Kakdwip / Sagar to different loacations in connection with preparedness of cyclonic storm YAAS under South 24-Pgs Mechanical Division, PHE Dte. |  |  | ORD/000464/2021-2022 | 167/YAAS/SMD | 30/05/2021 | 19/06/2021 | M/S. S.S. ENTERPRISE | 4.88 | 4.88 | 100 | 0
2 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water (Pouches / Bottles) to Alipore Sub-Division, Diamond Harbour Sub-Division, Kakdwip Sub-Division and some other places of South 24 Pgns district to combat Cyclone Yaas from Dakshin Roypur Bottling Plant under South 24 Pgns | SM/09197 | Disaster | Cont. order for Carriage of packaged drinking water bottle & self contained water pouches from MTU at Kakdwip / Sagar to different loacations in connection with preparedness of cyclonic storm YAAS under South 24-Pgs Mechanical Division, PHE Dte. |  |  | ORD/000466/2021-2022 | 169/YAAS/SMD | 31/05/2021 | 20/06/2021 | M/S. S.S. ENTERPRISE | 4.88 | 4.88 | 100 | 0
3 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water (Pouches / Bottles) to Alipore Sub-Division, Diamond Harbour Sub-Division, Kakdwip Sub-Division and some other places of South 24 Pgns district to combat Cyclone Yaas from Dakshin Roypur Bottling Plant under South 24 Pgns | SM/09197 | Disaster | Carriage of packaged drinking water bottle & self contained water pouches from MTU at Basanti / Baruipur to different loacations in connection with preparedness of cyclonic storm YAAS under South 24-Pgs Mechanical Division, PHE Dte. |  |  | ORD/000470/2021-2022 | 180/YAAS/SMD | 06/06/2021 | 26/06/2021 | M/S. S.S. ENTERPRISE | 4.94 | 4.94 | 100 | 0
4 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water (Pouches / Bottles) to Alipore Sub-Division, Diamond Harbour Sub-Division, Kakdwip Sub-Division and some other places of South 24 Pgns district to combat Cyclone Yaas from Dakshin Roypur Bottling Plant under South 24 Pgns | SM/09197 | Disaster | Cont. order for Carriage of packaged drinking water bottle & self contained water pouches from MTU at Kakdwip / Sagar to different loacations in connection with preparedness of cyclonic storm YAAS under South 24-Pgs Mechanical Division, PHE Dte. |  |  | ORD/000473/2021-2022 | 178/YAAS/SMD | 05/06/2021 | 25/06/2021 | M/S. S.S. ENTERPRISE | 4.88 | 4.88 | 100 | 0
5 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water (Pouches / Bottles) to Alipore Sub-Division, Diamond Harbour Sub-Division, Kakdwip Sub-Division and some other places of South 24 Pgns district to combat Cyclone Yaas from Dakshin Roypur Bottling Plant under South 24 Pgns | SM/09197 | Disaster | Cont. order for Carriage of packaged drinking water bottle & self contained water pouches from MTU at Kakdwip / Sagar to different loacations in connection with preparedness of cyclonic storm YAAS under South 24-Pgs Mechanical Division, PHE Dte. |  |  | ORD/000476/2021-2022 | 181/YAAS/SMD | 06/06/2021 | 26/06/2021 | M/S. S.S. ENTERPRISE | 4.88 | 4.88 | 100 | 0
6 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water (Pouches / Bottles) to Alipore Sub-Division, Diamond Harbour Sub-Division, Kakdwip Sub-Division and some other places of South 24 Pgns district to combat Cyclone Yaas from Dakshin Roypur Bottling Plant under South 24 Pgns | SM/09197 | Disaster | Cont. order for Carriage of packaged drinking water bottle & self contained water pouches from MTU at Kakdwip / Sagar to different loacations in connection with preparedness of cyclonic storm YAAS under South 24-Pgs Mechanical Division, PHE Dte. |  |  | ORD/000478/2021-2022 | 183/YAAS/SMD | 08/06/2021 | 28/06/2021 | M/S. S.S. ENTERPRISE | 4.88 | 4.88 | 100 | 0
7 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water (Pouches / Bottles) to Alipore Sub-Division, Diamond Harbour Sub-Division, Kakdwip Sub-Division and some other places of South 24 Pgns district to combat Cyclone Yaas from Dakshin Roypur Bottling Plant under South 24 Pgns | SM/09197 | Disaster | Cont. order for Carriage of packaged drinking water bottle & self contained water pouches from MTU at Kakdwip / Sagar to different loacations in connection with preparedness of cyclonic storm YAAS under South 24-Pgs Mechanical Division, PHE Dte. |  |  | ORD/000484/2021-2022 | 184/YAAS/SMD | 09/06/2021 | 29/06/2021 | M/S. S.S. ENTERPRISE | 4.88 | 4.88 | 100 | 0
8 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water (Pouches / Bottles) to Alipore Sub-Division, Diamond Harbour Sub-Division, Kakdwip Sub-Division and some other places of South 24 Pgns district to combat Cyclone Yaas from Dakshin Roypur Bottling Plant under South 24 Pgns | SM/09197 | Disaster | Cont. order for Carriage of packaged drinking water bottle & self contained water pouches from MTU at Kakdwip / Sagar to different loacations in connection with preparedness of cyclonic storm YAAS under South 24-Pgs Mechanical Division, PHE Dte. |  |  | ORD/000485/2021-2022 | 146/YAAS/SMD | 28/05/2021 | 17/06/2021 | M/S. S.S. ENTERPRISE | 4.88 | 4.88 | 100 | 0
9 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water (Pouches / Bottles) to Alipore Sub-Division, Diamond Harbour Sub-Division, Kakdwip Sub-Division and some other places of South 24 Pgns district to combat Cyclone Yaas from Dakshin Roypur Bottling Plant under South 24 Pgns | SM/09197 | Disaster | Cont. order for Carriage of packaged drinking water bottle & self contained water pouches from MTU at Kakdwip / Sagar to different loacations in connection with preparedness of cyclonic storm YAAS under South 24-Pgs Mechanical Division, PHE Dte. |  |  | ORD/000486/2021-2022 | 188/YAAS/SMD | 12/06/2021 | 02/07/2021 | M/S. S.S. ENTERPRISE | 2.05 | 2.05 | 100 | 0
10 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water (Pouches / Bottles) to Alipore Sub-Division, Diamond Harbour Sub-Division, Kakdwip Sub-Division and some other places of South 24 Pgns district to combat Cyclone Yaas from Dakshin Roypur Bottling Plant under South 24 Pgns | SM/09197 | Disaster | Cont. order for Carriage of packaged drinking water bottle & self contained water pouches from MTU at Kakdwip / Sagar to different loacations in connection with preparedness of cyclonic storm YAAS under South 24-Pgs Mechanical Division, PHE Dte. |  |  | ORD/000487/2021-2022 | 101/YAAS/SMD | 26/05/2021 | 15/06/2021 | M/S. S.S. ENTERPRISE | 4.88 | 4.88 | 100 | 0
11 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water (Pouches / Bottles) to Alipore Sub-Division, Diamond Harbour Sub-Division, Kakdwip Sub-Division and some other places of South 24 Pgns district to combat Cyclone Yaas from Dakshin Roypur Bottling Plant under South 24 Pgns | SM/09197 | Disaster | Cont. order for Carriage of packaged drinking water bottle & self contained water pouches from Dakshin Roypur to different loacations in connection with preparedness of cyclonic storm YAAS under South 24-Pgs Mechanical Division, PHE Dte. |  |  | ORD/000488/2021-2022 | 150/YAAS/SMD | 29/05/2021 | 18/06/2021 | M/S. S.S. ENTERPRISE | 2.74 | 2.74 | 100 | 0
12 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water (Pouches / Bottles) to Alipore Sub-Division, Diamond Harbour Sub-Division, Kakdwip Sub-Division and some other places of South 24 Pgns district to combat Cyclone Yaas from Dakshin Roypur Bottling Plant under South 24 Pgns | SM/09197 | Disaster | Cont. order for Carriage of packaged drinking water bottle & self contained water pouches from Dakshin Roypur to different loacations in connection with preparedness of cyclonic storm YAAS under South 24-Pgs Mechanical Division, PHE Dte. |  |  | ORD/000489/2021-2022 | 96/YAAS/SMD | 26/05/2021 | 15/06/2021 | M/S. S.S. ENTERPRISE | 4.74 | 0 | 0 | 0
13 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water (Pouches / Bottles) to Alipore Sub-Division, Diamond Harbour Sub-Division, Kakdwip Sub-Division and some other places of South 24 Pgns district to combat Cyclone Yaas from Dakshin Roypur Bottling Plant under South 24 Pgns | SM/09197 | Disaster | Cont. order for Carriage of packaged drinking water bottle & self contained water pouches from Dakshin Roypur to different loacations in connection with preparedness of cyclonic storm YAAS under South 24-Pgs Mechanical Division, PHE Dte. |  |  | ORD/000490/2021-2022 | 126/YAAS/SMD | 26/05/2021 | 15/06/2021 | M/S. S.S. ENTERPRISE | 4.74 | 4.74 | 100 | 0
14 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water (Pouches / Bottles) to Alipore Sub-Division, Diamond Harbour Sub-Division, Kakdwip Sub-Division and some other places of South 24 Pgns district to combat Cyclone Yaas from Dakshin Roypur Bottling Plant under South 24 Pgns | SM/09197 | Disaster | Cont. order for Carriage of packaged drinking water bottle & self contained water pouches from Dakshin Roypur to different loacations in connection with preparedness of cyclonic storm YAAS under South 24-Pgs Mechanical Division, PHE Dte. |  |  | ORD/000491/2021-2022 | 166/YAAS/SMD | 30/05/2021 | 19/06/2021 | M/S. S.S. ENTERPRISE | 0.44 | 0.44 | 100 | 0
15 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water (Pouches / Bottles) to Alipore Sub-Division, Diamond Harbour Sub-Division, Kakdwip Sub-Division and some other places of South 24 Pgns district to combat Cyclone Yaas from Dakshin Roypur Bottling Plant under South 24 Pgns | SM/09197 | Disaster | Cont. order for Carriage of packaged drinking water bottle & self contained water pouches from Dakshin Roypur to different loacations in connection with preparedness of cyclonic storm YAAS under South 24-Pgs Mechanical Division, PHE Dte. |  |  | ORD/000492/2021-2022 | 134/YAAS/SMD | 27/05/2021 | 16/06/2021 | M/S. S.S. ENTERPRISE | 4.21 | 4.21 | 100 | 0
16 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water (Pouches / Bottles) to Alipore Sub-Division, Diamond Harbour Sub-Division, Kakdwip Sub-Division and some other places of South 24 Pgns district to combat Cyclone Yaas from Dakshin Roypur Bottling Plant under South 24 Pgns | SM/09197 | Disaster | Cont. order for Carriage of packaged drinking water bottle & self contained water pouches from Dakshin Roypur to different loacations in connection with preparedness of cyclonic storm YAAS under South 24-Pgs Mechanical Division, PHE Dte. |  |  | ORD/000493/2021-2022 | 137/YAAS/SMD | 28/05/2021 | 17/06/2021 | M/S. S.S. ENTERPRISE | 4.21 | 4.21 | 100 | 0
17 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water (Pouches / Bottles) to Alipore Sub-Division, Diamond Harbour Sub-Division, Kakdwip Sub-Division and some other places of South 24 Pgns district to combat Cyclone Yaas from Dakshin Roypur Bottling Plant under South 24 Pgns | SM/09197 | Disaster | Cont. order for Carriage of packaged drinking water bottle & self contained water pouches from Dakshin Roypur to different loacations in connection with preparedness of cyclonic storm YAAS under South 24-Pgs Mechanical Division, PHE Dte. |  |  | ORD/000494/2021-2022 | 135/YAAS/SMD | 27/05/2021 | 16/06/2021 | M/S. S.S. ENTERPRISE | 4.21 | 4.21 | 100 | 0
18 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water (Pouches / Bottles) to Alipore Sub-Division, Diamond Harbour Sub-Division, Kakdwip Sub-Division and some other places of South 24 Pgns district to combat Cyclone Yaas from Dakshin Roypur Bottling Plant under South 24 Pgns | SM/09197 | Disaster | Cont. order for Carriage of packaged drinking water bottle & self contained water pouches from Dakshin Roypur to different loacations in connection with preparedness of cyclonic storm YAAS under South 24-Pgs Mechanical Division, PHE Dte. |  |  | ORD/000495/2021-2022 | 143/YAAS/SMD | 28/05/2021 | 17/06/2021 | M/S. S.S. ENTERPRISE | 2.74 | 2.74 | 100 | 0
19 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water (Pouches / Bottles) to Alipore Sub-Division, Diamond Harbour Sub-Division, Kakdwip Sub-Division and some other places of South 24 Pgns district to combat Cyclone Yaas from Dakshin Roypur Bottling Plant under South 24 Pgns | SM/09197 | Disaster | Cont. order for Carriage of packaged drinking water bottle & self contained water pouches from Dakshin Roypur to different loacations in connection with preparedness of cyclonic storm YAAS under South 24-Pgs Mechanical Division, PHE Dte. |  |  | ORD/000496/2021-2022 | 141/YAAS/SMD | 28/05/2021 | 17/06/2021 | M/S. S.S. ENTERPRISE | 2.74 | 2.74 | 100 | 0
20 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water (Pouches / Bottles) to Alipore Sub-Division, Diamond Harbour Sub-Division, Kakdwip Sub-Division and some other places of South 24 Pgns district to combat Cyclone Yaas from Dakshin Roypur Bottling Plant under South 24 Pgns | SM/09197 | Disaster | Cont. order for Carriage of packaged drinking water bottle & self contained water pouches from Dakshin Roypur to different loacations in connection with preparedness of cyclonic storm YAAS under South 24-Pgs Mechanical Division, PHE Dte. |  |  | ORD/000497/2021-2022 | 147/YAAS/SMD | 29/05/2021 | 18/06/2021 | M/S. S.S. ENTERPRISE | 2.74 | 2.74 | 100 | 0
21 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water (Pouches / Bottles) to Alipore Sub-Division, Diamond Harbour Sub-Division, Kakdwip Sub-Division and some other places of South 24 Pgns district to combat Cyclone Yaas from Dakshin Roypur Bottling Plant under South 24 Pgns | SM/09197 | Disaster | Cont. order for Carriage of packaged drinking water bottle & self contained water pouches from Dakshin Roypur to different loacations in connection with preparedness of cyclonic storm YAAS under South 24-Pgs Mechanical Division, PHE Dte. |  |  | ORD/000498/2021-2022 | 145/YAAS/SMD | 28/05/2021 | 17/06/2021 | M/S. S.S. ENTERPRISE | 2.74 | 2.74 | 100 | 0
22 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water (Pouches / Bottles) to Alipore Sub-Division, Diamond Harbour Sub-Division, Kakdwip Sub-Division and some other places of South 24 Pgns district to combat Cyclone Yaas from Dakshin Roypur Bottling Plant under South 24 Pgns | SM/09197 | Disaster | Cont. order for Carriage of packaged drinking water bottle & self contained water pouches from Dakshin Roypur to different loacations in connection with preparedness of cyclonic storm YAAS under South 24-Pgs Mechanical Division, PHE Dte. |  |  | ORD/000499/2021-2022 | 148/YAAS/SMD | 29/05/2021 | 18/06/2021 | M/S. S.S. ENTERPRISE | 2.74 | 2.74 | 100 | 0
23 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water (Pouches / Bottles) to Alipore Sub-Division, Diamond Harbour Sub-Division, Kakdwip Sub-Division and some other places of South 24 Pgns district to combat Cyclone Yaas from Dakshin Roypur Bottling Plant under South 24 Pgns | SM/09197 | Disaster | Carriage of packaged drinking water bottle & self contained water pouches from Basanti/Baruipur MTU to different loacations in connection with preparedness of cyclonic storm YAAS under South 24-Pgs Mechanical Division, PHE Dte. |  |  | ORD/000500/2021-2022 | 186/YAAS/SMD | 11/06/2021 | 01/07/2021 | M/S. S.S. ENTERPRISE | 2.62 | 2.57 | 98.18 | 0
24 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water (Pouches / Bottles) to Alipore Sub-Division, Diamond Harbour Sub-Division, Kakdwip Sub-Division and some other places of South 24 Pgns district to combat Cyclone Yaas from Dakshin Roypur Bottling Plant under South 24 Pgns | SM/09197 | Disaster | Carriage of packaged drinking water bottle & self contained water pouches from Basanti/Baruipur MTU to different loacations in connection with preparedness of cyclonic storm YAAS under South 24-Pgs Mechanical Division, PHE Dte. |  |  | ORD/000501/2021-2022 | 95/YAAS/SMD | 26/05/2021 | 15/06/2021 | M/S. S.S. ENTERPRISE | 4.94 | 4.94 | 100 | 0
25 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water (Pouches / Bottles) to Alipore Sub-Division, Diamond Harbour Sub-Division, Kakdwip Sub-Division and some other places of South 24 Pgns district to combat Cyclone Yaas from Dakshin Roypur Bottling Plant under South 24 Pgns | SM/09197 | Disaster | Carriage of packaged drinking water bottle & self contained water pouches from Basanti/Baruipur MTU to different loacations in connection with preparedness of cyclonic storm YAAS under South 24-Pgs Mechanical Division, PHE Dte. |  |  | ORD/000502/2021-2022 | 160/YAAS/SMD | 30/05/2021 | 19/06/2021 | M/S. S.S. ENTERPRISE | 4.94 | 4.94 | 100 | 0
26 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water (Pouches / Bottles) to Alipore Sub-Division, Diamond Harbour Sub-Division, Kakdwip Sub-Division and some other places of South 24 Pgns district to combat Cyclone Yaas from Dakshin Roypur Bottling Plant under South 24 Pgns | SM/09197 | Disaster | Cont. order for Carriage of packaged drinking water bottle & self contained water pouches from Gosaba Island in connection with preparedness of cyclonic storm YAAS under South 24-Pgs Mechanical Division, PHE Dte. |  |  | ORD/000503/2021-2022 | 170/YAAS/SMD | 01/06/2021 | 21/06/2021 | M/S. S.S. ENTERPRISE | 4.75 | 4.75 | 100 | 0
27 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water (Pouches / Bottles) to Alipore Sub-Division, Diamond Harbour Sub-Division, Kakdwip Sub-Division and some other places of South 24 Pgns district to combat Cyclone Yaas from Dakshin Roypur Bottling Plant under South 24 Pgns | SM/09197 | Disaster | Cont. order for Carriage of packaged drinking water bottle & self contained water pouches from Gosaba Island in connection with preparedness of cyclonic storm YAAS under South 24-Pgs Mechanical Division, PHE Dte. |  |  | ORD/000504/2021-2022 | 172/YAAS/SMD | 03/06/2021 | 23/06/2021 | M/S. S.S. ENTERPRISE | 4.75 | 4.75 | 100 | 0
28 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water (Pouches / Bottles) to Alipore Sub-Division, Diamond Harbour Sub-Division, Kakdwip Sub-Division and some other places of South 24 Pgns district to combat Cyclone Yaas from Dakshin Roypur Bottling Plant under South 24 Pgns | SM/09197 | Disaster | Cont. order for Carriage of packaged drinking water bottle & self contained water pouches from Gosaba Island in connection with preparedness of cyclonic storm YAAS under South 24-Pgs Mechanical Division, PHE Dte. |  |  | ORD/000505/2021-2022 | 174/YAAS/SMD | 03/06/2021 | 23/06/2021 | M/S. S.S. ENTERPRISE | 4.75 | 4.75 | 100 | 0
29 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water (Pouches / Bottles) to Alipore Sub-Division, Diamond Harbour Sub-Division, Kakdwip Sub-Division and some other places of South 24 Pgns district to combat Cyclone Yaas from Dakshin Roypur Bottling Plant under South 24 Pgns | SM/09197 | Disaster | Cont. order for Carriage of packaged drinking water bottle & self contained water pouches from Gosaba Island in connection with preparedness of cyclonic storm YAAS under South 24-Pgs Mechanical Division, PHE Dte. |  |  | ORD/000506/2021-2022 | 177/YAAS/SMD | 05/06/2021 | 25/06/2021 | M/S. S.S. ENTERPRISE | 4.75 | 4.75 | 100 | 0
30 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water (Pouches / Bottles) to Alipore Sub-Division, Diamond Harbour Sub-Division, Kakdwip Sub-Division and some other places of South 24 Pgns district to combat Cyclone Yaas from Dakshin Roypur Bottling Plant under South 24 Pgns | SM/09197 | Disaster | Cont. order for Carriage of packaged drinking water bottle & self contained water pouches from Gosaba Island in connection with preparedness of cyclonic storm YAAS under South 24-Pgs Mechanical Division, PHE Dte. |  |  | ORD/000507/2021-2022 | 179/YAAS/SMD | 06/06/2021 | 26/06/2021 | M/S. S.S. ENTERPRISE | 4.75 | 4.75 | 100 | 0
31 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water (Pouches / Bottles) to Alipore Sub-Division, Diamond Harbour Sub-Division, Kakdwip Sub-Division and some other places of South 24 Pgns district to combat Cyclone Yaas from Dakshin Roypur Bottling Plant under South 24 Pgns | SM/09197 | Disaster | Cont. order for Carriage of packaged drinking water bottle & self contained water pouches from Gosaba Island in connection with preparedness of cyclonic storm YAAS under South 24-Pgs Mechanical Division, PHE Dte. |  |  | ORD/000508/2021-2022 | 182/YAAS/SMD | 08/06/2021 | 28/06/2021 | M/S. S.S. ENTERPRISE | 4.75 | 4.75 | 100 | 0
32 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water (Pouches / Bottles) to Alipore Sub-Division, Diamond Harbour Sub-Division, Kakdwip Sub-Division and some other places of South 24 Pgns district to combat Cyclone Yaas from Dakshin Roypur Bottling Plant under South 24 Pgns | SM/09197 | Disaster | Cont. order for Carriage of packaged drinking water bottle & self contained water pouches from Gosaba Island in connection with preparedness of cyclonic storm YAAS under South 24-Pgs Mechanical Division, PHE Dte. |  |  | ORD/000509/2021-2022 | 185/YAAS/SMD | 11/06/2021 | 01/07/2021 | M/S. S.S. ENTERPRISE | 4.75 | 4.75 | 100 | 0
33 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water (Pouches / Bottles) to Alipore Sub-Division, Diamond Harbour Sub-Division, Kakdwip Sub-Division and some other places of South 24 Pgns district to combat Cyclone Yaas from Dakshin Roypur Bottling Plant under South 24 Pgns | SM/09197 | Disaster | Cont. order for Carriage of packaged drinking water bottle & self contained water pouches from Gosaba Island in connection with preparedness of cyclonic storm YAAS under South 24-Pgs Mechanical Division, PHE Dte. |  |  | ORD/000510/2021-2022 | 187/YAAS/SMD | 12/06/2021 | 02/07/2021 | M/S. S.S. ENTERPRISE | 4.75 | 4.75 | 100 | 0
34 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water (Pouches / Bottles) to Alipore Sub-Division, Diamond Harbour Sub-Division, Kakdwip Sub-Division and some other places of South 24 Pgns district to combat Cyclone Yaas from Dakshin Roypur Bottling Plant under South 24 Pgns | SM/09197 | Disaster | Cont. order for Carriage of packaged drinking water bottle & self contained water pouches from Gosaba Island in connection with preparedness of cyclonic storm YAAS under South 24-Pgs Mechanical Division, PHE Dte. |  |  | ORD/000511/2021-2022 | 189/YAAS/SMD | 14/06/2021 | 04/07/2021 | M/S. S.S. ENTERPRISE | 4.75 | 4.75 | 100 | 0
35 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water (Pouches / Bottles) to Alipore Sub-Division, Diamond Harbour Sub-Division, Kakdwip Sub-Division and some other places of South 24 Pgns district to combat Cyclone Yaas from Dakshin Roypur Bottling Plant under South 24 Pgns | SM/09197 | Disaster | Cont. order for Carriage of packaged drinking water bottle & self contained water pouches from Gosaba Island in connection with preparedness of cyclonic storm YAAS under South 24-Pgs Mechanical Division, PHE Dte. |  |  | ORD/000512/2021-2022 | 190/YAAS/SMD | 17/06/2021 | 07/07/2021 | M/S. S.S. ENTERPRISE | 4.75 | 4.75 | 100 | 0
36 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water (Pouches / Bottles) to Alipore Sub-Division, Diamond Harbour Sub-Division, Kakdwip Sub-Division and some other places of South 24 Pgns district to combat Cyclone Yaas from Dakshin Roypur Bottling Plant under South 24 Pgns | SM/09197 | Disaster | Cont. order for Carriage of packaged drinking water bottle & self contained water pouches from Gosaba Island in connection with preparedness of cyclonic storm YAAS under South 24-Pgs Mechanical Division, PHE Dte. |  |  | ORD/000513/2021-2022 | 191/YAAS/SMD | 18/06/2021 | 08/07/2021 | M/S. S.S. ENTERPRISE | 4.75 | 4.75 | 100 | 0
37 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water (Pouches / Bottles) to Alipore Sub-Division, Diamond Harbour Sub-Division, Kakdwip Sub-Division and some other places of South 24 Pgns district to combat Cyclone Yaas from Dakshin Roypur Bottling Plant under South 24 Pgns | SM/09197 | Disaster | Cont. order for Carriage of packaged drinking water bottle & self contained water pouches from Gosaba Island in connection with preparedness of cyclonic storm YAAS under South 24-Pgs Mechanical Division, PHE Dte. |  |  | ORD/000514/2021-2022 | 193/YAAS/SMD | 20/06/2021 | 10/07/2021 | M/S. S.S. ENTERPRISE | 4.75 | 4.75 | 100 | 0
38 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water (Pouches / Bottles) to Alipore Sub-Division, Diamond Harbour Sub-Division, Kakdwip Sub-Division and some other places of South 24 Pgns district to combat Cyclone Yaas from Dakshin Roypur Bottling Plant under South 24 Pgns | SM/09197 | Disaster | Cont. order for Carriage of packaged drinking water bottle & self contained water pouches from Gosaba Island in connection with preparedness of cyclonic storm YAAS under South 24-Pgs Mechanical Division, PHE Dte. |  |  | ORD/000515/2021-2022 | 194/YAAS/SMD | 23/06/2021 | 13/07/2021 | M/S. S.S. ENTERPRISE | 4.75 | 4.75 | 100 | 0
39 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water (Pouches / Bottles) to Alipore Sub-Division, Diamond Harbour Sub-Division, Kakdwip Sub-Division and some other places of South 24 Pgns district to combat Cyclone Yaas from Dakshin Roypur Bottling Plant under South 24 Pgns | SM/09197 | Disaster | Cont. order for Carriage of packaged drinking water bottle & self contained water pouches from Gosaba Island in connection with preparedness of cyclonic storm YAAS under South 24-Pgs Mechanical Division, PHE Dte. |  |  | ORD/000516/2021-2022 | 195/YAAS/SMD | 24/06/2021 | 14/07/2021 | M/S. S.S. ENTERPRISE | 4.75 | 4.75 | 100 | 0
40 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water (Pouches / Bottles) to Alipore Sub-Division, Diamond Harbour Sub-Division, Kakdwip Sub-Division and some other places of South 24 Pgns district to combat Cyclone Yaas from Dakshin Roypur Bottling Plant under South 24 Pgns | SM/09197 | Disaster | Cont. order for Carriage of packaged drinking water bottle & self contained water pouches from Gosaba Island in connection with preparedness of cyclonic storm YAAS under South 24-Pgs Mechanical Division, PHE Dte. |  |  | ORD/000517/2021-2022 | 196/YAAS/SMD | 26/06/2021 | 16/07/2021 | M/S. S.S. ENTERPRISE | 4.75 | 9.49 | 199.74 | 0
41 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water (Pouches / Bottles) to Alipore Sub-Division, Diamond Harbour Sub-Division, Kakdwip Sub-Division and some other places of South 24 Pgns district to combat Cyclone Yaas from Dakshin Roypur Bottling Plant under South 24 Pgns | SM/09197 | Disaster | Cont. order for Carriage of packaged drinking water bottle & self contained water pouches from Gosaba Island in connection with preparedness of cyclonic storm YAAS under South 24-Pgs Mechanical Division, PHE Dte. |  |  | ORD/000518/2021-2022 | 197/YAAS/SMD | 28/06/2021 | 18/07/2021 | M/S. S.S. ENTERPRISE | 4.18 | 4.18 | 100 | 0
42 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water (Pouches / Bottles) to Alipore Sub-Division, Diamond Harbour Sub-Division, Kakdwip Sub-Division and some other places of South 24 Pgns district to combat Cyclone Yaas from Dakshin Roypur Bottling Plant under South 24 Pgns | SM/09197 | Disaster | Cont. order for Carriage of packaged drinking water bottle & self contained water pouches from Gosaba Island in connection with preparedness of cyclonic storm YAAS under South 24-Pgs Mechanical Division, PHE Dte. |  |  | ORD/000519/2021-2022 | 168/YAAS/SMD | 31/05/2021 | 20/06/2021 | M/S. S.S. ENTERPRISE | 4.75 | 4.75 | 100 | 0
43 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water (Pouches / Bottles) to Alipore Sub-Division, Diamond Harbour Sub-Division, Kakdwip Sub-Division and some other places of South 24 Pgns district to combat Cyclone Yaas from Dakshin Roypur Bottling Plant under South 24 Pgns | SM/09197 | Disaster | Cont. order for Carriage of packaged drinking water bottle & self contained water pouches from Gosaba Island in connection with preparedness of cyclonic storm YAAS under South 24-Pgs Mechanical Division, PHE Dte. |  |  | ORD/000520/2021-2022 | 159/YAAS/SMD | 30/05/2021 | 19/06/2021 | M/S. S.S. ENTERPRISE | 4.75 | 4.75 | 100 | 0
44 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water (Pouches / Bottles) to Alipore Sub-Division, Diamond Harbour Sub-Division, Kakdwip Sub-Division and some other places of South 24 Pgns district to combat Cyclone Yaas from Dakshin Roypur Bottling Plant under South 24 Pgns | SM/09197 | Disaster | Cont. order for Carriage of packaged drinking water bottle & self contained water pouches from Gosaba Island in connection with preparedness of cyclonic storm YAAS under South 24-Pgs Mechanical Division, PHE Dte. |  |  | ORD/000521/2021-2022 | 149/YAAS/SMD | 29/05/2021 | 18/06/2021 | M/S. S.S. ENTERPRISE | 4.75 | 4.75 | 100 | 0
45 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water (Pouches / Bottles) to Alipore Sub-Division, Diamond Harbour Sub-Division, Kakdwip Sub-Division and some other places of South 24 Pgns district to combat Cyclone Yaas from Dakshin Roypur Bottling Plant under South 24 Pgns | SM/09197 | Disaster | Cont. order for Carriage of packaged drinking water bottle & self contained water pouches from Gosaba Island in connection with preparedness of cyclonic storm YAAS under South 24-Pgs Mechanical Division, PHE Dte. |  |  | ORD/000522/2021-2022 | 139/YAAS/SMD | 28/05/2021 | 17/06/2021 | M/S. S.S. ENTERPRISE | 4.75 | 4.75 | 100 | 0
46 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water (Pouches / Bottles) to Alipore Sub-Division, Diamond Harbour Sub-Division, Kakdwip Sub-Division and some other places of South 24 Pgns district to combat Cyclone Yaas from Dakshin Roypur Bottling Plant under South 24 Pgns | SM/09197 | Disaster | Cont. order for Carriage of packaged drinking water bottle & self contained water pouches from Gosaba Island in connection with preparedness of cyclonic storm YAAS under South 24-Pgs Mechanical Division, PHE Dte. |  |  | ORD/000523/2021-2022 | 127/YAAS/SMD | 27/05/2021 | 16/06/2021 | M/S. S.S. ENTERPRISE | 4.75 | 4.75 | 100 | 0
47 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water (Pouches / Bottles) to Alipore Sub-Division, Diamond Harbour Sub-Division, Kakdwip Sub-Division and some other places of South 24 Pgns district to combat Cyclone Yaas from Dakshin Roypur Bottling Plant under South 24 Pgns | SM/09197 | Disaster | Cont. order for Carriage of packaged drinking water bottle & self contained water pouches from Gosaba Island in connection with preparedness of cyclonic storm YAAS under South 24-Pgs Mechanical Division, PHE Dte. |  |  | ORD/000524/2021-2022 | 94/YAAS/SMD | 26/05/2021 | 15/06/2021 | M/S. S.S. ENTERPRISE | 4.75 | 4.75 | 100 | 0
48 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water (Pouches / Bottles) to Alipore Sub-Division, Diamond Harbour Sub-Division, Kakdwip Sub-Division and some other places of South 24 Pgns district to combat Cyclone Yaas from Dakshin Roypur Bottling Plant under South 24 Pgns | SM/09197 | Disaster | Cont. order for Supply & delivery of poly film roll for emergency production of drinking water pouch to combat Cyclone YAAS under SMD, PHE Dte. |  |  | ORD/000525/2021-2022 | 4/Yaas/I/SMD | 27/05/2021 | 16/06/2021 | M/S. S.S. ENTERPRISE | 0.97 | 0 | 0 | 0
49 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water (Pouches / Bottles) to Alipore Sub-Division, Diamond Harbour Sub-Division, Kakdwip Sub-Division and some other places of South 24 Pgns district to combat Cyclone Yaas from Dakshin Roypur Bottling Plant under South 24 Pgns | SM/09197 | Disaster | Cont. order for Supply & delivery of poly film roll for emergency production of drinking water pouch to combat Cyclone YAAS under SMD, PHE Dte. |  |  | ORD/000526/2021-2022 | 09/Yaas/I/SMD | 31/05/2021 | 20/06/2021 | M/S. S.S. ENTERPRISE | 0.97 | 0 | 0 | 0
50 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water (Pouches / Bottles) to Alipore Sub-Division, Diamond Harbour Sub-Division, Kakdwip Sub-Division and some other places of South 24 Pgns district to combat Cyclone Yaas from Dakshin Roypur Bottling Plant under South 24 Pgns | SM/09197 | Disaster | Cont. order for Supply & delivery of poly film roll for emergency production of drinking water pouch to combat Cyclone YAAS under SMD, PHE Dte. |  |  | ORD/000527/2021-2022 | 15/Yaas/I/SMD | 03/06/2021 | 23/06/2021 | M/S. S.S. ENTERPRISE | 0.97 | 0 | 0 | 0
51 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water (Pouches / Bottles) to Alipore Sub-Division, Diamond Harbour Sub-Division, Kakdwip Sub-Division and some other places of South 24 Pgns district to combat Cyclone Yaas from Dakshin Roypur Bottling Plant under South 24 Pgns | SM/09197 | Disaster | Cont. order for Supply & delivery of poly film roll for emergency production of drinking water pouch to combat Cyclone YAAS under SMD, PHE Dte. |  |  | ORD/000528/2021-2022 | 16/Yaas/I/SMD | 03/06/2021 | 23/06/2021 | M/S. S.S. ENTERPRISE | 0.97 | 0 | 0 | 0
52 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water (Pouches / Bottles) to Alipore Sub-Division, Diamond Harbour Sub-Division, Kakdwip Sub-Division and some other places of South 24 Pgns district to combat Cyclone Yaas from Dakshin Roypur Bottling Plant under South 24 Pgns | SM/09197 | Disaster | Cont. order for Supply & delivery of poly film roll for emergency production of drinking water pouch to combat Cyclone YAAS under SMD, PHE Dte. |  |  | ORD/000529/2021-2022 | 19/Yaas/I/SMD | 04/06/2021 | 24/06/2021 | M/S. S.S. ENTERPRISE | 0.97 | 0 | 0 | 0
53 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water (Pouches / Bottles) to Alipore Sub-Division, Diamond Harbour Sub-Division, Kakdwip Sub-Division and some other places of South 24 Pgns district to combat Cyclone Yaas from Dakshin Roypur Bottling Plant under South 24 Pgns | SM/09197 | Disaster | Cont. order for Supply & delivery of poly film roll for emergency production of drinking water pouch to combat Cyclone YAAS under SMD, PHE Dte. |  |  | ORD/000531/2021-2022 | 38/Yaas/I/SMD | 14/06/2021 | 04/07/2021 | M/S. S.S. ENTERPRISE | 0.97 | 0 | 0 | 0
54 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water (Pouches / Bottles) to Alipore Sub-Division, Diamond Harbour Sub-Division, Kakdwip Sub-Division and some other places of South 24 Pgns district to combat Cyclone Yaas from Dakshin Roypur Bottling Plant under South 24 Pgns | SM/09197 | Disaster | Cont. order for Supply & delivery of poly film roll for emergency production of drinking water pouch to combat Cyclone YAAS under SMD, PHE Dte. |  |  | ORD/000532/2021-2022 | 35/Yaas/I/SMD | 11/06/2021 | 01/07/2021 | M/S. S.S. ENTERPRISE | 0.97 | 0 | 0 | 0
55 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water (Pouches / Bottles) to Alipore Sub-Division, Diamond Harbour Sub-Division, Kakdwip Sub-Division and some other places of South 24 Pgns district to combat Cyclone Yaas from Dakshin Roypur Bottling Plant under South 24 Pgns | SM/09197 | Disaster | Cont. order for Supply & delivery of poly film roll for emergency production of drinking water pouch to combat Cyclone YAAS under SMD, PHE Dte. |  |  | ORD/000534/2021-2022 | 31/Yaas/I/SMD | 01/06/2021 | 21/06/2021 | M/S. S.S. ENTERPRISE | 0.97 | 0 | 0 | 0
56 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water (Pouches / Bottles) to Alipore Sub-Division, Diamond Harbour Sub-Division, Kakdwip Sub-Division and some other places of South 24 Pgns district to combat Cyclone Yaas from Dakshin Roypur Bottling Plant under South 24 Pgns | SM/09197 | Disaster | Cont. order for Supply & delivery of poly film roll for emergency production of drinking water pouch to combat Cyclone YAAS under SMD, PHE Dte. |  |  | ORD/000535/2021-2022 | 28/Yaas/I/SMD | 09/06/2021 | 29/06/2021 | M/S. S.S. ENTERPRISE | 0.97 | 0 | 0 | 0
57 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water (Pouches / Bottles) to Alipore Sub-Division, Diamond Harbour Sub-Division, Kakdwip Sub-Division and some other places of South 24 Pgns district to combat Cyclone Yaas from Dakshin Roypur Bottling Plant under South 24 Pgns | SM/09197 | Disaster | Cont. order for Supply & delivery of poly film roll for emergency production of drinking water pouch to combat Cyclone YAAS under SMD, PHE Dte. |  |  | ORD/000537/2021-2022 | 25/Yaas/I/SMD | 08/06/2021 | 28/06/2021 | M/S. S.S. ENTERPRISE | 0.97 | 0 | 0 | 0
58 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water (Pouches / Bottles) to Alipore Sub-Division, Diamond Harbour Sub-Division, Kakdwip Sub-Division and some other places of South 24 Pgns district to combat Cyclone Yaas from Dakshin Roypur Bottling Plant under South 24 Pgns | SM/09197 | Disaster | Cont. order for Supply & delivery of poly film roll for emergency production of drinking water pouch to combat Cyclone YAAS under SMD, PHE Dte. |  |  | ORD/000539/2021-2022 | 22/Yaas/I/SMD | 07/06/2021 | 27/06/2021 | M/S. S.S. ENTERPRISE | 0.97 | 0 | 0 | 0
59 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water (Pouches / Bottles) to Alipore Sub-Division, Diamond Harbour Sub-Division, Kakdwip Sub-Division and some other places of South 24 Pgns district to combat Cyclone Yaas from Dakshin Roypur Bottling Plant under South 24 Pgns | SM/09197 | Disaster | Cont. order for Supply & delivery of poly film roll for emergency production of drinking water pouch to combat Cyclone YAAS under SMD, PHE Dte. |  |  | ORD/000540/2021-2022 | 11/Yaas/I/SMD | 01/06/2021 | 21/06/2021 | M/S. S.S. ENTERPRISE | 0.97 | 0 | 0 | 0
60 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water (Pouches / Bottles) to Alipore Sub-Division, Diamond Harbour Sub-Division, Kakdwip Sub-Division and some other places of South 24 Pgns district to combat Cyclone Yaas from Dakshin Roypur Bottling Plant under South 24 Pgns | SM/09197 | Disaster | Cont. for Carriage of self contained water pouches to Various locations to combat with Cyclone YAAS under SMD, PHE Dte. |  |  | ORD/000542/2021-2022 | 37/Yaas/I/SMD | 14/06/2021 | 04/07/2021 | M/S. S.S. ENTERPRISE | 0.99 | 0 | 0 | 0
61 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water (Pouches / Bottles) to Alipore Sub-Division, Diamond Harbour Sub-Division, Kakdwip Sub-Division and some other places of South 24 Pgns district to combat Cyclone Yaas from Dakshin Roypur Bottling Plant under South 24 Pgns | SM/09197 | Disaster | Cont. for Carriage of self contained water pouches to Various locations to combat with Cyclone YAAS under SMD, PHE Dte. |  |  | ORD/000543/2021-2022 | 33/Yaas/I/SMD | 11/06/2021 | 01/07/2021 | M/S. S.S. ENTERPRISE | 0.99 | 0 | 0 | 0
62 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water (Pouches / Bottles) to Alipore Sub-Division, Diamond Harbour Sub-Division, Kakdwip Sub-Division and some other places of South 24 Pgns district to combat Cyclone Yaas from Dakshin Roypur Bottling Plant under South 24 Pgns | SM/09197 | Disaster | Cont. for Carriage of self contained water pouches to Various locations to combat with Cyclone YAAS under SMD, PHE Dte. |  |  | ORD/000545/2021-2022 | 39/Yaas/I/SMD | 15/06/2021 | 05/07/2021 | M/S. S.S. ENTERPRISE | 0.99 | 0 | 0 | 0
63 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water (Pouches / Bottles) to Alipore Sub-Division, Diamond Harbour Sub-Division, Kakdwip Sub-Division and some other places of South 24 Pgns district to combat Cyclone Yaas from Dakshin Roypur Bottling Plant under South 24 Pgns | SM/09197 | Disaster | Cont. for Carriage of self contained water pouches to Various locations to combat with Cyclone YAAS under SMD, PHE Dte. |  |  | ORD/000546/2021-2022 | 34/Yaas/I/SMD | 11/06/2021 | 01/07/2021 | M/S. S.S. ENTERPRISE | 0.99 | 0 | 0 | 0
64 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water (Pouches / Bottles) to Alipore Sub-Division, Diamond Harbour Sub-Division, Kakdwip Sub-Division and some other places of South 24 Pgns district to combat Cyclone Yaas from Dakshin Roypur Bottling Plant under South 24 Pgns | SM/09197 | Disaster | Cont. for Carriage of self contained water pouches to Various locations to combat with Cyclone YAAS under SMD, PHE Dte. |  |  | ORD/000547/2021-2022 | 36/Yaas/I/SMD | 14/06/2021 | 04/07/2021 | M/S. S.S. ENTERPRISE | 0.99 | 0 | 0 | 0
65 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water (Pouches / Bottles) to Alipore Sub-Division, Diamond Harbour Sub-Division, Kakdwip Sub-Division and some other places of South 24 Pgns district to combat Cyclone Yaas from Dakshin Roypur Bottling Plant under South 24 Pgns | SM/09197 | Disaster | Cont. for Carriage of self contained water pouches to Various locations to combat with Cyclone YAAS under SMD, PHE Dte. |  |  | ORD/000548/2021-2022 | 36/A/Yaas/I/SMD | 14/06/2021 | 04/07/2021 | M/S. S.S. ENTERPRISE | 0.99 | 0 | 0 | 0
66 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water (Pouches / Bottles) to Alipore Sub-Division, Diamond Harbour Sub-Division, Kakdwip Sub-Division and some other places of South 24 Pgns district to combat Cyclone Yaas from Dakshin Roypur Bottling Plant under South 24 Pgns | SM/09197 | Disaster | Carriage of self contained water pouches to Various locations to combat with Cyclone YAAS under SMD, PHE Dte. |  |  | ORD/000549/2021-2022 | 5/Yaas/I/SMD | 27/05/2021 | 16/06/2021 | M/S. S.S. ENTERPRISE | 0.99 | 0 | 0 | 0
67 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water (Pouches / Bottles) to Alipore Sub-Division, Diamond Harbour Sub-Division, Kakdwip Sub-Division and some other places of South 24 Pgns district to combat Cyclone Yaas from Dakshin Roypur Bottling Plant under South 24 Pgns | SM/09197 | Disaster | Cont. for Carriage of self contained water pouches to Various locations to combat with Cyclone YAAS under SMD, PHE Dte. |  |  | ORD/000551/2021-2022 | 07/Yaas/I/SMD | 28/05/2021 | 17/06/2021 | M/S. S.S. ENTERPRISE | 0.99 | 0 | 0 | 0
68 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water (Pouches / Bottles) to Alipore Sub-Division, Diamond Harbour Sub-Division, Kakdwip Sub-Division and some other places of South 24 Pgns district to combat Cyclone Yaas from Dakshin Roypur Bottling Plant under South 24 Pgns | SM/09197 | Disaster | Cont. for Carriage of self contained water pouches to Various locations to combat with Cyclone YAAS under SMD, PHE Dte. |  |  | ORD/000553/2021-2022 | 08/Yaas/I/SMD | 31/05/2021 | 20/06/2021 | M/S. S.S. ENTERPRISE | 0.99 | 0 | 0 | 0
69 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water (Pouches / Bottles) to Alipore Sub-Division, Diamond Harbour Sub-Division, Kakdwip Sub-Division and some other places of South 24 Pgns district to combat Cyclone Yaas from Dakshin Roypur Bottling Plant under South 24 Pgns | SM/09197 | Disaster | Cont. for Carriage of self contained water pouches to Various locations to combat with Cyclone YAAS under SMD, PHE Dte. |  |  | ORD/000556/2021-2022 | 10/Yaas/I/SMD | 01/06/2021 | 21/06/2021 | M/S. S.S. ENTERPRISE | 0.99 | 0 | 0 | 0
70 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water (Pouches / Bottles) to Alipore Sub-Division, Diamond Harbour Sub-Division, Kakdwip Sub-Division and some other places of South 24 Pgns district to combat Cyclone Yaas from Dakshin Roypur Bottling Plant under South 24 Pgns | SM/09197 | Disaster | Cont. for Carriage of self contained water pouches to Various locations to combat with Cyclone YAAS under SMD, PHE Dte. |  |  | ORD/000557/2021-2022 | 12/Yaas/I/SMD | 02/06/2021 | 22/06/2021 | M/S. S.S. ENTERPRISE | 0.99 | 0 | 0 | 0
71 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water (Pouches / Bottles) to Alipore Sub-Division, Diamond Harbour Sub-Division, Kakdwip Sub-Division and some other places of South 24 Pgns district to combat Cyclone Yaas from Dakshin Roypur Bottling Plant under South 24 Pgns | SM/09197 | Disaster | Cont. for Carriage of self contained water pouches to Various locations to combat with Cyclone YAAS under SMD, PHE Dte. |  |  | ORD/000558/2021-2022 | 13/Yaas/I/SMD | 02/06/2021 | 22/06/2021 | M/S. S.S. ENTERPRISE | 0.99 | 0 | 0 | 0
72 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water (Pouches / Bottles) to Alipore Sub-Division, Diamond Harbour Sub-Division, Kakdwip Sub-Division and some other places of South 24 Pgns district to combat Cyclone Yaas from Dakshin Roypur Bottling Plant under South 24 Pgns | SM/09197 | Disaster | Cont. for Carriage of self contained water pouches to Various locations to combat with Cyclone YAAS under SMD, PHE Dte. |  |  | ORD/000559/2021-2022 | 14/Yaas/I/SMD | 03/06/2021 | 23/06/2021 | M/S. S.S. ENTERPRISE | 0.99 | 0 | 0 | 0
73 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water (Pouches / Bottles) to Alipore Sub-Division, Diamond Harbour Sub-Division, Kakdwip Sub-Division and some other places of South 24 Pgns district to combat Cyclone Yaas from Dakshin Roypur Bottling Plant under South 24 Pgns | SM/09197 | Disaster | Cont. for Carriage of self contained water pouches to Various locations to combat with Cyclone YAAS under SMD, PHE Dte. |  |  | ORD/000560/2021-2022 | 17/Yaas/I/SMD | 04/06/2021 | 24/06/2021 | M/S. S.S. ENTERPRISE | 0.99 | 0 | 0 | 0
74 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water (Pouches / Bottles) to Alipore Sub-Division, Diamond Harbour Sub-Division, Kakdwip Sub-Division and some other places of South 24 Pgns district to combat Cyclone Yaas from Dakshin Roypur Bottling Plant under South 24 Pgns | SM/09197 | Disaster | Cont. for Carriage of self contained water pouches to Various locations to combat with Cyclone YAAS under SMD, PHE Dte. |  |  | ORD/000561/2021-2022 | 18/Yaas/I/SMD | 04/06/2021 | 24/06/2021 | M/S. S.S. ENTERPRISE | 0.99 | 0 | 0 | 0
75 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water (Pouches / Bottles) to Alipore Sub-Division, Diamond Harbour Sub-Division, Kakdwip Sub-Division and some other places of South 24 Pgns district to combat Cyclone Yaas from Dakshin Roypur Bottling Plant under South 24 Pgns | SM/09197 | Disaster | Cont. for Carriage of self contained water pouches to Various locations to combat with Cyclone YAAS under SMD, PHE Dte. |  |  | ORD/000562/2021-2022 | 23/Yaas/I/SMD | 07/06/2021 | 27/06/2021 | M/S. S.S. ENTERPRISE | 0.99 | 0 | 0 | 0
76 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water (Pouches / Bottles) to Alipore Sub-Division, Diamond Harbour Sub-Division, Kakdwip Sub-Division and some other places of South 24 Pgns district to combat Cyclone Yaas from Dakshin Roypur Bottling Plant under South 24 Pgns | SM/09197 | Disaster | Cont. for Carriage of self contained water pouches to Various locations to combat with Cyclone YAAS under SMD, PHE Dte. |  |  | ORD/000563/2021-2022 | 21/Yaas/I/SMD | 07/06/2021 | 27/06/2021 | M/S. S.S. ENTERPRISE | 0.99 | 0 | 0 | 0
77 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water (Pouches / Bottles) to Alipore Sub-Division, Diamond Harbour Sub-Division, Kakdwip Sub-Division and some other places of South 24 Pgns district to combat Cyclone Yaas from Dakshin Roypur Bottling Plant under South 24 Pgns | SM/09197 | Disaster | Cont. for Carriage of self contained water pouches to Various locations to combat with Cyclone YAAS under SMD, PHE Dte. |  |  | ORD/000564/2021-2022 | 24/Yaas/I/SMD | 08/06/2021 | 28/06/2021 | M/S. S.S. ENTERPRISE | 0.99 | 0 | 0 | 0
78 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water (Pouches / Bottles) to Alipore Sub-Division, Diamond Harbour Sub-Division, Kakdwip Sub-Division and some other places of South 24 Pgns district to combat Cyclone Yaas from Dakshin Roypur Bottling Plant under South 24 Pgns | SM/09197 | Disaster | Cont. for Carriage of self contained water pouches to Various locations to combat with Cyclone YAAS under SMD, PHE Dte. |  |  | ORD/000565/2021-2022 | 27/Yaas/I/SMD | 09/06/2021 | 29/06/2021 | M/S. S.S. ENTERPRISE | 0.99 | 0 | 0 | 0
79 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water (Pouches / Bottles) to Alipore Sub-Division, Diamond Harbour Sub-Division, Kakdwip Sub-Division and some other places of South 24 Pgns district to combat Cyclone Yaas from Dakshin Roypur Bottling Plant under South 24 Pgns | SM/09197 | Disaster | Cont. for Carriage of self contained water pouches to Various locations to combat with Cyclone YAAS under SMD, PHE Dte. |  |  | ORD/000568/2021-2022 | 26/Yaas/I/SMD | 09/06/2021 | 29/06/2021 | M/S. S.S. ENTERPRISE | 0.99 | 0 | 0 | 0
80 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water (Pouches / Bottles) to Alipore Sub-Division, Diamond Harbour Sub-Division, Kakdwip Sub-Division and some other places of South 24 Pgns district to combat Cyclone Yaas from Dakshin Roypur Bottling Plant under South 24 Pgns | SM/09197 | Disaster | Cont. for Carriage of self contained water pouches to Various locations to combat with Cyclone YAAS under SMD, PHE Dte. |  |  | ORD/000570/2021-2022 | 41/Yaas/I/SMD | 16/06/2021 | 06/07/2021 | M/S. S.S. ENTERPRISE | 0.99 | 0 | 0 | 0
81 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water (Pouches / Bottles) to Alipore Sub-Division, Diamond Harbour Sub-Division, Kakdwip Sub-Division and some other places of South 24 Pgns district to combat Cyclone Yaas from Dakshin Roypur Bottling Plant under South 24 Pgns | SM/09197 | Disaster | Cont. for Carriage of self contained water pouches to Various locations to combat with Cyclone YAAS under SMD, PHE Dte. |  |  | ORD/000571/2021-2022 | 40/Yaas/I/SMD | 16/06/2021 | 06/07/2021 | M/S. S.S. ENTERPRISE | 0.99 | 0 | 0 | 0
82 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water (Pouches / Bottles) to Alipore Sub-Division, Diamond Harbour Sub-Division, Kakdwip Sub-Division and some other places of South 24 Pgns district to combat Cyclone Yaas from Dakshin Roypur Bottling Plant under South 24 Pgns | SM/09197 | Disaster | Cont. for Carriage of self contained water pouches to Various locations to combat with Cyclone YAAS under SMD, PHE Dte. |  |  | ORD/000572/2021-2022 | 42/Yaas/I/SMD | 17/06/2021 | 07/07/2021 | M/S. S.S. ENTERPRISE | 0.12 | 0 | 0 | 0
83 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water (Pouches / Bottles) to Alipore Sub-Division, Diamond Harbour Sub-Division, Kakdwip Sub-Division and some other places of South 24 Pgns district to combat Cyclone Yaas from Dakshin Roypur Bottling Plant under South 24 Pgns | SM/09197 | Disaster | Cont. for Carriage of self contained water pouches to Various locations to combat with Cyclone YAAS under SMD, PHE Dte. |  |  | ORD/000573/2021-2022 | 30/Yaas/I/SMD | 10/06/2021 | 30/06/2021 | M/S. S.S. ENTERPRISE | 0.99 | 0 | 0 | 0
84 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water (Pouches / Bottles) to Alipore Sub-Division, Diamond Harbour Sub-Division, Kakdwip Sub-Division and some other places of South 24 Pgns district to combat Cyclone Yaas from Dakshin Roypur Bottling Plant under South 24 Pgns | SM/09197 | Disaster | Cont. for Carriage of self contained water pouches to Various locations to combat with Cyclone YAAS under SMD, PHE Dte. |  |  | ORD/000574/2021-2022 | 29/Yaas/I/SMD | 10/06/2021 | 30/06/2021 | M/S. S.S. ENTERPRISE | 0.99 | 0 | 0 | 0
85 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water (Pouches / Bottles) to Alipore Sub-Division, Diamond Harbour Sub-Division, Kakdwip Sub-Division and some other places of South 24 Pgns district to combat Cyclone Yaas from Dakshin Roypur Bottling Plant under South 24 Pgns | SM/09197 | Disaster | Continuation for Carriage of self contained water pouches to Various locations to combet with Cyclone "YAAS" under SMD PHE Dte. |  |  | ORD/000620/2021-2022 | 29/YAAS/I/SMSD. | 10/06/2021 | 30/06/2021 | M/S. S.S. ENTERPRISE | 0.99 | 0.99 | 100 | 0
86 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water (Pouches / Bottles) to Alipore Sub-Division, Diamond Harbour Sub-Division, Kakdwip Sub-Division and some other places of South 24 Pgns district to combat Cyclone Yaas from Dakshin Roypur Bottling Plant under South 24 Pgns | SM/09197 | Disaster | Continuation for Carriage of self contained water pouches to Various locations to combet with Cyclone "YAAS" under SMD PHE Dte. |  |  | ORD/000621/2021-2022 | 42/YAAS/I/SMSD. | 17/06/2021 | 07/07/2021 | M/S. S.S. ENTERPRISE | 0.12 | 0.12 | 100 | 0
87 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water (Pouches / Bottles) to Alipore Sub-Division, Diamond Harbour Sub-Division, Kakdwip Sub-Division and some other places of South 24 Pgns district to combat Cyclone Yaas from Dakshin Roypur Bottling Plant under South 24 Pgns | SM/09197 | Disaster | Continuation for Carriage of self contained water pouches to Various locations to combet with Cyclone "YAAS" under SMD PHE Dte. |  |  | ORD/000622/2021-2022 | 30/YAAS/I/SMSD. | 10/06/2021 | 30/06/2021 | M/S. S.S. ENTERPRISE | 0.99 | 0.99 | 100 | 0
88 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water (Pouches / Bottles) to Alipore Sub-Division, Diamond Harbour Sub-Division, Kakdwip Sub-Division and some other places of South 24 Pgns district to combat Cyclone Yaas from Dakshin Roypur Bottling Plant under South 24 Pgns | SM/09197 | Disaster | Continuation for Carriage of self contained water pouches to Various locations to combet with Cyclone "YAAS" under SMD PHE Dte. |  |  | ORD/000623/2021-2022 | 40/YAAS/I/SMSD. | 16/06/2021 | 06/07/2021 | M/S. S.S. ENTERPRISE | 0.99 | 0.99 | 100 | 0
89 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water (Pouches / Bottles) to Alipore Sub-Division, Diamond Harbour Sub-Division, Kakdwip Sub-Division and some other places of South 24 Pgns district to combat Cyclone Yaas from Dakshin Roypur Bottling Plant under South 24 Pgns | SM/09197 | Disaster | Continuation for Carriage of self contained water pouches to Various locations to combet with Cyclone "YAAS" under SMD PHE Dte. |  |  | ORD/000624/2021-2022 | 41/YAAS/SMSD. | 16/06/2021 | 06/07/2021 | M/S. S.S. ENTERPRISE | 0.99 | 0.99 | 100 | 0
90 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water (Pouches / Bottles) to Alipore Sub-Division, Diamond Harbour Sub-Division, Kakdwip Sub-Division and some other places of South 24 Pgns district to combat Cyclone Yaas from Dakshin Roypur Bottling Plant under South 24 Pgns | SM/09197 | Disaster | Continuation for Carriage of self contained water pouches to Various locations to combet with Cyclone "YAAS" under SMD PHE Dte. |  |  | ORD/000625/2021-2022 | 26/YAAS/I/SMSD. | 09/06/2021 | 29/06/2021 | M/S. S.S. ENTERPRISE | 0.99 | 0.99 | 100 | 0
91 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water (Pouches / Bottles) to Alipore Sub-Division, Diamond Harbour Sub-Division, Kakdwip Sub-Division and some other places of South 24 Pgns district to combat Cyclone Yaas from Dakshin Roypur Bottling Plant under South 24 Pgns | SM/09197 | Disaster | Continuation for Carriage of self contained water pouches to Various locations to combet with Cyclone "YAAS" under SMD PHE Dte. |  |  | ORD/000626/2021-2022 | 27/YAAS/I/SMSD. | 09/06/2021 | 29/06/2021 | M/S. S.S. ENTERPRISE | 0.99 | 0.99 | 100 | 0
92 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water (Pouches / Bottles) to Alipore Sub-Division, Diamond Harbour Sub-Division, Kakdwip Sub-Division and some other places of South 24 Pgns district to combat Cyclone Yaas from Dakshin Roypur Bottling Plant under South 24 Pgns | SM/09197 | Disaster | Continuation for Carriage of self contained water pouches to Various locations to combet with Cyclone "YAAS" under SMD PHE Dte. |  |  | ORD/000627/2021-2022 | 24/YAAS/I/SMSD. | 08/06/2021 | 28/06/2021 | M/S. S.S. ENTERPRISE | 0.99 | 0.99 | 100 | 0
93 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water (Pouches / Bottles) to Alipore Sub-Division, Diamond Harbour Sub-Division, Kakdwip Sub-Division and some other places of South 24 Pgns district to combat Cyclone Yaas from Dakshin Roypur Bottling Plant under South 24 Pgns | SM/09197 | Disaster | Continuation for Carriage of self contained water pouches to Various locations to combet with Cyclone "YAAS" under SMD PHE Dte. |  |  | ORD/000628/2021-2022 | 21/YAAS/I/SMSD. | 07/06/2021 | 27/06/2021 | M/S. S.S. ENTERPRISE | 0.99 | 0.99 | 100 | 0
94 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water (Pouches / Bottles) to Alipore Sub-Division, Diamond Harbour Sub-Division, Kakdwip Sub-Division and some other places of South 24 Pgns district to combat Cyclone Yaas from Dakshin Roypur Bottling Plant under South 24 Pgns | SM/09197 | Disaster | Continuation for Carriage of self contained water pouches to Various locations to combet with Cyclone "YAAS" under SMD PHE Dte. |  |  | ORD/000629/2021-2022 | 23/YAAS/I/SMSD. | 07/06/2021 | 27/06/2021 | M/S. S.S. ENTERPRISE | 0.99 | 0.99 | 100 | 0
95 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water (Pouches / Bottles) to Alipore Sub-Division, Diamond Harbour Sub-Division, Kakdwip Sub-Division and some other places of South 24 Pgns district to combat Cyclone Yaas from Dakshin Roypur Bottling Plant under South 24 Pgns | SM/09197 | Disaster | Continuation for Carriage of self contained water pouches to Various locations to combet with Cyclone "YAAS" under SMD PHE Dte. |  |  | ORD/000630/2021-2022 | 18/YAAS/I/SMSD. | 04/06/2021 | 24/06/2021 | M/S. S.S. ENTERPRISE | 0.99 | 0.99 | 100 | 0
96 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water (Pouches / Bottles) to Alipore Sub-Division, Diamond Harbour Sub-Division, Kakdwip Sub-Division and some other places of South 24 Pgns district to combat Cyclone Yaas from Dakshin Roypur Bottling Plant under South 24 Pgns | SM/09197 | Disaster | Continuation for Carriage of self contained water pouches to Various locations to combet with Cyclone "YAAS" under SMD PHE Dte. |  |  | ORD/000631/2021-2022 | 17/YAAS/I/SMSD. | 04/06/2021 | 24/06/2021 | M/S. S.S. ENTERPRISE | 0.99 | 0.99 | 100 | 0
97 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water (Pouches / Bottles) to Alipore Sub-Division, Diamond Harbour Sub-Division, Kakdwip Sub-Division and some other places of South 24 Pgns district to combat Cyclone Yaas from Dakshin Roypur Bottling Plant under South 24 Pgns | SM/09197 | Disaster | Continuation for Carriage of self contained water pouches to Various locations to combet with Cyclone "YAAS" under SMD PHE Dte. |  |  | ORD/000632/2021-2022 | 14/YAAS/I/SMSD. | 03/06/2021 | 23/06/2021 | M/S. S.S. ENTERPRISE | 0.99 | 0.99 | 100 | 0
98 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water (Pouches / Bottles) to Alipore Sub-Division, Diamond Harbour Sub-Division, Kakdwip Sub-Division and some other places of South 24 Pgns district to combat Cyclone Yaas from Dakshin Roypur Bottling Plant under South 24 Pgns | SM/09197 | Disaster | Continuation for Carriage of self contained water pouches to Various locations to combet with Cyclone "YAAS" under SMD PHE Dte. |  |  | ORD/000633/2021-2022 | 13/YAAS/I/SMSD. | 02/06/2021 | 22/06/2021 | M/S. S.S. ENTERPRISE | 0.99 | 0.99 | 100 | 0
99 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water (Pouches / Bottles) to Alipore Sub-Division, Diamond Harbour Sub-Division, Kakdwip Sub-Division and some other places of South 24 Pgns district to combat Cyclone Yaas from Dakshin Roypur Bottling Plant under South 24 Pgns | SM/09197 | Disaster | Cont. for Carriage of self contained water pouches to Various locations to combat with Cyclone YAAS under SMD, PHE Dte. |  |  | ORD/000634/2021-2022 | 12/YAAS/I/SMSD. | 02/06/2021 | 22/06/2021 | M/S. S.S. ENTERPRISE | 0.99 | 0.99 | 100 | 0
100 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water (Pouches / Bottles) to Alipore Sub-Division, Diamond Harbour Sub-Division, Kakdwip Sub-Division and some other places of South 24 Pgns district to combat Cyclone Yaas from Dakshin Roypur Bottling Plant under South 24 Pgns | SM/09197 | Disaster | Cont. for Carriage of self contained water pouches to Various locations to combat with Cyclone YAAS under SMD, PHE Dte. |  |  | ORD/000635/2021-2022 | 10/YAAS/I/SMSD. | 01/06/2021 | 21/06/2021 | M/S. S.S. ENTERPRISE | 0.99 | 0.99 | 100 | 0
101 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water (Pouches / Bottles) to Alipore Sub-Division, Diamond Harbour Sub-Division, Kakdwip Sub-Division and some other places of South 24 Pgns district to combat Cyclone Yaas from Dakshin Roypur Bottling Plant under South 24 Pgns | SM/09197 | Disaster | Cont. for Carriage of self contained water pouches to Various locations to combat with Cyclone YAAS under SMD, PHE Dte. |  |  | ORD/000636/2021-2022 | 08/YAAS/I/SMSD. | 31/05/2021 | 20/06/2021 | M/S. S.S. ENTERPRISE | 0.99 | 0.99 | 100 | 0
102 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water (Pouches / Bottles) to Alipore Sub-Division, Diamond Harbour Sub-Division, Kakdwip Sub-Division and some other places of South 24 Pgns district to combat Cyclone Yaas from Dakshin Roypur Bottling Plant under South 24 Pgns | SM/09197 | Disaster | Cont. for Carriage of self contained water pouches to Various locations to combat with Cyclone YAAS under SMD, PHE Dte. |  |  | ORD/000637/2021-2022 | 07/YAAS/I/SMSD. | 28/05/2021 | 17/06/2021 | M/S. S.S. ENTERPRISE | 0.99 | 0.99 | 100 | 0
103 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water (Pouches / Bottles) to Alipore Sub-Division, Diamond Harbour Sub-Division, Kakdwip Sub-Division and some other places of South 24 Pgns district to combat Cyclone Yaas from Dakshin Roypur Bottling Plant under South 24 Pgns | SM/09197 | Disaster | Cont. for Carriage of self contained water pouches to Various locations to combat with Cyclone YAAS under SMD, PHE Dte. |  |  | ORD/000638/2021-2022 | 05/YAAS/I/SMSD. | 27/05/2021 | 16/06/2021 | M/S. S.S. ENTERPRISE | 0.99 | 0.99 | 100 | 0
104 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water (Pouches / Bottles) to Alipore Sub-Division, Diamond Harbour Sub-Division, Kakdwip Sub-Division and some other places of South 24 Pgns district to combat Cyclone Yaas from Dakshin Roypur Bottling Plant under South 24 Pgns | SM/09197 | Disaster | Cont. for Carriage of self contained water pouches to Various locations to combat with Cyclone YAAS under SMD, PHE Dte. |  |  | ORD/000639/2021-2022 | 36/YAAS/I/SMD. | 14/06/2021 | 04/07/2021 | M/S. S.S. ENTERPRISE | 0.99 | 0.99 | 100 | 0
105 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water (Pouches / Bottles) to Alipore Sub-Division, Diamond Harbour Sub-Division, Kakdwip Sub-Division and some other places of South 24 Pgns district to combat Cyclone Yaas from Dakshin Roypur Bottling Plant under South 24 Pgns | SM/09197 | Disaster | Cont. for Carriage of self contained water pouches to Various locations to combat with Cyclone YAAS under SMD, PHE Dte. |  |  | ORD/000640/2021-2022 | 34/YAAS/I/SMSD. | 11/06/2021 | 01/07/2021 | M/S. S.S. ENTERPRISE | 0.99 | 0.99 | 100 | 0
106 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water (Pouches / Bottles) to Alipore Sub-Division, Diamond Harbour Sub-Division, Kakdwip Sub-Division and some other places of South 24 Pgns district to combat Cyclone Yaas from Dakshin Roypur Bottling Plant under South 24 Pgns | SM/09197 | Disaster | Cont. for Carriage of self contained water pouches to Various locations to combat with Cyclone YAAS under SMD, PHE Dte. |  |  | ORD/000641/2021-2022 | 39/YAAS/I/SMSD. | 15/06/2021 | 05/07/2021 | M/S. S.S. ENTERPRISE | 0.99 | 0.99 | 100 | 0
107 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water (Pouches / Bottles) to Alipore Sub-Division, Diamond Harbour Sub-Division, Kakdwip Sub-Division and some other places of South 24 Pgns district to combat Cyclone Yaas from Dakshin Roypur Bottling Plant under South 24 Pgns | SM/09197 | Disaster | Cont. for Carriage of self contained water pouches to Various locations to combat with Cyclone YAAS under SMD, PHE Dte. |  |  | ORD/000642/2021-2022 | 33/YAAS/I/SMSD. | 11/06/2021 | 01/07/2021 | M/S. S.S. ENTERPRISE | 0.99 | 0.99 | 100 | 0
108 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water (Pouches / Bottles) to Alipore Sub-Division, Diamond Harbour Sub-Division, Kakdwip Sub-Division and some other places of South 24 Pgns district to combat Cyclone Yaas from Dakshin Roypur Bottling Plant under South 24 Pgns | SM/09197 | Disaster | Cont. for Carriage of self contained water pouches to Various locations to combat with Cyclone YAAS under SMD, PHE Dte. |  |  | ORD/000643/2021-2022 | 37/YAAS/I/SMSD. | 14/06/2021 | 04/07/2021 | M/S. S.S. ENTERPRISE | 0.99 | 0.99 | 100 | 0
109 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water (Pouches / Bottles) to Alipore Sub-Division, Diamond Harbour Sub-Division, Kakdwip Sub-Division and some other places of South 24 Pgns district to combat Cyclone Yaas from Dakshin Roypur Bottling Plant under South 24 Pgns | SM/09197 | Disaster | Cont. for supply & delivery of Poly film roll for emergency production of drinking water pouches to combat with Cyclone YAAS under SMD, PHE Dte. |  |  | ORD/000644/2021-2022 | 11/YAAS/I/SMSD. | 01/06/2021 | 21/06/2021 | M/S. S.S. ENTERPRISE | 0.97 | 0.97 | 100 | 0
110 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water (Pouches / Bottles) to Alipore Sub-Division, Diamond Harbour Sub-Division, Kakdwip Sub-Division and some other places of South 24 Pgns district to combat Cyclone Yaas from Dakshin Roypur Bottling Plant under South 24 Pgns | SM/09197 | Disaster | Cont. for supply & delivery of Poly film roll for emergency production of drinking water pouches to combat with Cyclone YAAS under SMD, PHE Dte. |  |  | ORD/000645/2021-2022 | 22/YAAS/I/SMSD. | 07/06/2021 | 27/06/2021 | M/S. S.S. ENTERPRISE | 0.97 | 0.97 | 100 | 0
111 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water (Pouches / Bottles) to Alipore Sub-Division, Diamond Harbour Sub-Division, Kakdwip Sub-Division and some other places of South 24 Pgns district to combat Cyclone Yaas from Dakshin Roypur Bottling Plant under South 24 Pgns | SM/09197 | Disaster | Cont. for supply & delivery of Poly film roll for emergency production of drinking water pouches to combat with Cyclone YAAS under SMD, PHE Dte. |  |  | ORD/000646/2021-2022 | 25/YAAS/I/SMSD. | 08/06/2021 | 28/06/2021 | M/S. S.S. ENTERPRISE | 0.97 | 0.97 | 100 | 0
112 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water (Pouches / Bottles) to Alipore Sub-Division, Diamond Harbour Sub-Division, Kakdwip Sub-Division and some other places of South 24 Pgns district to combat Cyclone Yaas from Dakshin Roypur Bottling Plant under South 24 Pgns | SM/09197 | Disaster | Cont. for supply & delivery of Poly film roll for emergency production of drinking water pouches to combat with Cyclone YAAS under SMD, PHE Dte. |  |  | ORD/000647/2021-2022 | 28/YAAS/I/SMSD. | 09/06/2021 | 29/06/2021 | M/S. S.S. ENTERPRISE | 0.97 | 0.97 | 100 | 0
113 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water (Pouches / Bottles) to Alipore Sub-Division, Diamond Harbour Sub-Division, Kakdwip Sub-Division and some other places of South 24 Pgns district to combat Cyclone Yaas from Dakshin Roypur Bottling Plant under South 24 Pgns | SM/09197 | Disaster | Cont. for supply & delivery of Poly film roll for emergency production of drinking water pouches to combat with Cyclone YAAS under SMD, PHE Dte. |  |  | ORD/000648/2021-2022 | 31/YAAS/I/SMSD. | 10/06/2021 | 30/06/2021 | M/S. S.S. ENTERPRISE | 0.97 | 0.97 | 100 | 0
114 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water (Pouches / Bottles) to Alipore Sub-Division, Diamond Harbour Sub-Division, Kakdwip Sub-Division and some other places of South 24 Pgns district to combat Cyclone Yaas from Dakshin Roypur Bottling Plant under South 24 Pgns | SM/09197 | Disaster | Cont. for supply & delivery of Poly film roll for emergency production of drinking water pouches to combat with Cyclone YAAS under SMD, PHE Dte. |  |  | ORD/000649/2021-2022 | 35/YAAS/I/SMSD. | 11/06/2021 | 01/07/2021 | M/S. S.S. ENTERPRISE | 0.97 | 0.97 | 100 | 0
115 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water (Pouches / Bottles) to Alipore Sub-Division, Diamond Harbour Sub-Division, Kakdwip Sub-Division and some other places of South 24 Pgns district to combat Cyclone Yaas from Dakshin Roypur Bottling Plant under South 24 Pgns | SM/09197 | Disaster | Cont. for supply & delivery of Poly film roll for emergency production of drinking water pouches to combat with Cyclone YAAS under SMD, PHE Dte. |  |  | ORD/000650/2021-2022 | 38/YAAS/I/SMSD. | 14/06/2021 | 04/07/2021 | M/S. S.S. ENTERPRISE | 0.97 | 0.97 | 100 | 0
116 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water (Pouches / Bottles) to Alipore Sub-Division, Diamond Harbour Sub-Division, Kakdwip Sub-Division and some other places of South 24 Pgns district to combat Cyclone Yaas from Dakshin Roypur Bottling Plant under South 24 Pgns | SM/09197 | Disaster | Cont. for supply & delivery of Poly film roll for emergency production of drinking water pouches to combat with Cyclone YAAS under SMD, PHE Dte. |  |  | ORD/000651/2021-2022 | 19/YAAS/I/SMSD. | 04/06/2021 | 24/06/2021 | M/S. S.S. ENTERPRISE | 0.97 | 0.97 | 100 | 0
117 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water (Pouches / Bottles) to Alipore Sub-Division, Diamond Harbour Sub-Division, Kakdwip Sub-Division and some other places of South 24 Pgns district to combat Cyclone Yaas from Dakshin Roypur Bottling Plant under South 24 Pgns | SM/09197 | Disaster | Cont. for supply & delivery of Poly film roll for emergency production of drinking water pouches to combat with Cyclone YAAS under SMD, PHE Dte. |  |  | ORD/000652/2021-2022 | 16/YAAS/I/SMSD. | 03/06/2021 | 23/06/2021 | M/S. S.S. ENTERPRISE | 0.97 | 0.97 | 100 | 0
118 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water (Pouches / Bottles) to Alipore Sub-Division, Diamond Harbour Sub-Division, Kakdwip Sub-Division and some other places of South 24 Pgns district to combat Cyclone Yaas from Dakshin Roypur Bottling Plant under South 24 Pgns | SM/09197 | Disaster | Cont. for supply & delivery of Poly film roll for emergency production of drinking water pouches to combat with Cyclone YAAS under SMD, PHE Dte. |  |  | ORD/000653/2021-2022 | 15/YAAS/I/SMSD. | 03/06/2021 | 23/06/2021 | M/S. S.S. ENTERPRISE | 0.97 | 0.97 | 100 | 0
119 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water (Pouches / Bottles) to Alipore Sub-Division, Diamond Harbour Sub-Division, Kakdwip Sub-Division and some other places of South 24 Pgns district to combat Cyclone Yaas from Dakshin Roypur Bottling Plant under South 24 Pgns | SM/09197 | Disaster | Cont. for supply & delivery of Poly film roll for emergency production of drinking water pouches to combat with Cyclone YAAS under SMD, PHE Dte. |  |  | ORD/000654/2021-2022 | 09/YAAS/I/SMSD. | 31/05/2021 | 20/06/2021 | M/S. S.S. ENTERPRISE | 0.97 | 0.97 | 100 | 0
120 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water (Pouches / Bottles) to Alipore Sub-Division, Diamond Harbour Sub-Division, Kakdwip Sub-Division and some other places of South 24 Pgns district to combat Cyclone Yaas from Dakshin Roypur Bottling Plant under South 24 Pgns | SM/09197 | Disaster | Cont. for supply & delivery of Poly film roll for emergency production of drinking water pouches to combat with Cyclone YAAS under SMD, PHE Dte. |  |  | ORD/000655/2021-2022 | 04/YAAS/I/SMSD. | 27/05/2021 | 16/06/2021 | M/S. S.S. ENTERPRISE | 0.97 | 0 | 0 | 0
121 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water (Pouches / Bottles) to Alipore Sub-Division, Diamond Harbour Sub-Division, Kakdwip Sub-Division and some other places of South 24 Pgns district to combat Cyclone Yaas from Dakshin Roypur Bottling Plant under South 24 Pgns | SM/09197 | Disaster | Cont. order for Supply & delivery of polyfilm roll for emergency production of drinking water pouch to combat Cyclone YAAS under SMD, PHE Dte. |  |  | ORD/000656/2021-2022 | 04/YAAS/I/SMSD.. | 27/05/2021 | 16/06/2021 | M/S. S.S. ENTERPRISE | 0.97 | 0.97 | 100 | 0
122 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water (Pouches / Bottles) to Alipore Sub-Division, Diamond Harbour Sub-Division, Kakdwip Sub-Division and some other places of South 24 Pgns district to combat Cyclone Yaas from Dakshin Roypur Bottling Plant under South 24 Pgns | SM/09197 | Disaster | Providing diesel generator set at Dhapdhapi-II GP water supply scheme under Baruipur sub-Division for prepardness of cyclonic storm YAAS to maintain uninterruptred drinking water supply under South 24-Pgs Mechanical Division, PHE Dte. |  |  | ORD/000657/2021-2022 | 78/YAAS/SMD | 26/05/2021 | 15/06/2021 | S.P. CONSTRUCTION | 1.13 | 1.13 | 100 | 0
123 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water (Pouches / Bottles) to Alipore Sub-Division, Diamond Harbour Sub-Division, Kakdwip Sub-Division and some other places of South 24 Pgns district to combat Cyclone Yaas from Dakshin Roypur Bottling Plant under South 24 Pgns | SM/09197 | Disaster | Providing diesel generator set at OHR No - 46 water supply scheme under Baruipur sub-Division for prepardness of cyclonic storm YAAS to maintain uninterruptred drinking water supply under South 24-Pgs Mechanical Division, PHE Dte. |  |  | ORD/000658/2021-2022 | 75/YAAS/SMD | 26/05/2021 | 15/06/2021 | S.P. CONSTRUCTION | 2.44 | 2.44 | 100 | 0
124 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water (Pouches / Bottles) to Alipore Sub-Division, Diamond Harbour Sub-Division, Kakdwip Sub-Division and some other places of South 24 Pgns district to combat Cyclone Yaas from Dakshin Roypur Bottling Plant under South 24 Pgns | SM/09197 | Disaster | Supply and delivery of 10 sq.mm 4 core un-armoured round copper conductor cable for restoration of power in connection cyclonic storm YAAS at Khordanala PH-1 W/S Scheme of D.H -I Block under South 24-Pgs Mechanical Division, PHE Dte. |  |  | ORD/000659/2021-2022 | 1516/A/AE-II/SMD | 27/05/2021 | 11/06/2021 | S.P. CONSTRUCTION | 0.95 | 0.95 | 100 | 0
125 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water (Pouches / Bottles) to Alipore Sub-Division, Diamond Harbour Sub-Division, Kakdwip Sub-Division and some other places of South 24 Pgns district to combat Cyclone Yaas from Dakshin Roypur Bottling Plant under South 24 Pgns | SM/09197 | Disaster | Supply and delivery of 10 sq.mm 4 core un-armoured round copper conductor cable for restoration of power in connection cyclonic storm YAAS at Lakhipur PH-1 W/S Scheme of D.H -I Block under South 24-Pgs Mechanical Division, PHE Dte. |  |  | ORD/000660/2021-2022 | 1519/AE-II/SMD | 27/05/2021 | 11/06/2021 | S.P. CONSTRUCTION | 0.95 | 0.95 | 100 | 0
126 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water (Pouches / Bottles) to Alipore Sub-Division, Diamond Harbour Sub-Division, Kakdwip Sub-Division and some other places of South 24 Pgns district to combat Cyclone Yaas from Dakshin Roypur Bottling Plant under South 24 Pgns | SM/09197 | Disaster | Supply and delivery of 10 sq.mm 4 core un-armoured round copper conductor cable for restoration of power in connection cyclonic storm YAAS at Fatepur PH-1 W/S Scheme of Falta Block under South 24-Pgs Mechanical Division, PHE Dte. |  |  | ORD/000661/2021-2022 | 1520/A/AE-II/SMD | 27/05/2021 | 11/06/2021 | S.P. CONSTRUCTION | 0.95 | 0.95 | 100 | 0
127 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water (Pouches / Bottles) to Alipore Sub-Division, Diamond Harbour Sub-Division, Kakdwip Sub-Division and some other places of South 24 Pgns district to combat Cyclone Yaas from Dakshin Roypur Bottling Plant under South 24 Pgns | SM/09197 | Disaster | Supply and delivery of 10 sq.mm 4 core un-armoured round copper conductor cable for restoration of power in connection cyclonic storm YAAS at Khandalia PH-1 W/S Scheme of D.H.-I Block under South 24-Pgs Mechanical Division, PHE Dte. |  |  | ORD/000662/2021-2022 | 1521/AE-II/SMD | 27/05/2021 | 11/06/2021 | S.P. CONSTRUCTION | 0.95 | 0.95 | 100 | 0
128 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water (Pouches / Bottles) to Alipore Sub-Division, Diamond Harbour Sub-Division, Kakdwip Sub-Division and some other places of South 24 Pgns district to combat Cyclone Yaas from Dakshin Roypur Bottling Plant under South 24 Pgns | SM/09197 | Disaster | Supply and delivery of 10 sq.mm 4 core un-armoured round copper conductor cable for restoration of power in connection cyclonic storm YAAS at OHR Zone-1 W/S Scheme of Fata Block under South 24-Pgs Mechanical Division, PHE Dte. |  |  | ORD/000663/2021-2022 | 1508/A/AE-II/SMD | 27/05/2021 | 11/06/2021 | S.P. CONSTRUCTION | 0.95 | 0.95 | 100 | 0
129 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water (Pouches / Bottles) to Alipore Sub-Division, Diamond Harbour Sub-Division, Kakdwip Sub-Division and some other places of South 24 Pgns district to combat Cyclone Yaas from Dakshin Roypur Bottling Plant under South 24 Pgns | SM/09197 | Disaster | Supply and delivery of 10 sq.mm 4 core un-armoured round copper conductor cable for restoration of power in connection cyclonic storm YAAS at OHR Zone-8 W/S Scheme of Falta Block under South 24-Pgs Mechanical Division, PHE Dte. |  |  | ORD/000664/2021-2022 | 1509/AE-II/SMD | 27/05/2021 | 11/06/2021 | S.P. CONSTRUCTION | 0.95 | 0.95 | 100 | 0
130 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water (Pouches / Bottles) to Alipore Sub-Division, Diamond Harbour Sub-Division, Kakdwip Sub-Division and some other places of South 24 Pgns district to combat Cyclone Yaas from Dakshin Roypur Bottling Plant under South 24 Pgns | SM/09197 | Disaster | Supply and delivery of 10 sq.mm 4 core un-armoured round copper conductor cable for restoration of power in connection cyclonic storm YAAS at Mollapukur PH-2 W/S Scheme of D.H-I Block under South 24-Pgs Mechanical Division, PHE Dte. |  |  | ORD/000665/2021-2022 | 1520/AE-II/SMD | 27/05/2021 | 11/06/2021 | S.P. CONSTRUCTION | 0.95 | 0.95 | 100 | 0
131 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water (Pouches / Bottles) to Alipore Sub-Division, Diamond Harbour Sub-Division, Kakdwip Sub-Division and some other places of South 24 Pgns district to combat Cyclone Yaas from Dakshin Roypur Bottling Plant under South 24 Pgns | SM/09197 | Disaster | Supply and delivery of 10 sq.mm 4 core un-armoured round copper conductor cable for restoration of power in connection cyclonic storm YAAS at Mongrajpur PH-2 W/S Scheme of D.H-I Block under South 24-Pgs Mechanical Division, PHE Dte. |  |  | ORD/000666/2021-2022 | 1512/AE-II/SMD | 27/05/2021 | 11/06/2021 | S.P. CONSTRUCTION | 0.95 | 0.95 | 100 | 0
132 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water (Pouches / Bottles) to Alipore Sub-Division, Diamond Harbour Sub-Division, Kakdwip Sub-Division and some other places of South 24 Pgns district to combat Cyclone Yaas from Dakshin Roypur Bottling Plant under South 24 Pgns | SM/09197 | Disaster | Supply & delivery of 10 sq.mm. 4 crore un-armored round copper conductor cable for restoration of power in connection with Cyclone YASH at Harindanga PH-1 w/s scheme of Falta Block under SMD, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000668/2021-2022 | 1518/A/AE-II/SMD. | 27/05/2021 | 16/06/2021 | S.P. CONSTRUCTION | 0.9 | 0 | 0 | 0
133 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water (Pouches / Bottles) to Alipore Sub-Division, Diamond Harbour Sub-Division, Kakdwip Sub-Division and some other places of South 24 Pgns district to combat Cyclone Yaas from Dakshin Roypur Bottling Plant under South 24 Pgns | SM/09197 | Disaster | Supply, delivery & temporary installation of main switch, changeover & cable for DG set connection during super cyclone AMPHAN AT Bhogali & Koaberia w/s scheme under SMD, PHE Dte. |  |  | ORD/000670/2021-2022 | 253/AE-I/SMD | 28/04/2021 | 18/05/2021 | R.K. CONSTRUCTION | 0.59 | 0.59 | 100 | 0
134 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water (Pouches / Bottles) to Alipore Sub-Division, Diamond Harbour Sub-Division, Kakdwip Sub-Division and some other places of South 24 Pgns district to combat Cyclone Yaas from Dakshin Roypur Bottling Plant under South 24 Pgns | SM/09197 | Disaster | Supply, delivery & temporary installation of main switch, changeover & cable for DG set connection during super cyclone AMPHAN at Hesamabad & Ramganga w/s scheme under SMD, PHE Dte. |  |  | ORD/000672/2021-2022 | 252/AE-I/SMD | 28/04/2021 | 18/05/2021 | R.K. CONSTRUCTION | 0.59 | 0.59 | 100 | 0
135 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water (Pouches / Bottles) to Alipore Sub-Division, Diamond Harbour Sub-Division, Kakdwip Sub-Division and some other places of South 24 Pgns district to combat Cyclone Yaas from Dakshin Roypur Bottling Plant under South 24 Pgns | SM/09197 | Disaster | Supply & delivery of 10 sq.mm. 4 crore un-armored round copper conductor cable for restoration of power in connection with Cyclone YASH at Dostipur PH-1 w/s scheme of Falta Block under SMD, PHE Dte. |  |  | ORD/000674/2021-2022 | 1517/A/AE-II/SMD. | 27/05/2021 | 16/06/2021 | S.P. CONSTRUCTION | 0.95 | 0.95 | 100 | 0
136 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water (Pouches / Bottles) to Alipore Sub-Division, Diamond Harbour Sub-Division, Kakdwip Sub-Division and some other places of South 24 Pgns district to combat Cyclone Yaas from Dakshin Roypur Bottling Plant under South 24 Pgns | SM/09197 | Disaster | Supply & delivery of 10 sq.mm. 4 crore un-armored round copper conductor cable for restoration of power in connection with Cyclone YASH at OHR Zone-20 w/s scheme of Falta Block under SMD, PHE Dte. |  |  | ORD/000676/2021-2022 | 1508/A/AE-II/SMD. | 27/05/2021 | 16/06/2021 | S.P. CONSTRUCTION | 0.95 | 0.95 | 100 | 0
137 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water (Pouches / Bottles) to Alipore Sub-Division, Diamond Harbour Sub-Division, Kakdwip Sub-Division and some other places of South 24 Pgns district to combat Cyclone Yaas from Dakshin Roypur Bottling Plant under South 24 Pgns | SM/09197 | Disaster | Cont order for Emergency hiring charges of 62.5 KVA Mobile silent type diesel generator set on the situation of AMPHAN 2020 for PH-1 of Akshaynagar Aug. water supply scheme under SMD, PHE Dte. |  |  | ORD/003189/2020-2021 | 638/AMP/AE-I/SMD | 31/05/2020 | 20/06/2020 | S.K. ENTERPRISE | 0.67 | 0.67 | 100 | 0
138 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water (Pouches / Bottles) to Alipore Sub-Division, Diamond Harbour Sub-Division, Kakdwip Sub-Division and some other places of South 24 Pgns district to combat Cyclone Yaas from Dakshin Roypur Bottling Plant under South 24 Pgns | SM/09197 | Disaster | Cont order for Emergency hiring charges of 62.5 KVA Mobile silent type diesel generator set on the situation of AMPHAN 2020 for PH-1 of Akshaynagar Aug. water supply scheme under SMD, PHE Dte. |  |  | ORD/003190/2020-2021 | 657/AMP/AE-I/SMD | 02/06/2020 | 22/06/2020 | S.K. ENTERPRISE | 0.67 | 0.67 | 100 | 0
139 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water (Pouches / Bottles) to Alipore Sub-Division, Diamond Harbour Sub-Division, Kakdwip Sub-Division and some other places of South 24 Pgns district to combat Cyclone Yaas from Dakshin Roypur Bottling Plant under South 24 Pgns | SM/09197 | Disaster | Cont order for Emergency hiring charges of 62.5 KVA Mobile silent type diesel generator set on the situation of AMPHAN 2020 for PH-3 of Akshaynagar Aug. water supply scheme under SMD, PHE Dte. |  |  | ORD/003191/2020-2021 | 747/AMP/AE-I/SMD | 07/06/2020 | 27/06/2020 | S.K. ENTERPRISE | 0.67 | 0.67 | 100 | 0
140 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water (Pouches / Bottles) to Alipore Sub-Division, Diamond Harbour Sub-Division, Kakdwip Sub-Division and some other places of South 24 Pgns district to combat Cyclone Yaas from Dakshin Roypur Bottling Plant under South 24 Pgns | SM/09197 | Disaster | Cont order for Emergency hiring charges of 62.5 KVA Mobile silent type diesel generator set on the situation of AMPHAN 2020 for PH-3 of Akshaynagar Aug. water supply scheme under SMD, PHE Dte. |  |  | ORD/003192/2020-2021 | 645/AMP/AE-I/SMD | 01/06/2020 | 21/06/2020 | S.K. ENTERPRISE | 0.67 | 0.67 | 100 | 0
141 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water (Pouches / Bottles) to Alipore Sub-Division, Diamond Harbour Sub-Division, Kakdwip Sub-Division and some other places of South 24 Pgns district to combat Cyclone Yaas from Dakshin Roypur Bottling Plant under South 24 Pgns | SM/09197 | Disaster | Cont order for Emergency hiring charges of 62.5 KVA Mobile silent type diesel generator set on the situation of AMPHAN 2020 for PH-2, Zone-II of Ganeshpur water supply scheme under SMD, PHE Dte. |  |  | ORD/003193/2020-2021 | 601/AMP/AE-I/SMD | 29/05/2020 | 18/06/2020 | S.K. ENTERPRISE | 0.67 | 0.67 | 100 | 0
142 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water (Pouches / Bottles) to Alipore Sub-Division, Diamond Harbour Sub-Division, Kakdwip Sub-Division and some other places of South 24 Pgns district to combat Cyclone Yaas from Dakshin Roypur Bottling Plant under South 24 Pgns | SM/09197 | Disaster | Cont order for Emergency hiring charges of 62.5 KVA Mobile silent type diesel generator set on the situation of AMPHAN 2020 for PH-2, Zone-II of Ganeshpur water supply scheme under SMD, PHE Dte. |  |  | ORD/003194/2020-2021 | 707/AMP/AE-I/SMD | 04/06/2020 | 24/06/2020 | S.K. ENTERPRISE | 0.67 | 0.67 | 100 | 0
143 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water (Pouches / Bottles) to Alipore Sub-Division, Diamond Harbour Sub-Division, Kakdwip Sub-Division and some other places of South 24 Pgns district to combat Cyclone Yaas from Dakshin Roypur Bottling Plant under South 24 Pgns | SM/09197 | Disaster | Cont order for Emergency hiring charges of 62.5 KVA Mobile silent type diesel generator set on the situation of AMPHAN 2020 for PH-2, Zone-II of Ganeshpur water supply scheme under SMD, PHE Dte. |  |  | ORD/003195/2020-2021 | 637/AMP/AE-I/SMD | 31/05/2020 | 20/06/2020 | S.K. ENTERPRISE | 0.67 | 0.67 | 100 | 0
144 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water (Pouches / Bottles) to Alipore Sub-Division, Diamond Harbour Sub-Division, Kakdwip Sub-Division and some other places of South 24 Pgns district to combat Cyclone Yaas from Dakshin Roypur Bottling Plant under South 24 Pgns | SM/09197 | Disaster | Cont order for Emergency hiring charges of 62.5 KVA Mobile silent type diesel generator set on the situation of AMPHAN 2020 for PH-2, Zone-II of Ganeshpur water supply scheme under SMD, PHE Dte. |  |  | ORD/003196/2020-2021 | 658/AMP/AE-I/SMD | 02/06/2020 | 22/06/2020 | S.K. ENTERPRISE | 0.67 | 0.67 | 100 | 0
145 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water (Pouches / Bottles) to Alipore Sub-Division, Diamond Harbour Sub-Division, Kakdwip Sub-Division and some other places of South 24 Pgns district to combat Cyclone Yaas from Dakshin Roypur Bottling Plant under South 24 Pgns | SM/09197 | Disaster | Cont order for Emergency hiring charges of 62.5 KVA Mobile silent type diesel generator set on the situation of AMPHAN 2020 for PH-2, Zone-II of Ganeshpur water supply scheme under SMD, PHE Dte. |  |  | ORD/003197/2020-2021 | 740/AMP/AE-I/SMD | 06/06/2020 | 26/06/2020 | S.K. ENTERPRISE | 0.67 | 0.67 | 100 | 0
146 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water (Pouches / Bottles) to Alipore Sub-Division, Diamond Harbour Sub-Division, Kakdwip Sub-Division and some other places of South 24 Pgns district to combat Cyclone Yaas from Dakshin Roypur Bottling Plant under South 24 Pgns | SM/09197 | Disaster | Cont order for Emergency hiring charges of 62.5 KVA Mobile silent type diesel generator set on the situation of AMPHAN 2020 for PH-3 of Akshaynagar Aug. water supply scheme under SMD, PHE Dte. |  |  | ORD/003198/2020-2021 | 619/AMP/AE-I/SMD | 30/05/2020 | 19/06/2020 | S.K. ENTERPRISE | 0.67 | 0.67 | 100 | 0
147 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water (Pouches / Bottles) to Alipore Sub-Division, Diamond Harbour Sub-Division, Kakdwip Sub-Division and some other places of South 24 Pgns district to combat Cyclone Yaas from Dakshin Roypur Bottling Plant under South 24 Pgns | SM/09197 | Disaster | Cont order for Emergency hiring charges of 62.5 KVA Mobile silent type diesel generator set on the situation of AMPHAN 2020 for PH-2, Zone-II of Left out area of Ganeshpur Mouza water supply scheme under SMD, PHE Dte. |  |  | ORD/003199/2020-2021 | 572/AMP/AE-I/SMD | 28/05/2020 | 17/06/2020 | S.K. ENTERPRISE | 0.67 | 0.67 | 100 | 0
148 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water (Pouches / Bottles) to Alipore Sub-Division, Diamond Harbour Sub-Division, Kakdwip Sub-Division and some other places of South 24 Pgns district to combat Cyclone Yaas from Dakshin Roypur Bottling Plant under South 24 Pgns | SM/09197 | Disaster | Emergency hiring charges of 62.5 KVA Mobile silent type diesel generator set on the situation of AMPHAN 2020 for PH-2, Zone-II of Left out area of Ganeshpur Mouza water supply scheme under SMD, PHE Dte. |  |  | ORD/003200/2020-2021 | 433/AE-I/SMD. | 21/05/2020 | 10/06/2020 | S.K. ENTERPRISE | 0.67 | 0.67 | 100 | 0
149 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water (Pouches / Bottles) to Alipore Sub-Division, Diamond Harbour Sub-Division, Kakdwip Sub-Division and some other places of South 24 Pgns district to combat Cyclone Yaas from Dakshin Roypur Bottling Plant under South 24 Pgns | SM/09197 | Disaster | Emergency hiring charges of 62.5 KVA Mobile silent type diesel generator set on the situation of AMPHAN 2020 for PH-2, Zone-II of Ganeshpur water supply scheme under SMD, PHE Dte. |  |  | ORD/003201/2020-2021 | 436/AMP/AE-I/SMD | 21/05/2020 | 10/06/2020 | S.K. ENTERPRISE | 0.67 | 0.67 | 100 | 0
150 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water (Pouches / Bottles) to Alipore Sub-Division, Diamond Harbour Sub-Division, Kakdwip Sub-Division and some other places of South 24 Pgns district to combat Cyclone Yaas from Dakshin Roypur Bottling Plant under South 24 Pgns | SM/09197 | Disaster | Emergency hiring charges of 62.5 KVA Mobile silent type diesel generator set on the situation of AMPHAN 2020 for PH-1 of Akshaynagar Aug. water supply scheme under SMD, PHE Dte. |  |  | ORD/003202/2020-2021 | 435/AMP/AE-I/SMD | 21/05/2020 | 10/06/2020 | S.K. ENTERPRISE | 0.67 | 0.67 | 100 | 0
151 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Providing packaged drinking water (Pouches / Bottles) to Alipore Sub-Division, Diamond Harbour Sub-Division, Kakdwip Sub-Division and some other places of South 24 Pgns district to combat Cyclone Yaas from Dakshin Roypur Bottling Plant under South 24 Pgns | SM/09197 | Disaster | Fuel Bills |  |  | VCH/004036/2021-2022 | 105/PFMS | 19/03/2022 |  | TEMPLE MOTORS | 0.38 | 0 | 0 | 0
Total | [13 empty] | 297.47 | 259.64 | 87.28