## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Solarisation of WBSEDCL energised pump house with Supply and Installation of Grid-connected Solar PV systems with Net Metering for Begampur (Zone-II), Begampur (Zone-I), Sitakundu (Zone-II) & Brindakhali-I PWSS at Baruipur Block under South 24 Pgs Mechani | SM/18743 |  | Solarisation of WBSEDCL energised pump house with supply and installaiton of Grid-connected solar PV systems with net metering at Brindakhali Zone-I water supply scheme at Baruipur Block under SMD, PHE Dte, District South 24 Parganas | Assistant Engineer | Junior Engineer | ORD/002436/2023-2024 | 727/SMD | 08/02/2024 | 08/04/2024 | M/S INSILICA | 5.68 | 0 | 0 | 0
2 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Solarisation of WBSEDCL energised pump house with Supply and Installation of Grid-connected Solar PV systems with Net Metering for Begampur (Zone-II), Begampur (Zone-I), Sitakundu (Zone-II) & Brindakhali-I PWSS at Baruipur Block under South 24 Pgs Mechani | SM/18743 |  | Solarisation of WBSEDCL energised pump house with supply and installaiton of Grid-connected solar PV systems with net metering at Sitakundu Zone-II water supply scheme at Baruipur Block under SMD, PHE Dte, District South 24 Parganas | Assistant Engineer | Junior Engineer | ORD/002437/2023-2024 | 772/SMD | 07/02/2024 | 07/04/2024 | M/S INSILICA | 5.68 | 0 | 0 | 0
3 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Solarisation of WBSEDCL energised pump house with Supply and Installation of Grid-connected Solar PV systems with Net Metering for Begampur (Zone-II), Begampur (Zone-I), Sitakundu (Zone-II) & Brindakhali-I PWSS at Baruipur Block under South 24 Pgs Mechani | SM/18743 |  | Solarisation of WBSEDCL energised pump house with supply and installation of Grid-connected solar PV systems with net metering at Begampur Zone-I water supply scheme at Baruipur Block under SMD, PHE Dte, District South 24 Parganas | Assistant Engineer | Junior Engineer | ORD/002438/2023-2024 | 771/SMD | 07/02/2024 | 07/04/2024 | M/S INSILICA | 5.68 | 0 | 0 | 0
Total | [13 empty] | 17.05 | 0 | 0