## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | House Hold Survey in connection with providing Functional Household Tap Connections(FHTC) for Bishnupur-I/II & Thakurpukur Mahestala Blocks. | SM/08064 | Support-M&E | Door to door survey, reassign survey, data correction upper ceiling fixation including uploading to JJM Portal and allied works regarding Functional Household Tap Connection (FHTC) for Bishnupur-I and Bishnupur-II Blocks under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgs. | AE SWSD-I,AE SWSD-II |  | ORD/000257/2021-2022 | 2703/SWD-I | 25/03/2022 | 09/04/2022 | SRIJON ENTERPRISE | 1.2 | 1.18 | 98.31 | 0
2 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | House Hold Survey in connection with providing Functional Household Tap Connections(FHTC) for Bishnupur-I/II & Thakurpukur Mahestala Blocks. | SM/08064 | Support-M&E | Functional Household Tap Connection door to door survey for Panchanan, Patharberia, Joychandipur & Ramkrishnapur Berhanpur G.P.s of Bishnupur-II Block under Surface Water based Water Supply Scheme in the Arsenic affected areas of South 24-Parganas |  |  | VCH/000276/2021-2022 | BP-2021-22-73 | 06/08/2021 |  | SRIJON ENTERPRISE | 3.51 | 0 | 0 | 0
3 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | House Hold Survey in connection with providing Functional Household Tap Connections(FHTC) for Bishnupur-I/II & Thakurpukur Mahestala Blocks. | SM/08064 | Support-M&E | Functional Household Tap Connection door to door survey for Bakhrahat & Chak Enyatnagar G.P.s of Bishnupur-II Block under Surface Water based Water Supply Scheme in the Arsenic affected areas of South 24-Parganas. |  |  | VCH/000277/2021-2022 | BP-2021-22-74 | 06/08/2021 |  | SRIJON ENTERPRISE | 2.85 | 0 | 0 | 0
4 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | House Hold Survey in connection with providing Functional Household Tap Connections(FHTC) for Bishnupur-I/II & Thakurpukur Mahestala Blocks. | SM/08064 | Support-M&E | Functional Household Tap Connection door to door survey for Khanganberia, Moukhali & Nahazari G.P.s of Bishnupur-II Block under Surface Water based Water Supply Scheme in the Arsenic affected areas of South 24-Parganas. |  |  | VCH/000278/2021-2022 | BP-2021-22-75 | 06/08/2021 |  | SRIJON ENTERPRISE | 4.15 | 0 | 0 | 0
5 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | House Hold Survey in connection with providing Functional Household Tap Connections(FHTC) for Bishnupur-I/II & Thakurpukur Mahestala Blocks. | SM/08064 | Support-M&E | Functional Household Tap Connection door to door survey for Chandi, Gobindapur, Kalicharanpur & Khagramuri G.P.s of Bishnupur-II Block under Surface Water based Water Supply Scheme in the Arsenic affected areas of South 24-Parganas. |  |  | VCH/000279/2021-2022 | BP-2021-22-76 | 06/08/2021 |  | SRIJON ENTERPRISE | 4.29 | 0 | 0 | 0
6 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | House Hold Survey in connection with providing Functional Household Tap Connections(FHTC) for Bishnupur-I/II & Thakurpukur Mahestala Blocks. | SM/08064 | Support-M&E | Payments towards logistics support for survey personnel for door to door survey of FHTC for Paschim Bishnupur & Purba Bishnupur G.P.s under Bishnupur-I Block under Surface Water based Water Supply Scheme in the Arsenic affected areas of South 24-Parganas under SWD-I, PHE Dte. |  |  | VCH/000424/2021-2022 | BP-2021-22-111 | 22/09/2021 |  | SUNNY CONSTRUCTION | 2.1 | 0 | 0 | 0
7 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | House Hold Survey in connection with providing Functional Household Tap Connections(FHTC) for Bishnupur-I/II & Thakurpukur Mahestala Blocks. | SM/08064 | Support-M&E | Payments towards logistics support for survey personnel for door to door survey of FHTC for Amgachia, Adharmanik & Bhandaria (Part-I) G.P.s under Bishnupur-I Block under Surface Water based Water Supply Scheme in the Arsenic affected areas of South 24-Parganas under SWD-I, PHE Dte. |  |  | VCH/000425/2021-2022 | BP-2021-22-112 | 22/09/2021 |  | SUNNY CONSTRUCTION | 1.87 | 0 | 0 | 0
8 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | House Hold Survey in connection with providing Functional Household Tap Connections(FHTC) for Bishnupur-I/II & Thakurpukur Mahestala Blocks. | SM/08064 | Support-M&E | Payments towards logistics support for survey personnel for door to door survey of FHTC for Chandi, Gobindapur, Kalicharanpur & Khagramuri G.P.s under Bishnupur-II Block under Surface Water based Water Supply Scheme in the Arsenic affected areas of South 24-Parganas under SWD-I, PHE Dte. |  |  | VCH/000434/2021-2022 | 120/W/SWD-I | 01/10/2021 |  | SRIJON ENTERPRISE | 2.49 | 0 | 0 | 0
9 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | House Hold Survey in connection with providing Functional Household Tap Connections(FHTC) for Bishnupur-I/II & Thakurpukur Mahestala Blocks. | SM/08064 | Support-M&E | Payments towards logistics support for survey personnel for door to door survey of FHTC for Khanganberia, Moukhali & Nahazari G.P.s under Bishnupur-II Block under Surface Water based Water Supply Scheme in the Arsenic affected areas of South 24-Parganas under SWD-I, PHE Dte. |  |  | VCH/000435/2021-2022 | 120/W/SWD-I | 01/10/2021 |  | SRIJON ENTERPRISE | 2.41 | 0 | 0 | 0
10 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | House Hold Survey in connection with providing Functional Household Tap Connections(FHTC) for Bishnupur-I/II & Thakurpukur Mahestala Blocks. | SM/08064 | Support-M&E | Payments towards logistics support for survey personnel for door to door survey of FHTC for Panchanan, Patharberia, Joychandipur & Ramkrishnapur Berhanpur G.P.s under Bishnupur-II Block under Surface Water based Water Supply Scheme in the Arsenic affected areas of South 24-Parganas under SWD-I, PHE Dte. |  |  | VCH/000436/2021-2022 | 120/W/SWD-I | 01/10/2021 |  | SRIJON ENTERPRISE | 2.04 | 0 | 0 | 0
11 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | House Hold Survey in connection with providing Functional Household Tap Connections(FHTC) for Bishnupur-I/II & Thakurpukur Mahestala Blocks. | SM/08064 | Support-M&E | Payments towards logistics support for survey personnel for door to door survey of FHTC for Bakhrahat & Chak Enayatnagar G.P.s under Bishnupur-II Block under Surface Water based Water Supply Scheme in the Arsenic affected areas of South 24-Parganas under SWD-I, PHE Dte. |  |  | VCH/000437/2021-2022 | 120/W/SWD-I | 01/10/2021 |  | SRIJON ENTERPRISE | 1.65 | 0 | 0 | 0
12 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | House Hold Survey in connection with providing Functional Household Tap Connections(FHTC) for Bishnupur-I/II & Thakurpukur Mahestala Blocks. | SM/08064 | Support-M&E | Payments towards logistics support for survey personnel for door to door survey of FHTC for Rasapunja G.P.s under Thakurpukur Maheshtala Block under Surface Water based Water Supply Scheme in the Arsenic affected areas of South 24-Parganas under SWD-I, PHE Dte. |  |  | VCH/000438/2021-2022 | 120/W/SWD-I | 01/10/2021 |  | SUNNY CONSTRUCTION | 1.05 | 0 | 0 | 0
13 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | House Hold Survey in connection with providing Functional Household Tap Connections(FHTC) for Bishnupur-I/II & Thakurpukur Mahestala Blocks. | SM/08064 | Support-M&E | Payments towards logistics support for survey personnel for door to door survey of FHTC for Keoradanga, Kulerdari & Panakua G.P.s under Bishnupur-I Block under Surface Water based Water Supply Scheme in the Arsenic affected areas of South 24-Parganas under SWD-I, PHE Dte |  |  | VCH/000439/2021-2022 | 120/W/SWD-I | 01/10/2021 |  | SUNNY CONSTRUCTION | 2.36 | 0 | 0 | 0
Total | [13 empty] | 31.96 | 1.18 | 3.68