## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Augmentation of surface water based water supply Scheme for the arsenic affected areas of Budge Budge-II, Bisnupur,-II and part of Budge Budge-I (Mayapur GP only) Blocks in the district of South 24 Parganas | SM/08869 | Augmentation | Payment of Additional Quotation for new service connection at Makhalia OHR (JL. No. 44) under Augmentation of Surface Water based Water Supply Scheme of Budge Budge - II, Bishnupur - II and part of Budge Budge - I Block Application ID - 100000099662 Reference ID - 860291532 |  |  | BILL/01177/2024-2025 | BP-2024-25-241 | 12/08/2024 |  | WBSEDCL | 4.29 | 0 | 0 | null
2 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Augmentation of surface water based water supply Scheme for the arsenic affected areas of Budge Budge-II, Bisnupur,-II and part of Budge Budge-I (Mayapur GP only) Blocks in the district of South 24 Parganas | SM/08869 | Augmentation | Payment of Additional Quotation for new service connection at Sultangunge OHR (JL. No. 66) under Augmentation of Surface Water based Water Supply Scheme of Budge Budge - II, Bishnupur - II and part of Budge Budge - I Block Application ID - 100000099751 Reference ID - 860291661 |  |  | BILL/01178/2024-2025 | BP-2024-25-242 | 12/08/2024 |  | WBSEDCL | 7.61 | 0 | 0 | null
3 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Augmentation of surface water based water supply Scheme for the arsenic affected areas of Budge Budge-II, Bisnupur,-II and part of Budge Budge-I (Mayapur GP only) Blocks in the district of South 24 Parganas | SM/08869 | Augmentation | Quotation for new power connection at Baratala OHR (JL No-73) under augmentation of Surface Water Based Water Supply Scheme under Budge-budge-II, Bishnupur-II and part of Budge-budge-I Block. Application No- 1007782240 Reference Id- 106600770 Application Type- New Connection. Quotation Date-16/05/2024 |  |  | BILL/01179/2024-2025 | BP-2024-25-243 | 12/08/2024 |  | WBSEDCL | 5.1 | 0 | 0 | null
4 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Augmentation of surface water based water supply Scheme for the arsenic affected areas of Budge Budge-II, Bisnupur,-II and part of Budge Budge-I (Mayapur GP only) Blocks in the district of South 24 Parganas | SM/08869 | Augmentation | Quotation for new power connection at Dhancheberia OHR (JL No-68) under augmentation of Surface Water Based Water Supply Scheme under Budge-budge-II, Bishnupur-II and part of Budge-budge-I Block. Application No- 1007782282 Reference Id- 106600776 Application Type- New Connection. Quotation Date-16/05/2024 |  |  | BILL/01180/2024-2025 | BP-2024-25-244 | 12/08/2024 |  | WBSEDCL | 4.15 | 0 | 0 | null
5 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Augmentation of surface water based water supply Scheme for the arsenic affected areas of Budge Budge-II, Bisnupur,-II and part of Budge Budge-I (Mayapur GP only) Blocks in the district of South 24 Parganas | SM/08869 | Augmentation | Quotation for new power connection at Arjapara OHR (JL-97) under augmentation of Surface Water Based Water Supply Scheme under Budge-budge-II, Bishnupur-II and part of Budge-budge-I Block. Application No- 1007782206 Reference Id- 106600759 Application Type- New Connection. Quotation Date-16/05/2024 |  |  | BILL/01181/2024-2025 | BP-2024-25-245 | 12/08/2024 |  | WBSEDCL | 3.79 | 0 | 0 | null
6 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Augmentation of surface water based water supply Scheme for the arsenic affected areas of Budge Budge-II, Bisnupur,-II and part of Budge Budge-I (Mayapur GP only) Blocks in the district of South 24 Parganas | SM/08869 | Augmentation | Quotation for new power connection at Sehai OHR (JL-88) under augmentation of Surface Water Based Water Supply Scheme under Budge-budge-II, Bishnupur-II and part of Budge-budge-I Block. Application No- 1007766051 Reference Id- 106592632 Application Type- New Connection. Quotation Date-16/05/2024 |  |  | BILL/01182/2024-2025 | BP-2024-25-246 | 12/08/2024 |  | WBSEDCL | 4.17 | 0 | 0 | null
7 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Augmentation of surface water based water supply Scheme for the arsenic affected areas of Budge Budge-II, Bisnupur,-II and part of Budge Budge-I (Mayapur GP only) Blocks in the district of South 24 Parganas | SM/08869 | Augmentation | Payment of Quotation for new service connection at Sultangunge OHR (JL. No. 66) under Augmentation of Surface Water based Water Supply Scheme of Budge Budge - II, Bishnupur - II and part of Budge Budge - I Block Application No. - 1007514551 Reference ID - 106460076 |  |  | BILL/01183/2024-2025 | BP-2024-25-247 | 12/08/2024 |  | WBSEDCL | 0.71 | 0 | 0 | null
8 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Augmentation of surface water based water supply Scheme for the arsenic affected areas of Budge Budge-II, Bisnupur,-II and part of Budge Budge-I (Mayapur GP only) Blocks in the district of South 24 Parganas | SM/08869 | Augmentation | Payment of Quotation for new service connection at Makhalia OHR (JL. No. 44) under Augmentation of Surface Water based Water Supply Scheme of Budge Budge - II, Bishnupur - II and part of Budge Budge - I Block Application No. - 1007514561 Reference ID - 106460075 |  |  | BILL/01185/2024-2025 | BP-2024-25-248 | 12/08/2024 |  | WBSEDCL | 0.71 | 0 | 0 | null
9 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Augmentation of surface water based water supply Scheme for the arsenic affected areas of Budge Budge-II, Bisnupur,-II and part of Budge Budge-I (Mayapur GP only) Blocks in the district of South 24 Parganas | SM/08869 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at newly sunk tube well of Pump House under Zone-5 ( Dakshin Bawali) water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Budge Budge-II] | Assistant Engineer -II | Junior Engineer | ORD/000239/2024-2025 | 2485/SMD | 05/08/2024 | 03/11/2024 | PADMA ENGINEERING CO. | 13.52 | 0 | 0 | 0
10 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Augmentation of surface water based water supply Scheme for the arsenic affected areas of Budge Budge-II, Bisnupur,-II and part of Budge Budge-I (Mayapur GP only) Blocks in the district of South 24 Parganas | SM/08869 | Augmentation | Supply, Installation & commissioning of secondary Gaseous Chlorination arrangement for 14 (Fourteen) Nos. OHR points within Budge Budge-II Block under Improvement of water supply [Phase-I] in Bishnupur-I, Bishnupur-II and Budge Budge-II Block in the District of South 24 Pgs. under SMD PHE Dte. | Assistant Engineer -II | Junior Engineer | ORD/002691/2023-2024 | 2943/SMD | 05/09/2023 | 30/08/2024 | ORIENTAL ENGINEERING CO. | 400.14 | 0 | 0 | 0
11 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Augmentation of surface water based water supply Scheme for the arsenic affected areas of Budge Budge-II, Bisnupur,-II and part of Budge Budge-I (Mayapur GP only) Blocks in the district of South 24 Parganas | SM/08869 | Augmentation | Supply, Installation & commissioning of secondary Gaseous chlorination arrangement for 15 (Fifteen) Nos. OHR points Within Bishnupur-II Block under Improvement of water supply [Phase-i] in Bishnupur-I, Bishnupur-II and Budge Budge- II Block in the district of South 24 Pgs. under SMD, PHE Dte. | Assistant Engineer -II | Junior Engineer | ORD/002692/2023-2024 | 2977/SMD | 12/09/2023 | 06/09/2024 | MACHINE SUPPLIERS SYNDICATE(PVT.) LTD. | 428.72 | 0 | 0 | 0
12 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Augmentation of surface water based water supply Scheme for the arsenic affected areas of Budge Budge-II, Bisnupur,-II and part of Budge Budge-I (Mayapur GP only) Blocks in the district of South 24 Parganas | SM/08869 | Augmentation | Providing Power supply with gaseous chlorination arrangement at Booster Pumping Station GLR of Bishnupur-II Block for the Augmentation of Surface water based water supply scheme of Budge Budge-II, Bishnupur-II and part of Budge Budge-I Blocks in the District of South 24Pgs under South 24Pgs. Mechanical Division PHE Dte. | Assistant Engineer -II | Junior Engineer | ORD/003200/2022-2023 | 694/SMD | 13/03/2023 | 07/03/2024 | MACHINE SUPPLIERS SYNDICATE(PVT.) LTD. | 391.59 | 88.59 | 22.62 | 45
13 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Augmentation of surface water based water supply Scheme for the arsenic affected areas of Budge Budge-II, Bisnupur,-II and part of Budge Budge-I (Mayapur GP only) Blocks in the district of South 24 Parganas | SM/08869 | Augmentation | Restoration of carriageway and Hard Sholder damaged due to laying of pipes by PHE Dte. Location - Ch.6.584 km to 14.50km along Burul Bowali Road under Diamond Harbour Highway Division in the district of South 24 Parganas. |  |  | BILL/01492/2023-2024 | BP-2023-24-499 | 24/11/2023 |  | EXECUTIVE ENGINEER, DIAMOND HARBOUR HIGHWAY DIVISION PW(ROADS) DTE. | 14.07 | 0 | 0 | 0
14 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Augmentation of surface water based water supply Scheme for the arsenic affected areas of Budge Budge-II, Bisnupur,-II and part of Budge Budge-I (Mayapur GP only) Blocks in the district of South 24 Parganas | SM/08869 | Augmentation | Surveying, Design, Construction, Supply, Laying, Erection & Commissioning of 1(one) Clear Water Reservoir and 1(one) Ground Level Reservoir, Pumping main (M.S., D.I. etc.) for conveyance of Treated water to 29 (Twenty Nine) nos. OHR sites(old and New) including construction of Pump Houses, Sub-Station Buildings, Chlorine and Chlorine Tonner Rooms, 16 (sixteen) nos new OHRs of different capacities, Boundary wall, land development, pathway, arboriculture, Distribution System(M.S. D.I./ uPVC/HDPE Pipes etc.) in all the 29(twenty Nine) distribution zones including providing functional household tap connections(FHTC) to all the rural households and Public Institutions(e.g. Schools, AWC, Health Centers etc.), pipe carrying bridges & pipe carrying supports and other related Structure, Restoration of Roads to its original condition as required and related Electro-Mechanical, Instrumentation and Supervisory Control and Data Acquisition System (SCADA) as per scope of works including 03(three) months trial run and 72 Hrs performance guarantee test followed by 60(Sixty) months operation and maintenance (O&M) for Augmentation of surface water based water supply Scheme for arsenic affected areas of BUDGE BUDGE-II, BISHNUPUR-II and part of BUDGE BUDGE-I (MAYAPUR GP only) Blocks in the district of South 24 Parganas. | AE SWSD-I,AE SWSD-II | JE2 | ORD/000002/2022-2023 | 799 /SWD-I | 06/07/2022 | 25/06/2024 | WPIL LTD. | 43087 | 21892.09 | 50.81 | 60
15 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Augmentation of surface water based water supply Scheme for the arsenic affected areas of Budge Budge-II, Bisnupur,-II and part of Budge Budge-I (Mayapur GP only) Blocks in the district of South 24 Parganas | SM/08869 | Augmentation | Providing FHTC in connection to "Augmentation of surface water based water supply scheme for Budge Budge-II, Bishnupur-II and Budge Budge-I Blocks (Mayapur GP only)" under South 24-Pgns. W/S Division-I, PHE Dte., District - South 24-Parganas. [No. of FHTC = 90081] | AE SWSD-I | JE-1 | ORD/000231/2023-2024 | 1375/SWD-I | 12/07/2023 | 08/01/2024 | WPIL LTD. | 3016.78 | 456.74 | 15.14 | 10
16 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Augmentation of surface water based water supply Scheme for the arsenic affected areas of Budge Budge-II, Bisnupur,-II and part of Budge Budge-I (Mayapur GP only) Blocks in the district of South 24 Parganas | SM/08869 | Augmentation | Construction of temporary Boundary Wall at Jagat Ballavpur JL 45 Dag No: 834, Kh -1 , Dist. South 24 Paraganas in connection with Augmentation of Budge Budge I/II and Bisnupur II Water Supply Scheme under South 24-Parganas Water Supply Division-I, PHE Dte. | AE SWSD-I |  | ORD/000443/2021-2022 | 2608/SWD-I | 15/03/2022 | 14/05/2022 | MS POUSALI ENTERPRISE | 1.86 | 1.79 | 96.3 | 100
17 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Augmentation of surface water based water supply Scheme for the arsenic affected areas of Budge Budge-II, Bisnupur,-II and part of Budge Budge-I (Mayapur GP only) Blocks in the district of South 24 Parganas | SM/08869 | Augmentation | Hiring of diesel driven Non-Air conditioner Motor Cab having BS-III & above category (Luxury Ambassador / Indica / Swift Dezire Car) with driver for official use of the Assistant Engineer, Sub-Division-II under South 24-Pgns. W/S Division-I, PHE Dte. [w.e.f. 01/06/2022 to 31/05/2023] | AE SWSD-II |  | ORD/000612/2022-2023 | 519/SWD-I | 30/05/2022 | 30/05/2023 | AHMED REZA | 1.73 | 0.4 | 23.06 | 100
18 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Augmentation of surface water based water supply Scheme for the arsenic affected areas of Budge Budge-II, Bisnupur,-II and part of Budge Budge-I (Mayapur GP only) Blocks in the district of South 24 Parganas | SM/08869 | Augmentation | Continuation Order for the work of Engagement of Office attendant 01(one) no. for different JJM works at Boosting Station-I (Begampur) under Baruipur Sub-Division of South 24-Pgns. W/S Division-I, P.H. Engineering Dte. Period from 16/02/2023 to 15/06/2023 (Four months). | AE BSD |  | ORD/000765/2022-2023 | 2938/SWD-I | 15/02/2023 | 15/06/2023 | PEECON | 0.83 | 0 | 0 | 0
19 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Augmentation of surface water based water supply Scheme for the arsenic affected areas of Budge Budge-II, Bisnupur,-II and part of Budge Budge-I (Mayapur GP only) Blocks in the district of South 24 Parganas | SM/08869 | Augmentation | Continuation Order for the work of Engagement of Office attendant 01(one) no. for different JJM works at Boosting Station-II (Krishnamohan) under Baruipur Sub-Division of South 24-Pgns. W/S Division-I, P.H. Engineering Dte. Period from 16/02/2023 to 15/06/2023 (Four months). | AE BSD |  | ORD/000766/2022-2023 | 2939/SWD-I | 15/02/2023 | 15/06/2023 | PEECON | 0.83 | 0 | 0 | 0
20 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Augmentation of surface water based water supply Scheme for the arsenic affected areas of Budge Budge-II, Bisnupur,-II and part of Budge Budge-I (Mayapur GP only) Blocks in the district of South 24 Parganas | SM/08869 | Augmentation | Engagement of 01 no. Computer Operator / Data Entry Operator [Category - A] for the office works of Executive Engineer (Deputed from PWD) under Superintending Engineer, South 24-Parganas W/S Circle, PHE Dte. [w.e.f. 01.04.2023 to 31.03.2024] | AE HQ-II | JE-2 | ORD/000815/2022-2023 | 3720/SWD-I | 31/03/2023 | 30/03/2024 | M/S. SYSCON | 2.52 | 1.92 | 76.24 | 90
21 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Augmentation of surface water based water supply Scheme for the arsenic affected areas of Budge Budge-II, Bisnupur,-II and part of Budge Budge-I (Mayapur GP only) Blocks in the district of South 24 Parganas | SM/08869 | Augmentation | Engagement of 01 no. Computer Operator / Data Entry Operator [Category - C] for the office works of Superintending Engineer, PMU, WBDWSIP (ADB), PHE Dte. under Executive Engineer, South 24-Pgns. W/S Division-I, PHE Dte. [w.e.f. 01.04.2023 to 31.03.2024] | AE HQ-II | JE-2 | ORD/000816/2022-2023 | 3721/SWD-I | 31/03/2023 | 30/03/2024 | M/S. SYSCON | 2.05 | 1.56 | 76.33 | 95
22 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Augmentation of surface water based water supply Scheme for the arsenic affected areas of Budge Budge-II, Bisnupur,-II and part of Budge Budge-I (Mayapur GP only) Blocks in the district of South 24 Parganas | SM/08869 | Augmentation | Hiring of additional 01 (one) no. diesel driven Non-Air conditioner Motor Cab having BS-III & above category (Luxury Ambassador / Indica / Swift Dezire Car) with driver for official use of the Assistant Engineers under South 24-Pgns. W/S Division-I, PHE Dte. [w.e.f. 01/04/2023 to 30/09/2023] | AE HQ-II |  | ORD/000875/2022-2023 | 3728/SWD-I | 31/03/2023 | 30/09/2023 | SUBRAT KUMAR SETHY | 0.87 | 0.72 | 83.2 | 50
23 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Augmentation of surface water based water supply Scheme for the arsenic affected areas of Budge Budge-II, Bisnupur,-II and part of Budge Budge-I (Mayapur GP only) Blocks in the district of South 24 Parganas | SM/08869 | Augmentation | Acceptance-cum-Work Order for the work of Hiring of diesel driven Non-Air conditioner Maxi Cab having BS-III & above category (Luxury Ambassador / Scorpio / Bolero / Swift Dezire / Indica Car) with driver for official use of the Executive Engineer, South 24-Pgns. W/S Division-I, PHE Dte. [w.e.f. 01/06/2022 to 31/05/2023] | AE SWSD-I |  | ORD/000894/2022-2023 | 515/SWD-I | 30/05/2022 | 30/05/2023 | AVIK HALDER | 1.77 | 0.4 | 22.58 | 100
24 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Augmentation of surface water based water supply Scheme for the arsenic affected areas of Budge Budge-II, Bisnupur,-II and part of Budge Budge-I (Mayapur GP only) Blocks in the district of South 24 Parganas | SM/08869 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000006/2022-2023 | 1522/SWD-I | 29/09/2022 |  | Resource Division | 258.14 | 0 | 0 | 0
25 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Augmentation of surface water based water supply Scheme for the arsenic affected areas of Budge Budge-II, Bisnupur,-II and part of Budge Budge-I (Mayapur GP only) Blocks in the district of South 24 Parganas | SM/08869 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000307/2023-2024 | 2727/SWD-I | 06/11/2023 |  | Resource Division | 129.85 | 0 | 0 | 0
Total | [13 empty] | 47782.8 | 22444.21 | 46.97