## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Retrofitting of pipeline for supporting FHTC drive for Betuabati W/S Scheme and adjoining areas under Budge Budge I Block with allied works under SWD - I, P.H.E. Dte District South 24 Parganas. | SM/09948 | Retrofitting | Retrofitting of pipeline for supporting FHTC drive for Betuabati W/S Scheme and adjoining areas under Budge Budge I Block with allied works under SWD - I, P.H.E. Dte District South 24 Parganas. | AE SWSD-I | JE-1 | ORD/000102/2021-2022 | 1103/SWD-I | 25/10/2021 | 22/02/2022 | PREMANANDA ROY BISWAS | 57.11 | 30.27 | 53 | 100
2 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Retrofitting of pipeline for supporting FHTC drive for Betuabati W/S Scheme and adjoining areas under Budge Budge I Block with allied works under SWD - I, P.H.E. Dte District South 24 Parganas. | SM/09948 | Retrofitting | Repair of Concrete Road in Budge Budge I Block for laying of Pipeline within Betuabati W/S Scheme under South 24 Pargana W/S Divn. - I, P.H.E Dte. (TSM/8299) Part -D | AE SWSD-I |  | ORD/000462/2022-2023 | 2779/SWD-I | 31/01/2023 | 17/03/2023 | M/S. SREEJIT ENTERPRISE (EMAIL ID- RAYTARUN1974@GMAIL.COM) | 7.62 | 7.59 | 99.53 | 0
3 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Retrofitting of pipeline for supporting FHTC drive for Betuabati W/S Scheme and adjoining areas under Budge Budge I Block with allied works under SWD - I, P.H.E. Dte District South 24 Parganas. | SM/09948 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000123/2022-2023 | 3472/SWD-I | 15/03/2023 |  | Resource Division | 2.21 | 0 | 0 | 0
4 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Retrofitting of pipeline for supporting FHTC drive for Betuabati W/S Scheme and adjoining areas under Budge Budge I Block with allied works under SWD - I, P.H.E. Dte District South 24 Parganas. | SM/09948 | Retrofitting | Retrofitting of pipeline for supporting FHTC drive for Betuabati W/S Scheme and adjoining areas under Budge Budge I Block with allied works under SWD - I, P.H.E. Dte District South 24 Parganas. |  |  | VCH/001194/2021-2022 | BP-2021-22-219 | 30/03/2022 |  | PREMANANDA ROY BISWAS | 15.5 | 0 | 0 | 0
Total | [13 empty] | 82.44 | 37.86 | 45.92