## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 218 NOS IN BUDGE BUDGE-II BLOCK 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10115 | School | Water Supply arrangement for AWCs as per different models of work under BUDGE BUDGE-II block under South 24-Parganas W/S Division-I, PHE Dte. (13 Nos. Model-3) (Group-46) | AE SWSD-I |  | ORD/000133/2021-2022 | 2219/SWD-I | 15/02/2022 | 01/04/2022 | TIYASHA ENTERPRISE | 23.53 | 23.53 | 100 | 0
2 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 218 NOS IN BUDGE BUDGE-II BLOCK 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10115 | School | Water Supply arrangement for AWCs as per different models of work under BUDGE BUDGE-II block under South 24-Parganas W/S Division-I, PHE Dte. (1 No. Model-1 and 10 Nos. Model-2) (Group-45) | AE SWSD-I |  | ORD/000143/2021-2022 | 2224/SWD-I | 15/02/2022 | 01/04/2022 | MOUMITA ENTERPRISE | 19.35 | 19.35 | 100 | 0
3 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 218 NOS IN BUDGE BUDGE-II BLOCK 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10115 | School | Water Supply arrangement for AWCs as per different models of work under BUDGE BUDGE-II block under South 24-Parganas W/S Division-I, PHE Dte. (2 Nos. Model-4 and 6 Nos. Model-5) (Group-47) | AE SWSD-I |  | ORD/000144/2021-2022 | 2233/SWD-I | 15/02/2022 | 01/04/2022 | SOMBHUNATH BHATTACHARJEE | 15.31 | 9.58 | 62.56 | 0
4 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 218 NOS IN BUDGE BUDGE-II BLOCK 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10115 | School | Water Supply arrangement for GOVT. SCHOOLS as per different models of work under BUDGE BUDGE-II block under South 24-Parganas W/S Division-I, PHE Dte. (31 Nos. Model-6) (Group-39) | AE SWSD-I |  | ORD/000158/2021-2022 | 2176/SWD-I | 15/02/2022 | 16/04/2022 | KARUNAMOYEE ENTERPRISE | 82.05 | 81.06 | 98.78 | 0
5 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 218 NOS IN BUDGE BUDGE-II BLOCK 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10115 | School | Water Supply arrangement for HEALTH CENTRES as per different models of work under BUDGE BUDGE-II block under South 24-Parganas W/S Division-I, PHE Dte. (5 Nos. Model-6) (Group-55) | AE SWSD-I |  | ORD/000173/2021-2022 | 2244/SWD-I | 15/02/2022 | 01/04/2022 | SNEHA CONSTRUCTION | 13.24 | 13.18 | 99.61 | 0
6 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 218 NOS IN BUDGE BUDGE-II BLOCK 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10115 | School | Water Supply arrangement for AWCs as per different models of work under BUDGE BUDGE-II block under South 24-Parganas W/S Division-I, PHE Dte. (18 Nos. Model-6) (Group-49) | AE SWSD-I |  | ORD/000174/2021-2022 | 2198/SWD-I | 15/02/2022 | 16/04/2022 | SUKUMAR DEBNATH | 47.65 | 47.29 | 99.25 | 0
7 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 218 NOS IN BUDGE BUDGE-II BLOCK 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10115 | School | Water Supply arrangement for AWCs as per different models of work under BUDGE BUDGE-II block under South 24-Parganas W/S Division-I, PHE Dte. (7 Nos. Model-5) (Group-48) | AE SWSD-I |  | ORD/000180/2021-2022 | 2240/SWD-I | 15/02/2022 | 01/04/2022 | S.M ENTERPRISE | 13.45 | 13.3 | 98.91 | 0
8 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 218 NOS IN BUDGE BUDGE-II BLOCK 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10115 | School | Water Supply arrangement for GOVT. SCHOOLS as per different models of work under BUDGE BUDGE-II block under South 24-Parganas W/S Division-I, PHE Dte. (1 No. Model-8 and 3 Nos. Model-9) (Group-44) | AE SWSD-I |  | ORD/000186/2021-2022 | 2249/SWD-I | 15/02/2022 | 01/04/2022 | M/S. SREEJIT ENTERPRISE | 10.96 | 10.84 | 98.85 | 0
9 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 218 NOS IN BUDGE BUDGE-II BLOCK 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10115 | School | Water Supply arrangement for GOVT. SCHOOLS as per different models of work under BUDGE BUDGE-II block under South 24-Parganas W/S Division-I, PHE Dte. (7 Nos. Model-3) (Group-36) | AE SWSD-I |  | ORD/000192/2021-2022 | 2247/SWD-I | 15/02/2022 | 01/04/2022 | JOY GURU TRADING | 12.68 | 12.56 | 99.11 | 0
10 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 218 NOS IN BUDGE BUDGE-II BLOCK 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10115 | School | Water Supply arrangement for GOVT. SCHOOLS as per different models of work under BUDGE BUDGE-II block under South 24-Parganas W/S Division-I, PHE Dte. (29 Nos. Model-6) (Group-40) | AE SWSD-I |  | ORD/000195/2021-2022 | 2179/SWD-I | 15/02/2022 | 16/04/2022 | PROJECT AND MAINTENANCE | 76.73 | 76.24 | 99.36 | 0
11 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 218 NOS IN BUDGE BUDGE-II BLOCK 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10115 | School | Water Supply arrangement for AWCs as per different models of work under BUDGE BUDGE-II block under South 24-Parganas W/S Division-I, PHE Dte. (3 Nos. Model-8) (Group-52) | AE SWSD-I |  | ORD/000196/2021-2022 | 2260/SWD-I | 15/02/2022 | 01/04/2022 | SUKUMAR DEBNATH | 8.16 | 8.09 | 99.13 | 0
12 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 218 NOS IN BUDGE BUDGE-II BLOCK 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10115 | School | Water Supply arrangement for GOVT. SCHOOLS as per different models of work under BUDGE BUDGE-II block under South 24-Parganas W/S Division-I, PHE Dte. (7 Nos. Model-7) (Group-41) | AE SWSD-I |  | ORD/000197/2021-2022 | 2226/SWD-I | 15/02/2022 | 01/04/2022 | RAMASISH ENTERPRISE | 18.74 | 18.65 | 99.52 | 0
13 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 218 NOS IN BUDGE BUDGE-II BLOCK 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10115 | School | Water Supply arrangement for HEALTH CENTRES as per different models of work under BUDGE BUDGE-II block under South 24-Parganas W/S Division-I, PHE Dte. (7 Nos. Model-2) (Group-54) | AE SWSD-I |  | ORD/000198/2021-2022 | 2248/SWD-I | 15/02/2022 | 01/04/2022 | JOY GURU TRADING | 12.48 | 12.47 | 99.93 | 0
14 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 218 NOS IN BUDGE BUDGE-II BLOCK 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10115 | School | Water Supply arrangement for GOVT. SCHOOLS as per different models of work under BUDGE BUDGE-II block under South 24-Parganas W/S Division-I, PHE Dte. (3 Nos. Model-2) (Group-35) | AE SWSD-I |  | ORD/000200/2021-2022 | 2278/SWD-I | 15/02/2022 | 01/04/2022 | S.M ENTERPRISE | 5.35 | 5.34 | 99.84 | 0
15 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 218 NOS IN BUDGE BUDGE-II BLOCK 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10115 | School | Water Supply arrangement for GOVT. SCHOOLS as per different models of work under BUDGE BUDGE-II block under South 24-Parganas W/S Division-I, PHE Dte. (6 Nos. Model-4 and 2 Nos. Model-5) (Group-37) | AE SWSD-I |  | ORD/000209/2021-2022 | 2235/SWD-I | 15/02/2022 | 01/04/2022 | SANJAY MIDDEY | 15.19 | 15.04 | 99 | 0
16 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 218 NOS IN BUDGE BUDGE-II BLOCK 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10115 | School | Water Supply arrangement for GOVT. SCHOOLS as per different models of work under BUDGE BUDGE-II block under South 24-Parganas W/S Division-I, PHE Dte. (6 Nos. Model-7) (Group-42) | AE SWSD-I |  | ORD/000241/2021-2022 | 2230/SWD-I | 15/02/2022 | 01/04/2022 | MS A M ENTERPRISE PROP GULSAN SARWAR | 16.02 | 15.87 | 99.04 | 0
17 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 218 NOS IN BUDGE BUDGE-II BLOCK 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10115 | School | Water Supply arrangement for GOVT. SCHOOLS as per different models of work under BUDGE BUDGE-II block under South 24-Parganas W/S Division-I, PHE Dte. (10 Nos. Model-6) (Group-38) | AE SWSD-I |  | ORD/000251/2021-2022 | 2214/SWD-I | 15/02/2022 | 16/04/2022 | AYUSH ENTERPRISE | 26.46 | 25.8 | 97.52 | 0
18 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 218 NOS IN BUDGE BUDGE-II BLOCK 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10115 | School | Water Supply arrangement for GOVT. SCHOOLS as per different models of work under BUDGE BUDGE-II block under South 24-Parganas W/S Division-I, PHE Dte. (2 Nos. Model-8) (Group-43) | AE SWSD-I |  | ORD/000259/2021-2022 | 2275/SWD-I | 15/02/2022 | 01/04/2022 | GOUTAM MAZUMDER | 5.44 | 5.36 | 98.51 | 0
19 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 218 NOS IN BUDGE BUDGE-II BLOCK 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10115 | School | Water Supply arrangement for AWCs as per different models of work under BUDGE BUDGE-II block under South 24-Parganas W/S Division-I, PHE Dte. (13 Nos. Model-7) (Group-51) | AE SWSD-I |  | ORD/000264/2021-2022 | 2208/SWD-I | 15/02/2022 | 16/04/2022 | M/S. S.D. CONSTRUCTION | 34.66 | 34.33 | 99.04 | 0
20 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 218 NOS IN BUDGE BUDGE-II BLOCK 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10115 | School | Water Supply arrangement for AWCs as per different models of work under BUDGE BUDGE-II block under South 24-Parganas W/S Division-I, PHE Dte. (16 Nos. Model-6) (Group-50) | AE SWSD-I |  | ORD/000338/2021-2022 | 2202/SWD-I | 15/02/2022 | 16/04/2022 | NILKAMAL BASAK | 42.33 | 7.6 | 17.95 | 0
21 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 218 NOS IN BUDGE BUDGE-II BLOCK 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10115 | School | Water Supply arrangement for AWCs as per different models of work under BUDGE BUDGE-II block under South 24-Parganas W/S Division-I, PHE Dte. (6 Nos. Model-9) (Group-53) | AE SWSD-I |  | ORD/000381/2021-2022 | 2229/SWD-I | 15/02/2022 | 01/04/2022 | ELECTRONIC SURVILLANCE | 16.5 | 16.3 | 98.8 | 0
22 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 218 NOS IN BUDGE BUDGE-II BLOCK 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10115 | School | Material Requisition To Resource Division |  |  | RTOR000009/2021-2022 | 2102/SWD-I | 11/02/2022 |  | Resource Division | 135.93 | 0 | 0 | 0
Total | [13 empty] | 652.21 | 471.77 | 72.33