## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 181 NOS IN SONARPUR AND MOGRAHAT-II BLOCKS 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10117 | School | Water Supply arrangement for GOVT. SCHOOLS as per different models of work under SONARPUR block under South 24-Parganas W/S Division-I, PHE Dte. (4 Nos. Model-5) (Group-70) | AE BSD,AE HQ-I |  | ORD/000129/2021-2022 | 2267/SWD-I | 15/02/2022 | 01/04/2022 | NIKHIL SAMADDAR | 7.68 | 7.37 | 95.97 | 0
2 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 181 NOS IN SONARPUR AND MOGRAHAT-II BLOCKS 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10117 | School | Water Supply arrangement for GOVT. SCHOOLS as per different models of work under SONARPUR block under South 24-Parganas W/S Division-I, PHE Dte. (2 Nos. Model-1 and 3 Nos. Model-2) (Group-66) | AE BSD,AE HQ-I |  | ORD/000145/2021-2022 | 2259/SWD-I | 15/02/2022 | 01/04/2022 | MS JHARNA ENTERPRISE | 8.38 | 7.43 | 88.63 | 0
3 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 181 NOS IN SONARPUR AND MOGRAHAT-II BLOCKS 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10117 | School | Water Supply arrangement for GOVT. SCHOOLS as per different models of work under SONARPUR block under South 24-Parganas W/S Division-I, PHE Dte. (10 Nos. Model-2) (Group-67) | AE BSD,AE HQ-I |  | ORD/000240/2021-2022 | 2228/SWD-I | 15/02/2022 | 01/04/2022 | KAMALA ENTERPRISE | 17.82 | 17.74 | 99.57 | 0
4 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 181 NOS IN SONARPUR AND MOGRAHAT-II BLOCKS 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10117 | School | Water Supply arrangement for AWCs as per different models of work under MOGRAHAT-II block under South 24-Parganas W/S Division-I, PHE Dte. (9 Nos. Model-6) (Group-82) | AE BSD,AE HQ-I |  | ORD/000261/2021-2022 | 2218/SWD-I | 15/02/2022 | 01/04/2022 | RAJLAXMI CONSTRUCTION | 23.82 | 21.05 | 88.37 | 0
5 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 181 NOS IN SONARPUR AND MOGRAHAT-II BLOCKS 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10117 | School | Water Supply arrangement for GOVT. SCHOOLS as per different models of work under MOGRAHAT-II block under South 24-Parganas W/S Division-I, PHE Dte. (5 Nos. Model-6) (Group-81) | AE BSD,AE HQ-I |  | ORD/000263/2021-2022 | 2245/SWD-I | 15/02/2022 | 01/04/2022 | MS KRISHNA MONDAL | 13.23 | 11.37 | 85.98 | 0
6 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 181 NOS IN SONARPUR AND MOGRAHAT-II BLOCKS 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10117 | School | Water Supply arrangement for GOVT. SCHOOLS as per different models of work under SONARPUR block under South 24-Parganas W/S Division-I, PHE Dte. (3 Nos. Model-7) (Group-74) | AE BSD,AE HQ-I |  | ORD/000275/2021-2022 | 2263/SWD-I | 15/02/2022 | 01/04/2022 | KAMALA ENTERPRISE (BARISHA ) | 7.94 | 7.93 | 99.83 | 0
7 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 181 NOS IN SONARPUR AND MOGRAHAT-II BLOCKS 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10117 | School | Water Supply arrangement for GOVT. SCHOOLS as per different models of work under SONARPUR block under South 24-Parganas W/S Division-I, PHE Dte. (3 Nos. Model-8) (Group-75) | AE BSD,AE HQ-I |  | ORD/000277/2021-2022 | 2262/SWD-I | 15/02/2022 | 01/04/2022 | ADRIJA ENTERPRISE | 8.07 | 7.79 | 96.59 | 0
8 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 181 NOS IN SONARPUR AND MOGRAHAT-II BLOCKS 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10117 | School | Water Supply arrangement for GOVT. SCHOOLS as per different models of work under SONARPUR block under South 24-Parganas W/S Division-I, PHE Dte. (32 Nos. Model-6) (Group-72) | AE BSD,AE HQ-I |  | ORD/000288/2021-2022 | 2173/SWD-I | 15/02/2022 | 16/04/2022 | MUNNA AGROTECH ENTERPRISE | 84.65 | 44.72 | 52.83 | 100
9 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 181 NOS IN SONARPUR AND MOGRAHAT-II BLOCKS 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10117 | School | Water Supply arrangement for AWCs as per different models of work under SONARPUR block under South 24-Parganas W/S Division-I, PHE Dte. (19 Nos. Model-6) (Group-78) | AE BSD,AE HQ-I |  | ORD/000375/2021-2022 | 2195/SWDI | 15/02/2022 | 16/04/2022 | KAMALA ENTERPRISE (DIAMOND HARBOUR) | 49.32 | 49.18 | 99.71 | 0
10 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 181 NOS IN SONARPUR AND MOGRAHAT-II BLOCKS 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10117 | School | Water Supply arrangement for GOVT. SCHOOLS as per different models of work under SONARPUR block under South 24-Parganas W/S Division-I, PHE Dte. (34 Nos. Model-6) (Group-71) | AE BSD,AE HQ-I |  | ORD/000377/2021-2022 | 2170/SWD-I | 15/02/2022 | 16/04/2022 | MALLICK ENTERPRISE | 88.73 | 86.17 | 97.12 | 0
11 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 181 NOS IN SONARPUR AND MOGRAHAT-II BLOCKS 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10117 | School | Water Supply arrangement for GOVT. SCHOOLS as per different models of work under SONARPUR block under South 24-Parganas W/S Division-I, PHE Dte. (8 Nos. Model-9) (Group-76) | AE BSD,AE HQ-I |  | ORD/000394/2021-2022 | 2220/SWDI | 15/02/2022 | 01/04/2022 | STAR ENTERPRISE | 21.94 | 21.54 | 98.18 | 0
12 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 181 NOS IN SONARPUR AND MOGRAHAT-II BLOCKS 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10117 | School | Water Supply arrangement for AWCs as per different models of work under SONARPUR block under South 24-Parganas W/S Division-I, PHE Dte. (12 Nos. Model-2) (Group-77) | AE HQ-I |  | ORD/000413/2021-2022 | 2222/SWD-I | 15/02/2022 | 01/04/2022 | MOUMITA ENTERPRISE | 21.39 | 8.44 | 39.47 | 0
13 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 181 NOS IN SONARPUR AND MOGRAHAT-II BLOCKS 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10117 | School | Water Supply arrangement for HEALTH CENTRES as per different models of work under SONARPUR block under South 24-Parganas W/S Division-I, PHE Dte. (3 Nos. Model-2) (Group-79) | AE HQ-I |  | ORD/000466/2021-2022 | 2279/SWD-I | 15/02/2022 | 01/04/2022 | AHANA ENTERPRISE | 5.35 | 4.58 | 85.63 | 100
14 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 181 NOS IN SONARPUR AND MOGRAHAT-II BLOCKS 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10117 | School | Water Supply arrangement for HEALTH CENTRES as per different models of work under SONARPUR block under South 24-Parganas W/S Division-I, PHE Dte. (12 Nos. Model-6) (Group-80) |  |  | ORD/000578/2021-2022 | 2212/SWD-I | 15/02/2022 | 16/04/2022 | A.G. ENTERPRISE | 31.77 | 15.74 | 49.56 | 100
15 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 181 NOS IN SONARPUR AND MOGRAHAT-II BLOCKS 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10117 | School | Water Supply arrangement for GOVT. SCHOOLS as per different models of work under SONARPUR block under South 24-Parganas W/S Division-I, PHE Dte. (14 Nos. Model-6) (Group-73) | AE HQ-II | JE-3 | ORD/000589/2021-2022 | 2207\SWD-I | 15/02/2022 | 16/04/2022 | M/S. SAMADDAR CONSTRUCTION | 37.05 | 7.93 | 21.42 | 100
16 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | RUNNING WATER SUPPLY ARRAGEMENT FOR GOVT INSTITUTIONS (SCHOOL/ AWC/ HEALTH CENTRE) 181 NOS IN SONARPUR AND MOGRAHAT-II BLOCKS 0F SOUTH 24-PARGANAS DISTRICT UNDER SOUTH 24-PARGANAS WATER SUPPLY DIVISION-I, PHE DTE. | SM/10117 | School | Material Requisition To Resource Division |  |  | RTOR000004/2021-2022 | 2105/SWD-I | 11/02/2022 |  | Resource Division | 225.96 | 0 | 0 | 0
Total | [13 empty] | 653.09 | 319 | 48.84