## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARAGANAS | Magrahat - I | South 24 Pgs W/S Division I | Providing 100% FHTC in Zone-IX at Ghola Noapara Usthi mouza of Mograhat-I block within 'Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur District.- South-24 Pgns.' under South-24 Pgns W/S Divn-I, P.H.E Dte. | SM/11259 | New | Laying distribution system of pipe water supply scheme in ZONE-IX at GHOLA NOAPARA Mouza of Mograhat-I Block for Augmentation of Mega surface water based water supply scheme and providing Functional Household Tap Connection (FHTC) in ZONE-IX at GHOLA NOAPARA of MOGRAHAT-I block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. under South 24 Parganas water supply Sub-Division-II of South 24 Parganas Division-I, PHE Dte. (Number of FHTC ¿ 5309 Nos.) | AE SWSD-II | JE4 | ORD/000803/2022-2023 | 3694/SWD-I | 30/03/2023 | 28/07/2023 | MANASH GHOSH | 603.4 | 80.16 | 13.29 | 30
2 | SOUTH 24 PARAGANAS | Magrahat - I | South 24 Pgs W/S Division I | Providing 100% FHTC in Zone-IX at Ghola Noapara Usthi mouza of Mograhat-I block within 'Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur District.- South-24 Pgns.' under South-24 Pgns W/S Divn-I, P.H.E Dte. | SM/11259 | New | Material Requisition To Resource Division |  |  | RTOR000141/2023-2024 | 322/SWD-I | 25/04/2023 |  | Resource Division | 32.7 | 0 | 0 | 0
Total | [13 empty] | 636.11 | 80.16 | 12.6