## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARAGANAS | Bishnupur - I | S24 Pgns Mechanical | Proposed ground water based DEULI piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/11498 | New | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/03670/2023-2024 | BP-2023-24-392 | 23/11/2023 |  | WBSEDCL | 16.78 | 0 | 0 | 0
2 | SOUTH 24 PARAGANAS | Bishnupur - I | S24 Pgns Mechanical | Proposed ground water based DEULI piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/11498 | New | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Deuli water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Bishnupur-I] | Assistant Engineer -II | Junior Engineer | ORD/000467/2022-2023 | 278/SMD | 01/02/2023 | 02/05/2023 | AHALYA ENGINEERING WORKS | 26.76 | 6.52 | 24.38 | 50
3 | SOUTH 24 PARAGANAS | Bishnupur - I | South 24 Pgs W/S Division I | Proposed ground water based DEULI piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/11498 | New | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. Deep Tubewell by Rotary method for DEULIPIPE WATER SUPPLY SCHEME in the Arsenic affected areas of South 24 Pgs. Dist. in BISHNUPUR-I Block under South 24 Pgs W/S Sub-Division-II, P.H.E. Dte. | AE SWSD-II | JE2 | ORD/000032/2022-2023 | 916/SWD-I | 19/07/2022 | 18/08/2022 | SIMPLEX DRILLING CO. | 14.19 | 12.86 | 90.61 | 100
4 | SOUTH 24 PARAGANAS | Bishnupur - I | South 24 Pgs W/S Division I | Proposed ground water based DEULI piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/11498 | New | Construction of (Size 4.80mX3.66m) Pump House with water supply and sanitary arrangement (as per Deptt. drawing) of DEULI Pipe Water Supply Scheme in Bishnupur-I block under South 24-Pgns W/S Divn-I, PHE Dte. (SM/11498) (2nd Call) | AE SWSD-II | JE2 | ORD/000094/2023-2024 | 451/SWD-I | 04/05/2023 | 03/07/2023 | M/S ASHA ENGINEERING | 6.05 | 5.79 | 95.74 | 100
5 | SOUTH 24 PARAGANAS | Bishnupur - I | South 24 Pgs W/S Division I | Proposed ground water based DEULI piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/11498 | New | Construction of Boundary Wall & other allied works at 12 (twelve) nos. Head Work Sites of different PWSS within Bishnupur-I Block, Dist.-South 24-Parganas for Augmentation of Surface Water based Water Supply Scheme in the Arsenic Affected areas of South 24-Parganas District. | AE SWSD-II | JE1,JE2,JE4 | ORD/000209/2023-2024 | 1377/SWD-I | 12/07/2023 | 09/12/2023 | CONCORD PROJECTS PVT. LTD. | 105.47 | 0 | 0 | 15
6 | SOUTH 24 PARAGANAS | Bishnupur - I | South 24 Pgs W/S Division I | Proposed ground water based DEULI piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/11498 | New | Laying of Additional Pipeline for distribution system, rising main, construction of boundary walls, pump house and other allied works for Deuli PWSS to accommodate FHTC in Bishnupur - I Block under South 24 parganas W/S Divn-I, PHE Dte. South 24 Pgns District. (SM/11498) |  |  | ORD/000265/2024-2025 | 2680/SWD-I | 07/06/2024 | 22/07/2024 | SWATHI ENTERPRISE | 76 | 0 | 0 | 0
7 | SOUTH 24 PARAGANAS | Bishnupur - I | South 24 Pgs W/S Division I | Proposed ground water based DEULI piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/11498 | New | Preparation and submission of Detailed Project Report of "DEULI Ground Water Based Piped Water Supply Scheme" in BISHNUPUR-I block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE SWSD-II |  | ORD/000404/2022-2023 | 459/SWD-I | 24/05/2022 | 08/06/2022 | GEO SOLUTION | 2.55 | 2.55 | 99.99 | 100
8 | SOUTH 24 PARAGANAS | Bishnupur - I | South 24 Pgs W/S Division I | Proposed ground water based DEULI piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/11498 | New | Pipeline Protection for DEULI PWSS to accommodate FHTC in Bishnupur-I Block under South 24 Pgs W/S Sub-Division -I, P.H.E. Dte. (SM/11498) |  |  | ORD/000419/2024-2025 | 3748/SWD-I | 28/08/2024 | 12/10/2024 | NIRMAL UDYOG | 10.02 | 0 | 0 | 0
9 | SOUTH 24 PARAGANAS | Bishnupur - I | South 24 Pgs W/S Division I | Proposed ground water based DEULI piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/11498 | New | Laying Distribution System with providing Functional Household Tap Connection (FHTC) for Proposed DEULI PIPE WATER SUPPLY SCHEME in the Arsenic affected areas of South 24-Pgs. Dist. in BISHNUPUR-I Block under South 24 Pgs W/S Sub-Division -II, P.H.E. Dte. [No. of FHTC = 822] | AE SWSD-II | JE2 | ORD/000427/2022-2023 | 2565/SWD-I | 10/01/2023 | 11/03/2023 | TANMOY ROY CHOWDHURY | 123.95 | 80.71 | 65.12 | 80
10 | SOUTH 24 PARAGANAS | Bishnupur - I | South 24 Pgs W/S Division I | Proposed ground water based DEULI piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/11498 | New | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method at Second Tubewell site for DEULI PWSS of BISHNUPUR-I block for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/011201] | AE SWSD-II | JE2 | ORD/000596/2022-2023 | 3116/SWD-I | 24/02/2023 | 26/03/2023 | CIVIL CONSULTANT | 15.88 | 0 | 0 | 0
11 | SOUTH 24 PARAGANAS | Bishnupur - I | South 24 Pgs W/S Division I | Proposed ground water based DEULI piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/11498 | New | Development of low land and temporary aproach road for entering Tubewell site for proposed DEULI Piped Water Supply Scheme in Bishnupur-I Block for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic Affected Areas of South 24 Pgs. Dist. under South 24 Pgs. Water Supply Division-I, PHE Dte. [TSM/011201] | AE SWSD-II | JE2 | ORD/000810/2022-2023 | 3702/SWD-I | 30/03/2023 | 14/04/2023 | SIMPLEX DRILLING COMPANY | 0.9 | 0.86 | 95.9 | 100
12 | SOUTH 24 PARAGANAS | Bishnupur - I | South 24 Pgs W/S Division I | Proposed ground water based DEULI piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/11498 | New | Material Requisition To Resource Division |  |  | RTOR000103/2022-2023 | 3249/SWD-I | 01/03/2023 |  | Resource Division | 32.53 | 0 | 0 | 0
Total | [13 empty] | 431.08 | 109.3 | 25.35