## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARAGANAS | Jaynagar - I | S24 Pgns Mechanical | Ground water based DEWANGANJ piped water supply scheme to accommodate FHTC in JAYNAGAR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/11499 | New | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/00624/2023-2024 | BP-2023-24-92 | 14/06/2023 |  | WBSEDCL | 6.73 | 0 | 0 | 0
2 | SOUTH 24 PARAGANAS | Jaynagar - I | S24 Pgns Mechanical | Ground water based DEWANGANJ piped water supply scheme to accommodate FHTC in JAYNAGAR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/11499 | New | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 and 2, of Dewanganj water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Jaynagar-I] | Assistant Engineer | Junior Engineer | ORD/000732/2023-2024 | 2915/SMD | 31/08/2023 | 29/11/2023 | JAGANNATH ENTERPRISE | 18.87 | 4.37 | 23.15 | 45
3 | SOUTH 24 PARAGANAS | Jaynagar - I | S24 Pgns Mechanical | Ground water based DEWANGANJ piped water supply scheme to accommodate FHTC in JAYNAGAR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/11499 | New | Improvement of outdoor Illumination arrangement with allied works at Pump House no-1 of Dewanganj W/S Scheme under SMD, P.H.E. Dte. (Block-Jaynagar-I) | Assistant Engineer | Junior Engineer | ORD/002783/2023-2024 | 112/SMSD | 25/01/2024 | 09/02/2024 | JAGANNATH ENTERPRISE | 0.5 | 0 | 0 | 0
4 | SOUTH 24 PARAGANAS | Jaynagar - I | South 24 Pgs W/S Division I | Ground water based DEWANGANJ piped water supply scheme to accommodate FHTC in JAYNAGAR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/11499 | New | Sinking of Rig bored 02 (Two) nos. 250mm X 150mm dia & 300 mtr. deep Tubewell by Rotary method for DEWANGANJ PWSS of Joynagar-I Block Under South 24 Parganas W/S Division-I, PHE Dte. | AE BSD | JE-1 | ORD/000076/2022-2023 | 1187/SWD-I | 02/09/2022 | 02/10/2022 | TAPAS KUMAR GIRI | 28.52 | 6 | 21.05 | 50
5 | SOUTH 24 PARAGANAS | Jaynagar - I | South 24 Pgs W/S Division I | Ground water based DEWANGANJ piped water supply scheme to accommodate FHTC in JAYNAGAR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/11499 | New | Construction of 200 m3 capacity 20 M. staging height R.C.C. Over Head Water Reservoir as per departmental design, drawing & specification including R.C.C. Bored Pile & Pile Cap after soil investigation alongwith Providing 100% FHTC & Laying distribution system from Big dia deep Tube Well at DEWANGANJ Mouza of JOYNAGAR-I Block due to improvement of water supply in the water Scarcity area/non command area under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. (No. of FHTC = 1095) | AE BSD | JE-1 | ORD/000220/2022-2023 | 1629/SWD-I | 20/10/2022 | 16/08/2023 | SRIJON ENTERPRISE | 308.29 | 162.51 | 52.71 | 100
6 | SOUTH 24 PARAGANAS | Jaynagar - I | South 24 Pgs W/S Division I | Ground water based DEWANGANJ piped water supply scheme to accommodate FHTC in JAYNAGAR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/11499 | New | Preparation and submission of Detailed Project Report of DEWANGANJ Ground Water Based Piped Water Supply Scheme in JOYNAGAR-I Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD |  | ORD/000225/2021-2022 | 1965/SWD-I | 27/01/2022 | 26/02/2022 | GEO SOLUTION | 2.62 | 2.59 | 98.82 | 100
7 | SOUTH 24 PARAGANAS | Jaynagar - I | South 24 Pgs W/S Division I | Ground water based DEWANGANJ piped water supply scheme to accommodate FHTC in JAYNAGAR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/11499 | New | Construction of 02 (Two) nos. chlorination rooms at Dewanganj at Jaynagar-I Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas under South 24-Pgns Water Supply Divn-I, PHE Dte. | AE BSD | JE-1 | ORD/000375/2022-2023 | 2209/SWD-I | 13/12/2022 | 11/02/2023 | KHAN ENTERPRISE | 11.52 | 4.75 | 41.24 | 0
8 | SOUTH 24 PARAGANAS | Jaynagar - I | South 24 Pgs W/S Division I | Ground water based DEWANGANJ piped water supply scheme to accommodate FHTC in JAYNAGAR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/11499 | New | Construction of approach road in front of OHR site and construction of Boundary Walls at Tubewell site- 1 & 2 under Ground Water Based DEWANGANJ Pipe Water Supply Scheme to Accommodate FHTC in Jaynagar-I Block under South 24-Pgns. W/S Division-I, PHE Dte. (SM/11499) | AE BSD | JE-1 | ORD/000666/2023-2024 | 3026/SWD-I | 30/11/2023 | 29/01/2024 | SRIJON ENTERPRISE | 49.36 | 10.62 | 21.51 | 50
9 | SOUTH 24 PARAGANAS | Jaynagar - I | South 24 Pgs W/S Division I | Ground water based DEWANGANJ piped water supply scheme to accommodate FHTC in JAYNAGAR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/11499 | New | Additional work for sinking of 02 (two) nos. Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for Dewanganj PWSS of Joynagar-I Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division- I, P.H.E. Dte. [TSM/011007] | AE BSD | JE-1 | ORD/000733/2022-2023 | 3584/SWD-I | 22/03/2023 | 06/04/2023 | TAPAS KUMAR GIRI | 3.14 | 0.78 | 25 | 50
10 | SOUTH 24 PARAGANAS | Jaynagar - I | South 24 Pgs W/S Division I | Ground water based DEWANGANJ piped water supply scheme to accommodate FHTC in JAYNAGAR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/11499 | New | Balance miscellaneous work for Ground water based DEWANGANJ Piped Water Supply Scheme to accommodate FHTC in JAYNAGAR-I block under South 24-Pgns W/S Division-I, PHE Dte for AUGMENTATION of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgns District. (SM/11499) |  |  | ORD/000906/2023-2024 | 1205/SWD-I | 11/03/2024 | 25/04/2024 | M/S THE BASU ENTERPRISE | 16.06 | 0 | 0 | 0
11 | SOUTH 24 PARAGANAS | Jaynagar - I | South 24 Pgs W/S Division I | Ground water based DEWANGANJ piped water supply scheme to accommodate FHTC in JAYNAGAR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/11499 | New | Material Requisition To Resource Division |  |  | RTOR000079/2023-2024 | 294/SWD-I | 25/04/2023 |  | Resource Division | 46.39 | 0 | 0 | 0
Total | [13 empty] | 492.01 | 191.62 | 38.95