## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Ground water based GANGARAI piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. | SM/11732 | Augmentation | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/03347/2023-2024 | BP-2023-24-369 | 08/11/2023 |  | WBSEDCL | 4.3 | 0 | 0 | 0
2 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Ground water based GANGARAI piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. | SM/11732 | Augmentation | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/04003/2023-2024 | BP-2023-24-412 | 13/12/2023 |  | WBSEDCL | 5.56 | 0 | 0 | 0
3 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Ground water based GANGARAI piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. | SM/11732 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Gangarai water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Bishnupur-I] | Assistant Engineer -II | Junior Engineer | ORD/000485/2022-2023 | 238/SMD | 24/01/2023 | 24/04/2023 | M/S. PS & ASSOCIATES | 25.92 | 6.28 | 24.22 | 50
4 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Ground water based GANGARAI piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. | SM/11732 | Augmentation | Supply, Delivery and Fitting Fixing of the additional materials for PH No.-1 of Gangarai Water supply scheme under JJM under South 24 Pgs. Mechanical Division, PHE Dte. (Block : Bishnupur-I) [SM/11732] | Assistant Engineer -II | Junior Engineer | ORD/002237/2023-2024 | 8-AE-II-SMD | 03/01/2024 | 18/01/2024 | PS & ASSOCIATES | 0.58 | 0.29 | 50 | 100
5 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Ground water based GANGARAI piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. | SM/11732 | Augmentation | Upliftment of operational condition by providing necessary luminaires, LED Board, chair & table etc. at P.H. No. 1 under Gangarai Water Supply Scheme, under South 24 Pgs Mechanical Division, PHE Dte. (Block: Bishnupur-I) (SM/11732) | Assistant Engineer -II | Junior Engineer | ORD/002457/2023-2024 | 208-AE-II-SMD | 28/02/2024 | 14/03/2024 | SOMNATH ENTERPRISE | 0.75 | 0.38 | 50.66 | 100
6 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Ground water based GANGARAI piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. | SM/11732 | Augmentation | Construction of (Size 4.80mX3.66m) Pump House with water supply and sanitary arrangement (as per Deptt. drawing) of GANGRAI Pipe Water Supply Scheme in Bishnupur-I block under South 24-Pgns W/S Divn-I, PHE Dte. (SM/11493) (2nd Call) | AE SWSD-II | JE3 | ORD/000095/2023-2024 | 452/SWD-I | 04/05/2023 | 03/07/2023 | A.M. ENTERPRISE (BASIRHAT) | 6.04 | 2.91 | 48.14 | 100
7 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Ground water based GANGARAI piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. | SM/11732 | Augmentation | Sinking of Rig bored 250mm x 150mm dia & 300 mtr. deep Tubewell by Rotary method for GANGARAI Piped Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. Dist. in Bishnupur-I Block Under South 24 Paraganas W/S Division-I, PHE Dte. [SM/11732] | AE SWSD-II | JE3 | ORD/000174/2022-2023 | 1449/SWD-I | 26/09/2022 | 26/10/2022 | SUBHRA ENTERPRISE | 14.26 | 13.46 | 94.37 | 100
8 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Ground water based GANGARAI piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. | SM/11732 | Augmentation | Construction of Boundary Wall & other allied works at 11 (eleven) nos. Head Work Sites of different PWSS within Bishnupur-I Block, Dist.-South 24-Parganas for Augmentation of Surface Water based Water Supply Scheme in the Arsenic Affected areas of South 24-Parganas District. | AE SWSD-II | JE2,JE3,JE4 | ORD/000210/2023-2024 | 1376/SWD-I | 12/07/2023 | 09/12/2023 | CONCORD PROJECTS PVT. LTD. | 106.79 | 0 | 0 | 20
9 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Ground water based GANGARAI piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. | SM/11732 | Augmentation | Preparation and submission of Detailed Project Report of GANGRAL AND ADJOINING AREAS Ground Water Based Piped Water Supply Scheme in BISHNUPUR-I (ZONE-XIX) Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE SWSD-II |  | ORD/000233/2021-2022 | 1976/SWD-I | 27/01/2022 | 26/02/2022 | GEO SOLUTION | 2.76 | 2.55 | 92.54 | 100
10 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Ground water based GANGARAI piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. | SM/11732 | Augmentation | Construction of boundary wall, approach road, pump house, land development, road restoration, additional laying of pipeline, rising main and protection work of pipeline for GANGARAI PWSS to accommodate FHTC in Bishnupur-I Block under South 24-Pgns for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic Affected areas of South 24-Pgns, W/S Divn-I, PHE Dte. [SM/11732] | AE SWSD-II | JE3 | ORD/000268/2024-2025 | 2919/SWD-I | 25/06/2024 | 09/08/2024 | SUGANDHIT SUNDARBAN ENTERPRISE PVT. LTD. | 86.61 | 0 | 0 | 0
11 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Ground water based GANGARAI piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. | SM/11732 | Augmentation | Laying Distribution System with providing Functional Household Tap Connection (FHTC) for Ground Water Based GANGRAI PIPE WATER SUPPLY SCHEME for Augmentation of Surface Water Supply Scheme in the Arsenic affected areas of South 24-Pgs. Dist. in BISHNUPUR-I Block under South 24 Pgs W/S Division -I, P.H.E. Dte., South-24 Pgs. Dist. [No. of FHTC - 882 nos.] | AE SWSD-II | JE3 | ORD/000417/2022-2023 | 2471/SWD-I | 30/12/2022 | 30/03/2023 | MS BUILDWELL | 125.23 | 61.94 | 49.46 | 80
12 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Ground water based GANGARAI piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. | SM/11732 | Augmentation | Additional work for sinking of Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for GANGRAI PWSS of Bishnupur-I Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas district under South 24-Parganas W/S Division- I, P.H.E. Dte. [TSM/011791] | AE SWSD-II | JE3 | ORD/000526/2022-2023 | 2921/SWD-I | 14/02/2023 | 01/03/2023 | SUBHRA ENTERPRISE | 1.57 | 1.57 | 100 | 100
13 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Ground water based GANGARAI piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. | SM/11732 | Augmentation | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deepTubewell having 66 mtr. housing pipe by Rotary method at Second Tubewell site for GANGRAI PWSS of BISHNUPUR-I block for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/011791] | AE SWSD-II | JE3 | ORD/000557/2022-2023 | 3047/SWD-I | 20/02/2023 | 22/03/2023 | TAPAS KUMAR GIRI | 15.9 | 0 | 0 | 0
14 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Ground water based GANGARAI piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. | SM/11732 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000030/2022-2023 | 2555/SWD-I | 09/01/2023 |  | Resource Division | 5.43 | 0 | 0 | 0
15 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Ground water based GANGARAI piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. | SM/11732 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000113/2022-2023 | 3249/SWD-I | 01/03/2023 |  | Resource Division | 23.5 | 0 | 0 | 0
Total | [13 empty] | 425.19 | 89.37 | 21.02