## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | KAMARIA ZONE - IV piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24-Pgns W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 pgns district. | SM/11788 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Kamaria Zone-IV water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Jaynagar-I] | Assistant Engineer | Junior Engineer | ORD/000572/2022-2023 | 597/SMD | 27/02/2023 | 28/05/2023 | AHALYA ENGINEERING WORKS | 22.93 | 5.52 | 24.08 | 45
2 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | KAMARIA ZONE - IV piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24-Pgns W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 pgns district. | SM/11788 | Augmentation | Improvement of outdoor Illumination arrangement with allied works at Pump House no-1 of Kamaria (Zone-IV) W/S Scheme under SMD, P.H.E. Dte. (Block-Janagar-I) | Assistant Engineer | Junior Engineer | ORD/002406/2023-2024 | 1495/SMSD | 05/12/2023 | 20/12/2023 | AHALYA ENGINEERING WORKS | 0.48 | 0.24 | 50 | 100
3 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | KAMARIA ZONE - IV piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24-Pgns W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 pgns district. | SM/11788 | Augmentation | Sinking of Rig bored 02 (Two) nos. 300mm X 200mm dia & 300 mtr. deep Tubewell by Rotary method for KAMARIA (ZONE-IV) PWSS of Joynagar-I Block Under South 24 Parganas W/S Division-I, PHE Dte. | AE BSD | JE-1 | ORD/000084/2022-2023 | 1195/SWD-I | 02/09/2022 | 02/10/2022 | TAPAS KUMAR GIRI | 40.13 | 18.11 | 45.12 | 100
4 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | KAMARIA ZONE - IV piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24-Pgns W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 pgns district. | SM/11788 | Augmentation | Construction of 350 m3 capacity 20 M. staging height R.C.C. Over Head Water Reservoir as per departmental design, drawing & specification including R.C.C. Bored Pile & Pile Cap after soil investigation along with Providing 100% FHTC & Laying distribution system from Big dia deep Tube Well at KAMARIA (ZONE-IV) Mouza of JOYNAGAR-I Block due to improvement of water supply in the water Scarcity area/non command area under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. (No. of FHTC = 2051) | AE BSD | JE-1 | ORD/000278/2022-2023 | 1841/SWD-I | 11/11/2022 | 07/09/2023 | MANASH GHOSH | 411.42 | 154.37 | 37.52 | 50
5 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | KAMARIA ZONE - IV piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24-Pgns W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 pgns district. | SM/11788 | Augmentation | Preparation and submission of Detailed Project Report of KAMARIA (IV) Ground Water Based Piped Water Supply Scheme in JOYNAGAR-I Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD |  | ORD/000362/2021-2022 | 1964/SWD-I | 27/01/2022 | 26/02/2022 | MS R. DUTTA AND CO | 2.76 | 2.61 | 94.68 | 100
6 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | KAMARIA ZONE - IV piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24-Pgns W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 pgns district. | SM/11788 | Augmentation | Construction of 02 (Two) nos. chlorination rooms at Kamaria (Zone-IV) of Jaynagar-I Block uunder Surface Water Based Water Supply Scheme in the Arsenic affected areas under South 24-Pgns Water Supply Divn-I, PHE Dte. | AE BSD | JE-1 | ORD/000382/2022-2023 | 2215/SWD-I | 13/12/2022 | 11/02/2023 | ALISHA CONSTRUCTION | 11.52 | 2.39 | 20.72 | 50
7 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | KAMARIA ZONE - IV piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24-Pgns W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 pgns district. | SM/11788 | Augmentation | Additional work for sinking of 02 (two) nos. Rig bored 300 mm x 200 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for Kamaria Zone-IV PWSS of Joynagar-I Block for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division- I, P.H.E. Dte. [TSM/011004] | AE BSD | JE-1 | ORD/000743/2022-2023 | 3587/SWD-I | 23/03/2023 | 07/04/2023 | TAPAS KUMAR GIRI | 4.41 | 2.2 | 50 | 100
8 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | KAMARIA ZONE - IV piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24-Pgns W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 pgns district. | SM/11788 | Augmentation | Balance miscelleneous work for KAMARIA ZONE - IV piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24-Pgns W/S Division-I, PHE Dte for AUGMENTATION of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 pgns district. (SM/11788) |  |  | ORD/000912/2023-2024 | 1202/SWD-I | 11/03/2024 | 25/04/2024 | BANGA NIRMAN | 16.78 | 0 | 0 | 0
9 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | KAMARIA ZONE - IV piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24-Pgns W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 pgns district. | SM/11788 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000078/2023-2024 | 294/SWD-I | 25/04/2023 |  | Resource Division | 13.73 | 0 | 0 | 0
Total | [13 empty] | 524.16 | 185.44 | 35.38