## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARAGANAS | Magrahat - I | South 24 Pgs W/S Division I | Providing 100% FHTC in Zone-II at Rajballabhpur Mouza of Mograhat-I Block within 'Mega Surface Water based Water Supply Scheme For Falta-Mathurapur Dist- South 24 pgns. Under South 24 pgns. W/S Division-I P.H.E. Dte. | SM/11973 | New | Construction of 1000 cum. Capacity 20.0 M staging height R.C.C. overhead Reservoir as per departmental design, drawing & specification including R.C.C. Bored pile and pile cap, Laying distribution system of pipe water supply scheme in Zone-II at Rajballabhpur of Mograhat-I Block for Augmentation of Mega surface water based water supply scheme and providing Functional Household Tap Connection (FHTC) in Zone-II at Rajballabhpur of Mograhat-I Block within Mega surface water based water supply scheme for Falta-Mathurapur, district ¿ South 24 Parganas under South 24 Parganas water supply Sub-Division-II of South 24 Parganas Division-I, PHE Dte. (Number of FHTC ¿ 6219 Nos.) | AE SWSD-II,Assistant Engineer | JE1 | ORD/000418/2023-2024 | 1964/SWD-I | 24/08/2023 | 19/06/2024 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 1097.7 | 0 | 0 | 14
2 | SOUTH 24 PARAGANAS | Magrahat - I | South 24 Pgs W/S Division I | Providing 100% FHTC in Zone-II at Rajballabhpur Mouza of Mograhat-I Block within 'Mega Surface Water based Water Supply Scheme For Falta-Mathurapur Dist- South 24 pgns. Under South 24 pgns. W/S Division-I P.H.E. Dte. | SM/11973 | New | Material Requisition To Resource Division |  |  | RTOR000131/2023-2024 | 322/SWD-I | 25/04/2023 |  | Resource Division | 38.31 | 0 | 0 | 0
Total | [13 empty] | 1136.01 | 0 | 0