## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARAGANAS | Bhangar - I | S24 Pgns Mechanical | ERENDA Piped Water Supply Scheme in Bhangar-I Block in South 24 pgs under JJM | SM/12043 | New | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Erenda water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Bhangar-I] | Assistant Engineer | Junior Engineer | ORD/000497/2022-2023 | 300/SMD | 06/02/2023 | 07/05/2023 | B.T.PROJECTS PVT.LTD. | 23 | 0 | 0 | 0
2 | SOUTH 24 PARAGANAS | Bhangar - I | South 24 Pgs W/S Division I | ERENDA Piped Water Supply Scheme in Bhangar-I Block in South 24 pgs under JJM | SM/12043 | New | Sinking of 02 (Two) nos. big dia Tubewell 250mm X 150mm dia & 300 mtr. deep for ERENDA piped water supply scheme at headwork site (Dag No. 2362, Khatian No. 1233, JL. No. 120, Mouza- Erenda) & 2nd Tubewell site (Dag No. 391, Khatian No. 1321 , JL No. 132, Mouza- Noapara), Block- Bhangar-I, Dist.- South 24-Pgns. Under South 24 Parganas W/S Division-I, PHE Dte. | AE HQ-I |  | ORD/000167/2022-2023 | 1441/SWD-I | 26/09/2022 | 26/10/2022 | ABU TALEB MONDAL | 28.52 | 0 | 0 | 0
3 | SOUTH 24 PARAGANAS | Bhangar - I | South 24 Pgs W/S Division I | ERENDA Piped Water Supply Scheme in Bhangar-I Block in South 24 pgs under JJM | SM/12043 | New | Laying Distribution System, Rising Main, providing Functional Household Tap Connection (FHTC), Construction of Pump House cum Chlorine Room for ERENDA Piped Water Supply Scheme to accommodate FHTC in Bhangar-I Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas for implementation of JJM under South 24-Pgns. W/S Division-I, P.H.E. Dte. [No. of FHTC = 3188] | AE HQ-II | JE-4 | ORD/000428/2023-2024 | 2002/SWD-I | 28/08/2023 | 26/11/2023 | MAHMOOD ASSOCIATES PRIVATE LIMITED | 347.5 | 64.53 | 18.57 | 25
4 | SOUTH 24 PARAGANAS | Bhangar - I | South 24 Pgs W/S Division I | ERENDA Piped Water Supply Scheme in Bhangar-I Block in South 24 pgs under JJM | SM/12043 | New | Additional work for sinking of 02 (two) nos. Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for ERENDA PWSS at headwork site (Dag No. 2362, Khatian No. 1233, JL. No. 120, Mouza- Erenda) & 2nd Tube-well site (Dag No. 391 Khatian No. 1321, JL No. 132, Mouza- Noapara) of BHANGAR-I Block under South 24-Parganas W/S Division- I, P.H.E. Dte. [SM/12043] | AE HQ-I |  | ORD/000742/2022-2023 | 3568/SWD-I | 22/03/2023 | 06/04/2023 | ABUTALEB MONDAL | 3.13 | 0 | 0 | 0
5 | SOUTH 24 PARAGANAS | Bhangar - I | South 24 Pgs W/S Division I | ERENDA Piped Water Supply Scheme in Bhangar-I Block in South 24 pgs under JJM | SM/12043 | New | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method for ERENDA PWSS of Bhangar-I block for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/010678] | AE HQ-II | JE-4 | ORD/000748/2023-2024 | 562/SWD-I | 31/01/2024 | 15/02/2024 | TRAYEE DECORATOR | 15.88 | 6.52 | 41.09 | 100
6 | SOUTH 24 PARAGANAS | Bhangar - I | South 24 Pgs W/S Division I | ERENDA Piped Water Supply Scheme in Bhangar-I Block in South 24 pgs under JJM | SM/12043 | New | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method at 2nd Tubewell for ERENDA Piped Water Supply Scheme in BHANGAR-I Block for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [SM/12043] | AE HQ-II | JE-4 | ORD/000786/2023-2024 | 1069/SWD-I | 04/03/2024 | 03/04/2024 | ASHIM SHIL | 15.8 | 6.66 | 42.15 | 100
7 | SOUTH 24 PARAGANAS | Bhangar - I | South 24 Pgs W/S Division I | ERENDA Piped Water Supply Scheme in Bhangar-I Block in South 24 pgs under JJM | SM/12043 | New | Material Requisition To Resource Division |  |  | RTOR000053/2023-2024 | 287/SWD-I | 24/04/2023 |  | Resource Division | 14.98 | 0 | 0 | 0
8 | SOUTH 24 PARAGANAS | Bhangar - I | South 24 Pgs W/S Division I | ERENDA Piped Water Supply Scheme in Bhangar-I Block in South 24 pgs under JJM | SM/12043 | New | Material Requisition To Resource Division |  |  | RTOR000246/2023-2024 | 1007/SWD- I | 09/06/2023 |  | Resource Division | 19.64 | 0 | 0 | 0
Total | [13 empty] | 468.45 | 77.71 | 16.59