## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | KALIKAPUR piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas Under JJM. | SM/12207 | Augmentation | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/01985/2023-2024 | BP-2023-24-244 | 11/09/2023 |  | WBSEDCL | 8.05 | 0 | 0 | 0
2 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | KALIKAPUR piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas Under JJM. | SM/12207 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Kalikapur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Sonarpur] | Assistant Engineer | Junior Engineer | ORD/000297/2022-2023 | 447/SMD | 17/02/2023 | 18/05/2023 | INDIA ENTERPRISE | 26.01 | 23.79 | 91.46 | 80
3 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | KALIKAPUR piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas Under JJM. | SM/12207 | Augmentation | Supply & installation of LED board at PH No.-1&2 of Kalikapur water supply scheme under SMD, PHE Dte. |  |  | ORD/001180/2023-2024 | 114O/SMSD | 29/08/2023 | 13/09/2023 | ARPAN CONSTRUCTION | 0.78 | 0.39 | 50 | 100
4 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | KALIKAPUR piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas Under JJM. | SM/12207 | Augmentation | Supply & Fixing Bus bar,Cable laying including allied work at Pump House no-1 & 2 of Kalikapur W/S Scheme under SMD, P.H.E. Dte.(Block-Sonarpur) | Assistant Engineer | Junior Engineer | ORD/002384/2023-2024 | 1191/SMSD | 08/09/2023 | 23/09/2023 | INDIA ENTERPRISE | 1 | 1 | 100 | 100
5 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | KALIKAPUR piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas Under JJM. | SM/12207 | Augmentation | Supply & laying of cable including allied work at Pump House no-1 & 2 of Kalikapur W/S Scheme under SMD, P.H.E. Dte.(Block-Sonarpur) | Assistant Engineer | Junior Engineer | ORD/002385/2023-2024 | 1192/SMSD | 08/09/2023 | 23/09/2023 | INDIA ENTERPRISE | 0.97 | 0.56 | 57.89 | 100
6 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | KALIKAPUR piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas Under JJM. | SM/12207 | Augmentation | Improvement of outdoor illumination arrangement with allied works at Pump House no-2 of Kalikapur W/S Scheme under SMD, PHE Dte. (Block- Sonarpur) |  |  | ORD/002565/2023-2024 | 1188/SMSD | 08/09/2023 | 23/09/2023 | INDIA ENTERPRISE | 0.96 | 0.95 | 98.63 | 100
7 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | KALIKAPUR piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas Under JJM. | SM/12207 | Augmentation | Improvement of outdoor illumination arrangement with allied works at Pump House no-1 of Kalikapur W/S Scheme under SMD, PHE Dte. (Block- Sonarpur) |  |  | ORD/002566/2023-2024 | 1187/SMSD | 08/09/2023 | 23/09/2023 | INDIA ENTERPRISE | 0.93 | 0.93 | 100 | 100
8 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | KALIKAPUR piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas Under JJM. | SM/12207 | Augmentation | Distressed / Affected stretches of different road under P&RD Deptt. in West Bengal due to pipeline laying work by PHED [Sl. No.23] |  |  | BILL/00482/2024-2025 | BP-2024-25-293 | 11/09/2024 |  | WBSRDA SOUTH 24 PGS ALIPORE | 12.08 | 0 | 0 | 0
9 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | KALIKAPUR piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas Under JJM. | SM/12207 | Augmentation | Repairing and Renovation of Pumphouse, Office Room, Boundary Wall & allied works at 2nd TW site of Kalikapur PWSS within Sonarpur Block" KALIKAPUR Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission". (TSM/014873) | AE HQ-I |  | ORD/000010/2023-2024 | 34/SWD-I | 05/04/2023 | 04/06/2023 | SUSHANTA MANDAL | 13.21 | 12.34 | 93.41 | 100
10 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | KALIKAPUR piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas Under JJM. | SM/12207 | Augmentation | Construction of Boundary wall for OHR site for Sonarpur Block, in support work of Augmentation (part) of balance distribution pipeline (restoration) in different places of Zone-31 (Block-Sonarpur) under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. District. [PART-A, Front side (S), Right side (E) & Back side (N) 240 mtr] (SM/05835) | AE HQ-I |  | ORD/000256/2022-2023 | 1696/SWD-I | 01/11/2022 | 31/12/2022 | SUSHANTA MANDAL | 31.72 | 31.56 | 99.48 | 100
11 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | KALIKAPUR piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas Under JJM. | SM/12207 | Augmentation | Sinking of 02 (two) nos. Rig bored Tube well 250mm x 150mm dia & 300 mtr. deep for KALIKAPUR Piped Water Supply Scheme at headwork site & 2nd Tubewell site in Sonarpur Block Under South 24 Parganas W/S Division-I, PHE Dte. [SM/014837] | AE HQ-I |  | ORD/000261/2022-2023 | 1773/SWD-I | 07/11/2022 | 07/12/2022 | TAPAS KUMAR GIRI | 30.07 | 27.24 | 90.6 | 100
12 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | KALIKAPUR piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas Under JJM. | SM/12207 | Augmentation | Construction of 250 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) including design and drawing of pile foundation and pile cap after soil investigation along with Pump House, Rising Main, Laying distribution system, Functional Household Tap Connection (FHTC) to all households for KALIKAPUR Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Partganas, W/S Division-I for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. [No. of FHTC = 1717] | AE HQ-I,Assistant engineer (contractual) | JE-3 | ORD/000525/2022-2023 | 2959/SWD-I | 16/02/2023 | 13/12/2023 | HARBAUER INDIA PVT. LTD. | 445.06 | 98.87 | 22.21 | 10
13 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | KALIKAPUR piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas Under JJM. | SM/12207 | Augmentation | Construction of Pathway at 2nd site of Kalikapur PWSS within Sonarpur Block in connetion with" KALIKAPUR Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission"(SM/12207). |  |  | ORD/000562/2023-2024 | 2603/SWD-I | 16/10/2023 | 15/11/2023 | NILKANTHA ENTERPRISE | 4.53 | 2.19 | 48.34 | 100
14 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | KALIKAPUR piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas Under JJM. | SM/12207 | Augmentation | Supplying, fitting, fixing of Barbed wire fencing over existing Boundary wall & Construction of Drain at 2nd Tubewell site of Kalikapur PWSS within Sonarpur Block " KALIKAPUR Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission" (SM/12207) |  |  | ORD/000668/2023-2024 | 3019/SWD-I | 30/11/2023 | 15/12/2023 | KALAM ENTERPRISE | 1.89 | 0.89 | 47.23 | 100
15 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | KALIKAPUR piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas Under JJM. | SM/12207 | Augmentation | Additional work for sinking of 02 (two) nos. Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for KALIKAPUR PWSS at headwork site & 2nd Tubewell site of SONARPUR Block under South 24-Parganas W/S Division- I, P.H.E. Dte. [SM/12207] | AE HQ-I |  | ORD/000773/2022-2023 | 3652/SWD-I | 28/03/2023 | 12/04/2023 | TAPAS KUMAR GIRI | 3.14 | 3.14 | 100 | 100
16 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | KALIKAPUR piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas Under JJM. | SM/12207 | Augmentation | Construction of Pathway & allied works at Head work site of Kalikapur PWSS within Sonarpur Block "KALIKAPUR Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission". (TSM/014873) [ 2nd call] | Assistant engineer (contractual) | JE-3 | ORD/000815/2023-2024 | 1082/SWD-I | 04/03/2024 | 03/04/2024 | SUSHANTA MANDAL | 44.5 | 4.49 | 10.09 | 0
17 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | KALIKAPUR piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas Under JJM. | SM/12207 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000021/2023-2024 | 286/SWD-I | 24/04/2023 |  | Resource Division | 17.51 | 0 | 0 | 0
18 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | KALIKAPUR piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas Under JJM. | SM/12207 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000234/2023-2024 | 1006/SWD-I | 09/06/2023 |  | Resource Division | 10.58 | 0 | 0 | 0
Total | [13 empty] | 652.98 | 208.34 | 31.91