## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARAGANAS | Jaynagar - I | S24 Pgns Mechanical | Ground water based CHANDANESHWAR piped water supply scheme to accommodate FHTC in JAYNAGAR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/13011 | New | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/04093/2023-2024 | BP-2023-24-422 | 16/12/2023 |  | WBSEDCL | 8.62 | 0 | 0 | 0
2 | SOUTH 24 PARAGANAS | Jaynagar - I | S24 Pgns Mechanical | Ground water based CHANDANESHWAR piped water supply scheme to accommodate FHTC in JAYNAGAR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/13011 | New | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Chandaneswar water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Jaynagar-I] | Assistant Engineer | Junior Engineer | ORD/000573/2022-2023 | 598/SMD | 27/02/2023 | 28/05/2023 | AHALYA ENGINEERING WORKS | 22.93 | 10.38 | 45.28 | 90
3 | SOUTH 24 PARAGANAS | Jaynagar - I | S24 Pgns Mechanical | Ground water based CHANDANESHWAR piped water supply scheme to accommodate FHTC in JAYNAGAR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/13011 | New | Improvement of outdoor Illumination arrangement with allied works at Pump House no-2 of Chandaneswar W/S Scheme under SMD, P.H.E. Dte. (Block-Jaynagar-I) | Assistant Engineer | Junior Engineer | ORD/002778/2023-2024 | 114/SMSD | 25/01/2024 | 09/02/2024 | AHALYA ENGINEERING WORKS | 0.62 | 0 | 0 | 0
4 | SOUTH 24 PARAGANAS | Jaynagar - I | S24 Pgns Mechanical | Ground water based CHANDANESHWAR piped water supply scheme to accommodate FHTC in JAYNAGAR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/13011 | New | Improvement of outdoor Illumination arrangement with allied works at Pump House no-1 of Chandaneswar W/S Scheme under SMD, P.H.E. Dte. (Block-Jaynagar-I) | Assistant Engineer | Junior Engineer | ORD/002779/2023-2024 | 113/SMSD | 25/01/2024 | 09/02/2024 | AHALYA ENGINEERING WORKS | 0.62 | 0 | 0 | 0
5 | SOUTH 24 PARAGANAS | Jaynagar - I | South 24 Pgs W/S Division I | Ground water based CHANDANESHWAR piped water supply scheme to accommodate FHTC in JAYNAGAR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/13011 | New | Additional work for sinking of 02 (two) nos. Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for Chandaneswar PWSS of Joynagar-I Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division- I, P.H.E. Dte. [TSM/011097] | AE BSD | JE-1 | ORD/000005/2023-2024 | 26/SWD-I | 05/04/2023 | 20/04/2023 | VISHAL CONSTRUCTION CO. (E-MAIL ID :- VISHALCONSTRUCTION.VALVES@GMAIL.COM) | 3.13 | 1.56 | 50 | 100
6 | SOUTH 24 PARAGANAS | Jaynagar - I | South 24 Pgs W/S Division I | Ground water based CHANDANESHWAR piped water supply scheme to accommodate FHTC in JAYNAGAR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/13011 | New | Sinking of Rig bored 02 (Two) nos. 250mm X 150mm dia & 300 mtr. deep Tubewell by Rotary method for CHANDANESWAR PWSS of Joynagar-I Block Under South 24 Paraganas W/S Division-I, PHE Dte. [TSM/011097] | AE BSD | JE-1 | ORD/000213/2022-2023 | 1585/SWD-I | 17/10/2022 | 16/11/2022 | VISHAL CONSTRUCTION CO. | 28.53 | 13.11 | 45.97 | 100
7 | SOUTH 24 PARAGANAS | Jaynagar - I | South 24 Pgs W/S Division I | Ground water based CHANDANESHWAR piped water supply scheme to accommodate FHTC in JAYNAGAR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/13011 | New | Construction of boundary wall, approach road, development of land and other allied works for Ground water based CHANDANESWAR piped water supply scheme to accommodate FHTC in JOYNAGAR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of South 24 Parganas District.(SM/13011) |  |  | ORD/000222/2024-2025 | 2640/SWD-I | 07/06/2024 | 22/07/2024 | M/S L.P CONSTRUCTION | 62.59 | 0 | 0 | 0
8 | SOUTH 24 PARAGANAS | Jaynagar - I | South 24 Pgs W/S Division I | Ground water based CHANDANESHWAR piped water supply scheme to accommodate FHTC in JAYNAGAR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/13011 | New | Preparation and submission of Detailed Project Report of CHANDANESWAR Ground Water Based Piped Water Supply Scheme in JOYNAGAR-I Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD |  | ORD/000224/2021-2022 | 1928/SWD-I | 27/01/2022 | 26/02/2022 | GEO SOLUTION | 2.76 | 2.76 | 100 | 100
9 | SOUTH 24 PARAGANAS | Jaynagar - I | South 24 Pgs W/S Division I | Ground water based CHANDANESHWAR piped water supply scheme to accommodate FHTC in JAYNAGAR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/13011 | New | Construction of 02 (Two) nos. chlorination rooms at Chandaneswar of Jaynagar-I Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas under South 24-Pgns Water Supply Divn-I, PHE Dte. | AE BSD | JE-1 | ORD/000379/2022-2023 | 2213/SWD-I | 13/12/2022 | 11/02/2023 | ALISHA CONSTRUCTION | 11.52 | 5.03 | 43.63 | 100
10 | SOUTH 24 PARAGANAS | Jaynagar - I | South 24 Pgs W/S Division I | Ground water based CHANDANESHWAR piped water supply scheme to accommodate FHTC in JAYNAGAR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/13011 | New | Construction of 350 m3 capacity 20 M. staging height R.C.C. Over Head Water Reservoir as per departmental design, drawing & specification including R.C.C. Bored Pile & Pile Cap after soil investigation alongwith Providing 100% FHTC & Laying distribution system from Big dia deep Tube Well at CHANDANESWAR Mouza of JOYNAGAR-I Block due to improvement of water supply in the water Scarcity area/non command area under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. (No. of FHTC = 1531) | AE BSD | JE-1 | ORD/000489/2022-2023 | 2819/SWD-I | 03/02/2023 | 30/11/2023 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 511.76 | 92.08 | 17.99 | 30
11 | SOUTH 24 PARAGANAS | Jaynagar - I | South 24 Pgs W/S Division I | Ground water based CHANDANESHWAR piped water supply scheme to accommodate FHTC in JAYNAGAR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. | SM/13011 | New | Material Requisition To Resource Division |  |  | RTOR000304/2023-2024 | 2441/SWD-I | 30/09/2023 |  | Resource Division | 12.91 | 0 | 0 | 0
Total | [13 empty] | 665.98 | 124.93 | 18.76