## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | MATHURAPUR piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM. | SM/13500 | Augmentation | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/01508/2023-2024 | BP-2023-24-180 | 02/08/2023 |  | WBSEDCL | 3.18 | 0 | 0 | 0
2 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | MATHURAPUR piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM. | SM/13500 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Mathurapur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Bhangar-I] | Assistant Engineer | Junior Engineer | ORD/000503/2022-2023 | 321/SMD | 06/02/2023 | 07/05/2023 | ORIENTAL ENGINEERING CO. | 22.58 | 5.19 | 22.97 | 45
3 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | MATHURAPUR piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM. | SM/13500 | Augmentation | Improvement of outdoor illumination arrangement with allied works at Mathurapur PH-1 under Bhangar-I Block water supply scheme under SMD,PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002427/2023-2024 | 274/SMSD | 28/02/2024 | 14/03/2024 | ORIENTAL ENGINEERING CO. | 0.89 | 0.44 | 50 | 100
4 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | MATHURAPUR piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM. | SM/13500 | Augmentation | Distressed / Affected stretches of different road under P&RD Deptt. in West Bengal due to pipeline laying work by PHED [Sl. no.43] |  |  | BILL/00466/2024-2025 | BP-2024-25-293 | 11/09/2024 |  | WBSRDA SOUTH 24 PGS ALIPORE | 27.93 | 0 | 0 | 0
5 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | MATHURAPUR piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM. | SM/13500 | Augmentation | Sinking of 02 (Two) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method for MATHURAPUR PWSS of BHANGAR-I block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/015390] | AE HQ-I |  | ORD/000627/2022-2023 | 3236/SWD-I | 01/03/2023 | 31/03/2023 | SABYASACHI CHAKI | 31.6 | 13.49 | 42.67 | 50
6 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | MATHURAPUR piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM. | SM/13500 | Augmentation | Construction of 250 cum. capacity 20 mtr. staging height RCC Over Head Reservoir alongwith Soil Investigation work, Laying Distribution System and Rising Main, providing Functional Household Tap Connection (FHTC), Construction of Pump House cum Chlorine Room etc. for Mathurapur Piped Water Supply Scheme, Block-Bhangar-I, District-South 24-Parganas for for implementation of JJM under South 24-Pgns. W/S Division-I, P.H.E. Dte. [No. of FHTC = 1611] | AE HQ-I | JE-4 | ORD/000750/2022-2023 | 3612/SWD-I | 24/03/2023 | 18/01/2024 | MAHMOOD ASSOCIATES PRIVATE LIMITED | 404.21 | 204.3 | 50.54 | 50
7 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | MATHURAPUR piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM. | SM/13500 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000058/2023-2024 | 287/SWD-I | 24/04/2023 |  | Resource Division | 33.04 | 0 | 0 | 0
8 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | MATHURAPUR piped water supply scheme to accommodate FHTC in BHANGAR-I block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM. | SM/13500 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000256/2023-2024 | 1007/SWD- I | 09/06/2023 |  | Resource Division | 9.92 | 0 | 0 | 0
Total | [13 empty] | 533.36 | 223.42 | 41.89