## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Regular Up-gradation and Up-Keepment of Water Quality Monitoring, Programme Management & its implementation throughout the State related to WQMSP under Jal Jeevan Mission. | SM/13890 | Support-WQMSP | Day to day upkeep, upgradation of all water quality applications for data collection, alert generation system for contaminated sources, stock & faulty instruments and onsite sanitary survey data, integrated with WQMIS structure through cloud based secured survey, data repository system and engagement of efficient manpower for resource monitoring & management of water quality in drinking water sector for all districts of West Bengal for the period of 12 months for PHED, Govt. of West Bengal. |  |  | ORD/000473/2022-2023 | 2726/SWD-I | 24/01/2023 | 19/01/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT LTD | 226.19 | 82.77 | 36.59 | 75
2 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Regular Up-gradation and Up-Keepment of Water Quality Monitoring, Programme Management & its implementation throughout the State related to WQMSP under Jal Jeevan Mission. | SM/13890 | Support-WQMSP | Day to day upkeep, upgradation of State Water Quality Dash board, web interface, integration of stock management, laboratory assessment, all water quality data & laboratory data management for analytical reports (Online & Offline). Through over all coordination, supervision on water quality all across the state for the period of 12 months for PHED, Govt. of West Bengal. |  |  | ORD/000474/2022-2023 | 2705/SWD-I | 24/01/2023 | 19/01/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT LTD | 210.83 | 52.71 | 25 | 75
3 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Regular Up-gradation and Up-Keepment of Water Quality Monitoring, Programme Management & its implementation throughout the State related to WQMSP under Jal Jeevan Mission. | SM/13890 | Support-WQMSP | Continuation order for the work of Day to day upkeep, upgradation of State Water Quality Dash board, web interface, integration of stock management, laboratory assessment, all water quality data & laboratory data management for analytical reports (Online & Offline). Through over all coordination, supervision on water quality all across the state for the period of 1 months for PHED, Govt. of West Bengal. (For the Month of February, 2024) |  |  | ORD/000772/2023-2024 | 486/SWD-I | 25/01/2024 | 24/02/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT LTD | 17.57 | 8.78 | 50 | 100
4 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Regular Up-gradation and Up-Keepment of Water Quality Monitoring, Programme Management & its implementation throughout the State related to WQMSP under Jal Jeevan Mission. | SM/13890 | Support-WQMSP | Continution order for the work of Day to day upkeep, upgradation of all water quality applications for data collection, alert generation system for contaminated sources, stock & faulty instruments and onsite sanitary survey data, integrated with WQMIS structure through cloud based secured survey, data repository system and engagement of efficient manpower for resource monitoring & management of water quality in drinking water sector for all districts of West Bengal for the period of 1 month for PHED, Govt. of West Bengal. (For the Month of February, 2024) |  |  | ORD/000773/2023-2024 | 487/SWD-I | 25/01/2024 | 24/02/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT LTD | 18.85 | 9.42 | 50 | 100
Total | [13 empty] | 473.43 | 153.68 | 32.46