## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Proposed Ground water based MALLARCHAK ISHWARIPUR piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arse | SM/14661 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2 of Mallarchak Ishwaripur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Mograhat-II] | Assistant Engineer | Junior Engineer | ORD/000414/2022-2023 | 3812/SMD | 29/12/2022 | 29/03/2023 | JAL PRAVAHIKA PVT. LTD. | 22.36 | 0 | 0 | 0
2 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based MALLARCHAK ISHWARIPUR piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arse | SM/14661 | Augmentation | Laying distribution system, Rising main, Funtional Household Tap connection(FHTC) alongwith construction of Chlorine Room (2 Nos.) for Augmentation of MALLARCHAK ISHWARIPUR Mouza of MOGRAHAT-II Block, for implementation of JJM under augmentation of surface water based W/S scheme in the arsenic affected areas of South 24 Parganas district under Baruipur sub Division of South 24 Pgns. W/S Division-I, P.H.E Dte. (No of FHTC = 1962) [TSM/016725] | AE S24D1,AE SWSD-II | JE3,JE4 | ORD/000065/2023-2024 | 368/SWD-I | 27/04/2023 | 26/07/2023 | M/S ROY CHOWDHURY AND CO. | 290.21 | 87.22 | 30.05 | 50
3 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based MALLARCHAK ISHWARIPUR piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arse | SM/14661 | Augmentation | Sinking of 02 (Two) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell by Rotary method for MOLLARCHAK ISHWARPUR PWSS of MOGRAHAT-II block under South 24-Parganas W/S Division-I, P.H.E. Dte. for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district. [TSM/016725] | AE SWSD-II | JE4 | ORD/000626/2022-2023 | 3240/SWD-I | 01/03/2023 | 31/03/2023 | MONDAL CONSTRUCTION (MADHYAMGRAM) | 31.71 | 0 | 0 | 0
4 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based MALLARCHAK ISHWARIPUR piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arse | SM/14661 | Augmentation | Preparation and submission of Detailed Project Report of Ground Water Based Mallarchak Ishwaripur Piped Water Supply Scheme to accommodate FHTC in Magrahat-II Block under South 24-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. |  |  | ORD/000995/2022-2023 | 1466\SWD-I | 27/09/2022 | 27/10/2022 | GEO SOLUTION | 2.6 | 1.3 | 49.98 | 100
5 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based MALLARCHAK ISHWARIPUR piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arse | SM/14661 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000130/2022-2023 | 3389/SWD-I | 10/03/2023 |  | Resource Division | 12.09 | 0 | 0 | 0
6 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based MALLARCHAK ISHWARIPUR piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arse | SM/14661 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000173/2023-2024 | 629 | 19/05/2023 |  | Resource Division | 27.39 | 0 | 0 | 0
Total | [13 empty] | 386.35 | 88.51 | 22.91