## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Ground water based CHANDIPUR (PART) piped water supply scheme to accommodate FHTC in BUDGE BUDGE - II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affec | SM/14877 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 for Augmentation of Chandipur (Part) water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Bishnupur-II] | Assistant Engineer -II | Junior Engineer | ORD/001504/2022-2023 | 814/SMD | 17/03/2023 | 15/06/2023 | JOYSHREE CONCERN | 12.96 | 6.51 | 50.24 | 100
2 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Ground water based CHANDIPUR (PART) piped water supply scheme to accommodate FHTC in BUDGE BUDGE - II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affec | SM/14877 | Augmentation | Supply, Delivery and Fitting Fixing of the additional materials for PH No.-1 of Augmentation of Chandipur (Part) Water supply scheme under JJM under South 24 Pgs. Mechanical Division, PHE Dte. (Block : Bishnupur-I) [SM/14877] | Assistant Engineer -II | Junior Engineer | ORD/002327/2023-2024 | 1301-AE-II-SMD | 30/11/2023 | 15/12/2023 | JOYSHREE CONCERN | 0.4 | 0.4 | 100 | 100
3 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Ground water based CHANDIPUR (PART) piped water supply scheme to accommodate FHTC in BUDGE BUDGE - II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affec | SM/14877 | Augmentation | Miscellaneous works in the interest of improvement of outdoor illumination arrangement etc. at P.H. No. 1 under Augmentation of Chandipur (Part) Water Supply Scheme, under South 24 Pgs Mechanical Division, PHE Dte. (Block: Bishnupur-II) (SM/14877) | Assistant Engineer -II | Junior Engineer | ORD/002609/2023-2024 | 224-AE-II-SMD | 01/03/2024 | 16/03/2024 | DYNATECH SOLUTION | 0.75 | 0.75 | 100 | 100
4 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Ground water based CHANDIPUR (PART) piped water supply scheme to accommodate FHTC in BUDGE BUDGE - II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affec | SM/14877 | Augmentation | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell by Rotary method for CHANDIPUR PWSS of BUDGE BUDGE-II block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/017980] | AE SWSD-I |  | ORD/000599/2022-2023 | 3127/SWD-I | 24/02/2023 | 26/03/2023 | PROJECT AND MAINTENANCE | 15.88 | 15.18 | 95.56 | 100
5 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Ground water based CHANDIPUR (PART) piped water supply scheme to accommodate FHTC in BUDGE BUDGE - II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affec | SM/14877 | Augmentation | Construction of Pump House at Tubewell site for Chandipur (part) PWSS to accommodate FHTC in Budge Budge-II Block under South 24-Pgns W/S Division-I, PHE Dte. for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic Affected Area of South 24-Pgns. District (TSM/017980) | AE SWSD-I |  | ORD/000654/2022-2023 | 3352/SWD-I | 09/03/2023 | 08/05/2023 | MODERN CONSTRUCTION | 10.35 | 4.97 | 48.04 | 100
6 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Ground water based CHANDIPUR (PART) piped water supply scheme to accommodate FHTC in BUDGE BUDGE - II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affec | SM/14877 | Augmentation | Construction of Boundary Wall at Tubewell site for Chandipur (part) PWSS to accommodate FHTC in Budge Budge-II Block under South 24-Pgns W/S Division-I, PHE Dte. for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic Affected Area of South 24-Pgns. District (TSM/017980) | AE SWSD-I |  | ORD/000655/2022-2023 | 3353/SWD-I | 09/03/2023 | 23/04/2023 | S.M ENTERPRISE | 8.02 | 6.97 | 86.93 | 100
7 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Ground water based CHANDIPUR (PART) piped water supply scheme to accommodate FHTC in BUDGE BUDGE - II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affec | SM/14877 | Augmentation | Interconnection from Tubewell to Head Work Site for chandipur (part) PWSS to accommodate FHTC in Budge Budge-II Block under South 24-Pgns W/S Division-I, PHE Dte. for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic Affected Area of South 24-Pgns. District (TSM/017980) | AE SWSD-I |  | ORD/000656/2022-2023 | 3355/SWD-I | 09/03/2023 | 08/04/2023 | SUJOY SADHUKHAN | 3.97 | 3.2 | 80.53 | 100
8 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Ground water based CHANDIPUR (PART) piped water supply scheme to accommodate FHTC in BUDGE BUDGE - II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affec | SM/14877 | Augmentation | Laying distribution pipeline for Chandipur (part) PWSS to accommodate FHTC in Budge Budge-II Block under South 24-Pgns W/S Division-I, PHE Dte. for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic Affected Area of South 24-Pgns. District (TSM/017980) | AE SWSD-I | JE-2 | ORD/000657/2022-2023 | 3356/SWD-I | 09/03/2023 | 08/05/2023 | P S CONSTRUCTION | 41.26 | 30.62 | 74.22 | 100
9 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Ground water based CHANDIPUR (PART) piped water supply scheme to accommodate FHTC in BUDGE BUDGE - II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affec | SM/14877 | Augmentation | Land Development of Tubewell site and construction of approach road of Chandipur (Part) Piped Water Supply Scheme to accommodate FHTC in Budge Budge-II under South 24-Pgns W/S Division-I for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic Affected Areas of South 24 Parganas District. (SM/14877) |  |  | ORD/000814/2023-2024 | 1150/SWD-I | 07/03/2024 | 06/04/2024 | MS KRISHNA MONDAL | 9.6 | 4.77 | 49.66 | 100
10 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Ground water based CHANDIPUR (PART) piped water supply scheme to accommodate FHTC in BUDGE BUDGE - II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affec | SM/14877 | Augmentation | Preparation and submission of Detailed Project Report of Ground Water Based Chandipur Piped Water Supply Scheme to accommodate FHTC in Budge Budge-II Block under South 24-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district.. |  |  | ORD/000994/2022-2023 | 1534/SWD-I | 29/09/2022 | 29/10/2022 | GEO SOLUTION | 2.37 | 1.17 | 49.36 | 100
Total | [13 empty] | 105.58 | 74.55 | 70.61