## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARAGANAS | Kultali | S24 Pgns Mechanical | DETAILED PROJECT REPORT FORPROPOSED GROUND WATER BASED DONGAJORA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN KULTALI BLOCK UNDER SOUTH 24 PARGANAS W/S DIVISION-I, SOUTH 24 PARGANAS DISTRICT | SM/15633 | New | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 of Dongajora water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Kultali] | Assistant Engineer | Junior Engineer | ORD/000113/2023-2024 | 1013/SMD | 11/04/2023 | 10/07/2023 | BIDYUT KUMAR MUKHERJEE | 10.81 | 0 | 0 | 0
2 | SOUTH 24 PARAGANAS | Kultali | South 24 Pgs W/S Division I | DETAILED PROJECT REPORT FORPROPOSED GROUND WATER BASED DONGAJORA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN KULTALI BLOCK UNDER SOUTH 24 PARGANAS W/S DIVISION-I, SOUTH 24 PARGANAS DISTRICT | SM/15633 | New | Construction of Boundary Wall, Chlorine Room along with Laying Distribution, Rising Main, Functional House Hold Tap Connection (FHTC) at DONGAJORA of KULTALI Block for Ground Water Based DONGAJORA Piped Water Supply Scheme under South 24 Paragana W/S Division-I, PHE Dte. under South 24 Pgns. Dist. (TSM/020398) | AE BSD |  | ORD/000702/2022-2023 | 3511/SWD-I | 17/03/2023 | 15/06/2023 | AYUSH ENTERPRISE | 77.23 | 0 | 0 | 0
3 | SOUTH 24 PARAGANAS | Kultali | South 24 Pgs W/S Division I | DETAILED PROJECT REPORT FORPROPOSED GROUND WATER BASED DONGAJORA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN KULTALI BLOCK UNDER SOUTH 24 PARGANAS W/S DIVISION-I, SOUTH 24 PARGANAS DISTRICT | SM/15633 | New | Preparation and submission of Detailed Project Report of Ground Water Based Dongajora Piped Water Supply Scheme to accommodate FHTC in Kultoli Block under South 24-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district.. |  |  | ORD/000986/2022-2023 | 1483/SWD-I | 27/09/2022 | 27/10/2022 | GEO SOLUTION | 2.4 | 1.2 | 49.86 | 100
Total | [13 empty] | 90.44 | 1.2 | 1.32