## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Proposed Ground water based PASCHIM MADHABPUR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Aff | SM/16128 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 of Paschim Madhabpur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Baruipur] | Assistant Engineer | Junior Engineer | ORD/000090/2023-2024 | 1083/SMD | 18/04/2023 | 17/07/2023 | S.S. SIGNS | 9.38 | 0 | 0 | 0
2 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based PASCHIM MADHABPUR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Aff | SM/16128 | Augmentation | Construction of Boundary Wall, Pump House cum Chlorine Room along with Laying distribution, Rising main, Funtional Household Tap Connection (FHTC) for PASCHIM MADHABPUR PWSS of BARUIPUR Block for Augmentation of surface water based W/S scheme in the arsenic affected areas of South 24 Parganas district under Baruipur sub Division of South 24 Pgns. W/S Division-I, P.H.E Dte. [TSM/018425] | AE BSD | JE RWS | ORD/000088/2023-2024 | 346/SWD-I | 26/04/2023 | 25/07/2023 | S.N. ENTERPRISE | 67.07 | 14.61 | 21.78 | 30
3 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based PASCHIM MADHABPUR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Aff | SM/16128 | Augmentation | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method for PASCHIM MADHABPUR PWSS of BARUIPUR Block for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/018425] (3rd Call) | AE BSD |  | ORD/000230/2023-2024 | 1406/SWD-I | 14/07/2023 | 13/08/2023 | KHAN CONSTRUCTION | 15.87 | 0 | 0 | 0
4 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based PASCHIM MADHABPUR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Aff | SM/16128 | Augmentation | Preparation and submission of Detailed Project Report of Ground Water Based Pachim Madhabpur Piped Water Supply Scheme to accommodate FHTC in Baruipur Block under South 24-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. |  |  | ORD/000936/2022-2023 | 1237/SWD-I | 07/09/2022 | 07/10/2022 | GEO SOLUTION | 2.37 | 1.18 | 49.96 | 100
5 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based PASCHIM MADHABPUR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Aff | SM/16128 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000262/2023-2024 | 2427/SWD-I | 30/09/2023 |  | Resource Division | 9.81 | 0 | 0 | 0
6 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based PASCHIM MADHABPUR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Aff | SM/16128 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000331/2023-2024 | 273/SWD-I | 10/01/2024 |  | Resource Division | 2.05 | 0 | 0 | 0
Total | [13 empty] | 106.55 | 15.79 | 14.82