## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | Proposed Ground water based SANKARPUR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Ar | SM/16134 | Augmentation | Road restoration of 1) Conslrucfion Of Biluminous Road From Mirpur School To Matarmaa Veri 2) WB02328, L043-Sankarpur II GP Office Ie Rajgara School via Gocharan Road |  |  | BILL/01706/2024-2025 | BP-2024-25-791 | 25/10/2024 | 25/10/2024 | W.B.S.R.D.A., SOUTH TWENTY FOUR PARGANAS DIVISION | 4.04 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Proposed Ground water based SANKARPUR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Ar | SM/16134 | Augmentation | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/00125/2024-2025 | BP-2024-25-35 | 24/04/2024 | 24/04/2024 | WBSEDCL | 5 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Proposed Ground water based SANKARPUR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Ar | SM/16134 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 & 2 of Sankarpur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Baruipur] | Assistant Engineer | Junior Engineer | ORD/000095/2023-2024 | 1093/SMD | 18/04/2023 | 17/07/2023 | JAI BHARAT COMMERCIAL CORPORATION | 21.77 | 0 | 0 | 40
4 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Proposed Ground water based SANKARPUR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Ar | SM/16134 | Augmentation | Improvement of outdoor Illumination arrangement with allied works at Pump House no.2 of Sankarpur W/S Scheme under SMD, P.H.E. Dte. (Block-Sankarpur)(SM/16134) | Assistant Engineer | Junior Engineer | ORD/000276/2024-2025 | 912/SMSD | 25/06/2024 | 10/07/2024 | JAI BHARAT COMMERCIAL CORPORATION | 0.73 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Proposed Ground water based SANKARPUR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Ar | SM/16134 | Augmentation | Improvement of outdoor Illumination arrangement with allied works at Pump House no.1 of Sankarpur W/S Scheme under SMD, P.H.E. Dte. (Block-Sankarpur)(SM/16134) | Assistant Engineer | Junior Engineer | ORD/000277/2024-2025 | 911/SMSD | 25/06/2024 | 10/07/2024 | JAI BHARAT COMMERCIAL CORPORATION | 0.73 | 0 | 0 | 100
6 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Proposed Ground water based SANKARPUR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Ar | SM/16134 | Augmentation | Supply & Fixing main switch & Bus bar at Pump House no-1 & 2 of Sankarpur W/S Scheme under SMD, P.H.E. Dte.(Block-Baruipur)(SM/16134) | Assistant Engineer | Junior Engineer | ORD/000294/2024-2025 | 892/SMSD | 19/06/2024 | 04/07/2024 | JAI BHARAT COMMERCIAL CORPORATION | 0.58 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based SANKARPUR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Ar | SM/16134 | Augmentation | Construction of Boundary Wall, Pump House cum Chlorine Room along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) for SANKARPUR MOUZA Piped Water Supply Scheme of BARUIPUR Block for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district under South 24-Pgns. W/S Division-I, PHE Dte. [No. of FHTC =556] [TSM/017762] | AE BSD | JE-1 | ORD/000161/2023-2024 | 934/SWD-I | 06/06/2023 | 04/09/2023 | DIPTI ENTERPRISE | 138.93 | 0 | 0 | 80
8 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based SANKARPUR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Ar | SM/16134 | Augmentation | Sinking of 02 (Two) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method for SANKARPUR PWSS of BARUIPUR Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/017762] | AE BSD | JE-1 | ORD/000652/2022-2023 | 3349/SWD-I | 09/03/2023 | 08/04/2023 | TAPAS KUMAR GIRI | 31.8 | 0 | 0 | 50
9 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based SANKARPUR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Ar | SM/16134 | Augmentation | Preparation and submission of Detailed Project Report of Ground Water Based Sankarpur Piped Water Supply Scheme to accommodate FHTC in Baruipur Block under South 24-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. |  |  | ORD/000932/2022-2023 | 1224/SWD-I | 06/09/2022 | 06/10/2022 | GEO SOLUTION | 2.46 | 2.45 | 99.62 | 100
10 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Proposed Ground water based SANKARPUR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Ar | SM/16134 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000113/2023-2024 | 294/SWD-I | 25/04/2023 | 25/04/2023 | Resource Division | 25.88 | 0 | 0 | 0
Total | [13 empty] | 231.92 | 2.45 | 1.06