## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Augmentation of laying distribution system to extend the benefit of 100% Household in ZONE-IV at HIJALHAT under MOGRAHAT-I block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply | SM/16187 | Augmentation | Shifting of 2 nos. LT pole for construction of OHR at Alampur under JJM project of PHED |  |  | BILL/01763/2023-2024 | BP-2023-24-617 | 22/01/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.32 | 0 | 0 | 0
2 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Augmentation of laying distribution system to extend the benefit of 100% Household in ZONE-IV at HIJALHAT under MOGRAHAT-I block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply | SM/16187 | Augmentation | Construction of 900 Cum. capacity RCC Overhead Reservoir of 20 Mtr. Staging Height as per departmental design, drawing & specification with RCC Bored Pile & Pile Cap including Soil Investigation and foundation design, Boundary Wall and Laying Distribution System including FHTC for Augmentation of Laying Distribution System to extend benefit off 100% household in Zone-IV at HIJALHAT under Mograhat-I Block within Mega Surface Water based Water Supply Scheme of Falta-Mathurapur Dist.-South 24-Parganas under South 24-Pgns. W/S Division-I, PHE Dte. [No. of FHTC = 6310] [TSM/015076] | AE SWSD-II | JE4 | ORD/000125/2023-2024 | 568/SWD-I | 15/05/2023 | 10/03/2024 | M/S GHOSH AND CO. | 1160.71 | 250.57 | 21.59 | 15
3 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Augmentation of laying distribution system to extend the benefit of 100% Household in ZONE-IV at HIJALHAT under MOGRAHAT-I block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply | SM/16187 | Augmentation | Construction of FHTC platform, road restoration and other allied works for Zone-IV (Hijalhat) to accommodate FHTC in Magrahat-I Block under South 24-Pgns W/S Divn-I, PHE Dte. South 24 Parganas District. |  |  | ORD/000495/2024-2025 | 3867/SWD-I | 02/09/2024 | 01/12/2024 | MILAN GHOSH | 310.34 | 0 | 0 | 0
4 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Augmentation of laying distribution system to extend the benefit of 100% Household in ZONE-IV at HIJALHAT under MOGRAHAT-I block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply | SM/16187 | Augmentation | Design of Route survey of distribution system of Mograhat Zone-IV within Mograhat-I Block for Augmentation of Laying Distribution System, to extend the benefit of 100% households in Zone-IV at HIJALHAT of Mograhat-I Block within "Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, Dist. South 24-Pgs. under South 24-Pgns W/S Divn-I, P.H.E. Dte. (Route Surveying of 60 KM) [TSM/015076] | AE SWSD-II | JE4 | ORD/000658/2022-2023 | 3361/SWD-I | 09/03/2023 | 16/03/2023 | GEO SOLUTION | 2.38 | 2.37 | 99.63 | 0
5 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Augmentation of laying distribution system to extend the benefit of 100% Household in ZONE-IV at HIJALHAT under MOGRAHAT-I block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply | SM/16187 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000063/2023-2024 | 284/SWD-I | 24/04/2023 |  | Resource Division | 5.03 | 0 | 0 | 0
Total | [13 empty] | 1478.78 | 252.94 | 17.1