## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Augmentation of laying distribution system to extend the benefit of 100% Households in ZONE-II at JOYNAGAR-II block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply division-I, | SM/18222 | Augmentation | Joynagar-Moydah-Jibonmondalerhat Road from1.50Kmp to 6.00kmp and 7.30 Kmp to 8.40Kmp. Restoration of Hard Shoulder due to laying of Pipeline by PHED. Go WO under Lakshmikantapur Highway Sub-Division of Diamond Harbour Highway Division, P.W.(Roads Directorate in District of South 24- Parganas. |  |  | BILL/00655/2024-2025 | BP-2024-25-396 | 04/10/2024 | 04/10/2024 | EXECUTIVE ENGINEER, SOUTH 24 PGS HIGHWAY DIVISION PW (ROADS) DTE | 11.8 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Augmentation of laying distribution system to extend the benefit of 100% Households in ZONE-II at JOYNAGAR-II block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply division-I, | SM/18222 | Augmentation | Payment of Enhanced GST Rate vide W/O No.2336/SWD-I dt. 22/02/2022 |  |  | BILL/01807/2023-2024 | BP-2023-24-637 | 31/01/2024 | 31/01/2024 | SAMIRON GHOSH | 20.95 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Augmentation of laying distribution system to extend the benefit of 100% Households in ZONE-II at JOYNAGAR-II block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply division-I, | SM/18222 | Augmentation | Payment of Enhanced GST Rate vide W/O No.2483/SWD-I dt. 02/03/2022 |  |  | BILL/01809/2023-2024 | BP-2023-24-637 | 31/01/2024 | 31/01/2024 | SAMIRON GHOSH | 4.66 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Augmentation of laying distribution system to extend the benefit of 100% Households in ZONE-II at JOYNAGAR-II block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply division-I, | SM/18222 | Augmentation | Making arrangements for laying of 406.4 mm dia M.S. pipe of Tertiary Grid over Canal at Jibon Mandaler Haat under Augmentation of laying distribution system to extend the benefit of 100% Households in ZONE-II at JOYNAGAR-II Block within Mega surface water based water supply scheme of Falta-Mathurapur Dist.- South 24 pgns. under South 24 pgns Water Supply Division-I, PHE Dte. [SM/18222] |  |  | ORD/000075/2025-2026 | 1578/SWD-I | 11/06/2025 | 26/07/2025 | SRIJON ENTERPRISE | 32.71 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Augmentation of laying distribution system to extend the benefit of 100% Households in ZONE-II at JOYNAGAR-II block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply division-I, | SM/18222 | Augmentation | Laying distribution system of piped water supply at Zone-II-B (Mayahauri) of Joynagar-II Block, of BARUIPUR Sub-Division, for ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under South 24 Parganas W/S Division - I, P.H.E. Dte. | AE BSD | JE-1 | ORD/000400/2021-2022 | 2483/SWD-I | 02/03/2022 | 14/06/2025 | SAMIRON GHOSH | 385.01 | 87.02 | 22.6 | 95
6 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Augmentation of laying distribution system to extend the benefit of 100% Households in ZONE-II at JOYNAGAR-II block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply division-I, | SM/18222 | Augmentation | Laying distribution system of piped water supply at Zone-II-A (Mayahauri) of Joynagar-II Block, of BARUIPUR Sub-Division, for ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under South 24 Parganas W/S Division - I, P.H.E. Dte. | AE BSD | JE-2 | ORD/000408/2021-2022 | 2336/SWD-I | 22/02/2022 | 04/10/2025 | SAMIRON GHOSH | 579.07 | 391 | 67.52 | 95
7 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Augmentation of laying distribution system to extend the benefit of 100% Households in ZONE-II at JOYNAGAR-II block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply division-I, | SM/18222 | Augmentation | Construction of 1250 Cu.m. capacity 20 M. staging height R.C.C. Over Head Water Reservoir as per departmental design, drawing & specification including R.C.C. Bored Pile & Pile Cap For " Augmentation of laying distribution system to extend the benefit of 100% Household in ZONE-II at JOYNAGAR-II block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply division-I, PHE Dte.(TSM/016052) | AE BSD |  | ORD/000431/2023-2024 | 2005/SWD-I | 28/08/2023 | 23/06/2024 | M/S. S.S. ENTERPRISE | 435.92 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Augmentation of laying distribution system to extend the benefit of 100% Households in ZONE-II at JOYNAGAR-II block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply division-I, | SM/18222 | Augmentation | Construction of restoration of road, pipeline protection works and other allied works for Augmentation of laying distribution system to extend the benefit of 100% House Hold in ZONE-II at JOYNAGAR-II block within Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur District South 24 Parganas under South 24 Pgns W/S Division-I, PHE Dte. (SM/18222) (2nd call) | AE BSD | JE-1 | ORD/000736/2024-2025 | 4634/SWD-I | 14/11/2024 | 27/06/2025 | P.L. CONSTRUCTION | 83.92 | 0 | 0 | 45
9 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Augmentation of laying distribution system to extend the benefit of 100% Households in ZONE-II at JOYNAGAR-II block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply division-I, | SM/18222 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000065/2022-2023 | 2980/SWD-I | 20/02/2023 | 20/02/2023 | Resource Division | 28.62 | 0 | 0 | 0
10 | SOUTH 24 PARGANAS |  | South 24 Pgs W/S Division I | Augmentation of laying distribution system to extend the benefit of 100% Households in ZONE-II at JOYNAGAR-II block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply division-I, | SM/18222 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000293/2023-2024 | 2431/SWD-I | 30/09/2023 | 30/09/2023 | Resource Division | 709.28 | 0 | 0 | 0
Total | [13 empty] | 2291.94 | 478.01 | 20.86