## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | BONHOOGHLY piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/18225 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Bonhoogly water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Sonarpur] | Assistant Engineer | Junior Engineer | ORD/001419/2022-2023 | 3458/SMD | 23/12/2022 | 23/03/2023 | DEY ENTERPRISE | 25.93 | 0 | 0 | 0
2 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | BONHOOGHLY piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/18225 | Augmentation | SINKING OF 02 (TWO) NOS. TUBE WELL (250X150)MM DIA, 300M DEEP FOR THE BONHOOGHLY PIPED WATER SUPPLY SCHEME AT HEADWORK SITE AND 2ND TUBE WELL SITE, BLOCK- SONARPUR, UNDER SOUTH 24 PARGANAS WATER SUPPLY DIV-I. PHE.DTE. (TSM/016321) | AE HQ-I | JE-3 | ORD/000090/2023-2024 | 443/SWD-I | 03/05/2023 | 02/06/2023 | SARFARAZ CONSTRUCTION | 30.04 | 7.05 | 23.47 | 50
3 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | BONHOOGHLY piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/18225 | Augmentation | Additional work for sinking of 02 (two) nos. Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for BONHOOGHLY PWSS at headwork site & 2nd Tubewell site of SONARPUR Block under South 24-Parganas W/S Division- I, P.H.E. Dte. [SM/016321] | AE HQ-I | JE-3 | ORD/000091/2023-2024 | 444/SWD-I | 03/05/2023 | 18/05/2023 | SARFARAZ CONSTRUCTION | 3.14 | 0.78 | 25 | 50
4 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | BONHOOGHLY piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/18225 | Augmentation | Construction of 400 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) including design and drawing of pile foundation and pile cap after soil investigation along with Pump House, Rising Main, Laying distribution system, Functional Household Tap Connection (FHTC) to all households for BONHOOGHLY Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Partganas, W/S Division-I for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. [No. of FHTC = 3040] | AE HQ-I,AE HQ-II | JE RWS, Sonarpur Block | ORD/000175/2023-2024 | 972/SWD-I | 08/06/2023 | 03/04/2024 | DASGUPTA CONSTRUCTION | 610.86 | 48.52 | 7.94 | 50
5 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | BONHOOGHLY piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/18225 | Augmentation | Construction of Boundary Wall, Development of land, Pathway, Drain & others allied works of "BONHOOGHLY Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission". (SM/18225) |  |  | ORD/000418/2024-2025 | 3739/SWD-I | 27/08/2024 | 11/10/2024 | M/S SANJAY ADHIKARI | 33.99 | 0 | 0 | 0
6 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | BONHOOGHLY piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/18225 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000011/2023-2024 | 1721/SWD-I | 08/08/2023 |  | Resource Division | 25.05 | 0 | 0 | 0
7 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | BONHOOGHLY piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District Under JJM | SM/18225 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000314/2023-2024 | 247/SWD-I | 10/01/2024 |  | Resource Division | 18.73 | 0 | 0 | 0
Total | [13 empty] | 747.72 | 56.36 | 7.54