## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Ground water based UTTAR KAZIRHAT piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Are | SM/18375 | Augmentation | Restoration charges of damage road due to phed pipe laying between Ch.7.40 km of Thakurpukur Bibirhat Bakhrahat Raipur Road under South 24 pgs. Division, PWD during 2023-24, 50% of estimate cost i.e.1,04,88,089/- in advance as per minutes of the meeting with HMIC, PHED on 12.09.2022 |  |  | BILL/02110/2023-2024 | BP-2023-24-799 | 22/03/2024 |  | EXECUTIVE ENGINEER, SOUTH 24 PGS. DIVISION, PWD | 52.44 | 0 | 0 | 0
2 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Ground water based UTTAR KAZIRHAT piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Are | SM/18375 | Augmentation | Construction of boundary wall & other allied works at Head Work Site of UTTAR KAZIRHAT PWSS at Bishnupur-I block District- South 24-Parganas for augmentation of Surface Water Based W/S scheme in the Arsenic affected areas of South 24-Parganas District. [TSM/018475] (2nd call) | AE SWSD-II | JE-2 | ORD/000242/2023-2024 | 1439/SWD-I | 18/07/2023 | 16/09/2023 | UNI DEVELOPERS AND CONTRACTORS | 18.17 | 8.88 | 48.89 | 100
3 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Ground water based UTTAR KAZIRHAT piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Are | SM/18375 | Augmentation | Construction of 04 (four) nos. different capacities 20 mtr. staging height R.C.C. Over Head Reservoirs as per departmental design, drawing & specification with R.C.C. Bored Pile & Pile Cap including Soil investigation and foundation design for DAULATPUR, CHAK NITAI, BAKESWAR & UTTAR KAZIRHAT PWSS of Bishnupur-I Block for Augmentation of Surface Water based Water Supply Schme in the arsenic affected areas of South 24 Parganas District under South 24-Pgns. W/S Division-I, PHE Dte. [TSM/016355, TSM/017334, TSM/016358, TSM/018475] | AE SWSD-II | JE1,JE2,JE3,JE4 | ORD/000506/2023-2024 | 2220/SWD-I | 12/09/2023 | 08/07/2024 | KESHAVPRIYA INFRASTRUCTURES | 541.95 | 0 | 0 | 0
4 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Ground water based UTTAR KAZIRHAT piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Are | SM/18375 | Augmentation | Laying Distribution System with providing Functional Household Tap Connection (FHTC) for Proposed UTTAR KAZIRHAT PIPE WATER SUPPLY SCHEME in BISHNUPUR-I & Thakurpukur-Mahestala Block for augmentation of surface water based water supply scheme in the arsenic affected areas of South 24 Parganas District. (No of FHTC = 5617) [TSM/018475]. | AE SWSD-I | JE-2 | ORD/000528/2023-2024 | 2345/SWD-I | 22/09/2023 | 21/12/2023 | SUPRITI ENTERPRISE | 638.94 | 47.83 | 7.49 | 40
5 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Ground water based UTTAR KAZIRHAT piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Are | SM/18375 | Augmentation | Laying of Rising Main from Zone 9 to Zone 10 for Ground water based UTTAR KAZIRHAT piped water supply scheme to accommodate FHTC in Bishnupur-I block under South 24-Pgns. W/S Scheme in the Arsenic Affected Areas of South 24-Pgns. District. (SM/18375) | AE SWSD-I | JE-1 | ORD/000751/2023-2024 | 553/SWD-I | 31/01/2024 | 16/03/2024 | SUKUMAR DEBNATH | 40.63 | 8.74 | 21.52 | 50
6 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Ground water based UTTAR KAZIRHAT piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Are | SM/18375 | Augmentation | Preparation and submission of Detailed Project Report of Ground Water Based Uttar Kazirhat Piped Water Supply Scheme to accommodate FHTC in Bishnupur-I Block under South 24-Pgns W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. |  |  | ORD/000963/2022-2023 | 1167/SWD-I | 29/08/2022 | 28/09/2022 | GEO SOLUTION | 2.97 | 1.48 | 49.61 | 100
7 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Ground water based UTTAR KAZIRHAT piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Are | SM/18375 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000118/2022-2023 | 323/SWD-I | 25/04/2023 |  | Resource Division | 43.62 | 0 | 0 | 0
8 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Ground water based UTTAR KAZIRHAT piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Are | SM/18375 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000312/2023-2024 | 3116/SWD-I | 07/12/2023 |  | Resource Division | 94.04 | 0 | 0 | 0
Total | [13 empty] | 1432.76 | 66.93 | 4.67