## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Augmentation of laying distribution system to extend the benefit of 100% Households in ZONE-IV at JOYNAGAR-II block within Mega surface water based water supply scheme for Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns W/S division-I of South | SM/18655 | Augmentation | Payment of Enhanced GST Rate vide W/O No.2484/SWD-I dt. 02/03/2022 |  |  | BILL/01808/2023-2024 | BP-2023-24-637 | 31/01/2024 |  | SAMIRON GHOSH | 7.62 | 0 | 0 | 0
2 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Augmentation of laying distribution system to extend the benefit of 100% Households in ZONE-IV at JOYNAGAR-II block within Mega surface water based water supply scheme for Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns W/S division-I of South | SM/18655 | Augmentation | Construction of development of land, approach road, protection work for pipeline, and other allied works for "Augmentation of laying distribution system to extend the benifit of 100% House hold in Zone-IV at JOYNAGAR-II Block within Mega surface water based water supply scheme for Falta Mathurapur District South 24 Pgns under South 24 Parganas W/S Division-I, of South 24-Pgns. W/S Circle, PHE Dte." (SM/18655) |  |  | ORD/000251/2024-2025 | 2649/SWD-I | 07/06/2024 | 22/07/2024 | P.L. CONSTRUCTION | 46.65 | 0 | 0 | 0
3 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Augmentation of laying distribution system to extend the benefit of 100% Households in ZONE-IV at JOYNAGAR-II block within Mega surface water based water supply scheme for Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns W/S division-I of South | SM/18655 | Augmentation | Construction of pipe carrying structure with laying of 508 mm dia M.S. Secondary Rising Main for crossing of Canal at Simana Bazar, 610 mm dia M.S. Secondary Rising Main for crossing of Canal at Path Pukur Bridge and 355.6 mm dia M.S. pipe for Secondary Rising Main for crossing of Canal at Jibon Mandaler Haat under Augmentation of laying distribution system to extend the benefit of 100% Households in ZONE-VI, Zone-IV and Zone-II respectively within JOYNAGAR-II block within Mega surface water based water supply scheme for Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns W/S division-I of South 24-pgns. W/S Circle, PHE Dte. [SM/16191, 18655 & 18222] | AE BSD | JE-2 | ORD/000285/2024-2025 | 3041/SWD-I | 02/07/2024 | 16/08/2024 | SRIJON ENTERPRISE | 69.41 | 0 | 0 | 0
4 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Augmentation of laying distribution system to extend the benefit of 100% Households in ZONE-IV at JOYNAGAR-II block within Mega surface water based water supply scheme for Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns W/S division-I of South | SM/18655 | Augmentation | Laying distribution system of piped water supply at Zone-IV- B (Gardoani) of Joynagar -II Block, of BARUIPUR Sub-Division, for ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under South 24 Parganas W/S Division - I, P.H.E. Dte. | AE BSD | JE-1 | ORD/000453/2021-2022 | 2484/SWD-I | 02/03/2022 | 30/06/2022 | SAMIRON GHOSH | 485.75 | 142.23 | 29.28 | 95
5 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Augmentation of laying distribution system to extend the benefit of 100% Households in ZONE-IV at JOYNAGAR-II block within Mega surface water based water supply scheme for Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns W/S division-I of South | SM/18655 | Augmentation | Construction of 1500 Cu.m. capacity 20 M. staging height R.C.C. Over Head Water Reservoir as per departmental design, drawing & specification including R.C.C. Bored Pile and raft foundation within Zone-IV at Gordoani Mouza of Joynagar-II Block for Augmentation of laying distribution system to extend the benefit of 100% Households in ZONE-IV at JOYNAGAR-II block within Mega surface water based water supply scheme for Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns W/S division-I of South 24-pgns. W/S Circle, PHE Dte. (SM/18655) |  |  | ORD/000695/2023-2024 | 3190\SWD-I | 12/12/2023 | 07/10/2024 | UNITED BUILDERS | 440.77 | 0 | 0 | 0
6 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Augmentation of laying distribution system to extend the benefit of 100% Households in ZONE-IV at JOYNAGAR-II block within Mega surface water based water supply scheme for Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns W/S division-I of South | SM/18655 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000039/2022-2023 | 2957/SWD-I | 16/02/2023 |  | Resource Division | 121.77 | 0 | 0 | 0
7 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Augmentation of laying distribution system to extend the benefit of 100% Households in ZONE-IV at JOYNAGAR-II block within Mega surface water based water supply scheme for Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns W/S division-I of South | SM/18655 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000210/2023-2024 | 382/SWD-I | 27/04/2023 |  | Resource Division | 182.71 | 0 | 0 | 0
8 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Augmentation of laying distribution system to extend the benefit of 100% Households in ZONE-IV at JOYNAGAR-II block within Mega surface water based water supply scheme for Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns W/S division-I of South | SM/18655 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000300/2023-2024 | 2437/SWD-I | 30/09/2023 |  | Resource Division | 199.31 | 0 | 0 | 0
Total | [13 empty] | 1553.98 | 142.23 | 9.15