## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | AUGMENTATION OF EXISTING LAYING DISTRIBUTION SYSTEM TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS IN ZONE-V AT MANDIRBAZAR BLOCK WITHIN ' MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR, DISTRICT- SOUTH 24 PGNS' UNDER SOUTH-24 PGNS W/S DIVN- | SM/18715 | Augmentation | Construction of Boundary wall for proposed 500 Cum OHR Site of Zone-V within Mandirbazar block, Mouza-PurbaShrinagar (JL No-98), under Mega Surface Water Based Water Supply Secheme for Falta-Mathurapur, Dist. South 24 Paraganas. (Length- 135 mtr.) | AE HQ-I | JE-3 | ORD/000021/2022-2023 | 876/SWD-I | 14/07/2022 | 12/09/2022 | MS P B CONSTRUCTION | 25.37 | 18.68 | 73.64 | 100
2 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | AUGMENTATION OF EXISTING LAYING DISTRIBUTION SYSTEM TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS IN ZONE-V AT MANDIRBAZAR BLOCK WITHIN ' MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR, DISTRICT- SOUTH 24 PGNS' UNDER SOUTH-24 PGNS W/S DIVN- | SM/18715 | Augmentation | Construction of Hume Pipe Culvert 4.80 Mtr.span with 195 Mtr.Long temporary approach road(Plot No-183,189,189) for proposed Zone -V,OHR Site at Purba Srinagar Mouza(J.L.NO-98,Dag No-80,Khatian No-(60,147&256).at Mandirbazar Block for Augmentation of existing Laying Distribution System to extend the benefit of 100% households from existing distribution system in Zone-V at Mandirbazar Block within " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District- South 24 Pgns" under South-24 Pgns W/S Divn-I, PHE Dte. (TSM/014532) | AE HQ-I | JE-3 | ORD/000381/2023-2024 | 1817/SWD-I | 16/08/2023 | 15/09/2023 | M/S. KALPANA CONSTRUCTION | 13.51 | 3.15 | 23.32 | 0
3 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | AUGMENTATION OF EXISTING LAYING DISTRIBUTION SYSTEM TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS IN ZONE-V AT MANDIRBAZAR BLOCK WITHIN ' MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR, DISTRICT- SOUTH 24 PGNS' UNDER SOUTH-24 PGNS W/S DIVN- | SM/18715 | Augmentation | Diversion of Water for "Construction of Hume Pipe Culvert of 10.00 Mtr span for proposed Zone-V OHR Site at Purba Shreenagar Mouza (J.L.NO-132) at Mandirbazar Block for Augmentation of existing Laying Distribution System to extend the benefit of 100% households from existing distribution system in Zone-V at Mandirbazar Block within "Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District- South 24 Parganas" under South-24 Pgns W/S Divn-I, PHE Dte. (SM/18715) | AE HQ-I,Assistant Engineer | JE-3,JE2 | ORD/000432/2024-2025 | 3874/SWD-I | 03/09/2024 | 03/10/2024 | M/S. KALPANA CONSTRUCTION | 6.06 | 0 | 0 | 0
4 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | AUGMENTATION OF EXISTING LAYING DISTRIBUTION SYSTEM TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS IN ZONE-V AT MANDIRBAZAR BLOCK WITHIN ' MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR, DISTRICT- SOUTH 24 PGNS' UNDER SOUTH-24 PGNS W/S DIVN- | SM/18715 | Augmentation | Construction of 500 cum OHR , Laying distrbution main pipe line with FHTC for 'Augmentation of existing Laying Distribution System to extend the benefit of 100% households and providing FHTC from existing distribution system in Zone-V at Mandirbazar Block within " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District- South 24 Pgns" under South-24 Pgns W/S Divn-I of South 24-Pgns. W/S Circle, PHE Dte'. (No of FHTC.3829) | AE HQ-I | JE-3 | ORD/000461/2023-2024 | 2139/SWD-I | 31/08/2023 | 26/06/2024 | BALAJEE ENTERPRISES | 760.19 | 0 | 0 | 5
5 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | AUGMENTATION OF EXISTING LAYING DISTRIBUTION SYSTEM TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS IN ZONE-V AT MANDIRBAZAR BLOCK WITHIN ' MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR, DISTRICT- SOUTH 24 PGNS' UNDER SOUTH-24 PGNS W/S DIVN- | SM/18715 | Augmentation | Preparation and submission of Detailed Survey, Design and Drawing for laying distribution system of PURBA SRINAGAR MOUZA in MANDIRBAZAR (ZONE-V) Block under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, South 24-Pgns. district. | AE HQ-I |  | ORD/000462/2021-2022 | 1987/SWD-I | 27/01/2022 | 26/02/2022 | MS R. DUTTA AND CO | 4.42 | 3.58 | 80.99 | 100
6 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | AUGMENTATION OF EXISTING LAYING DISTRIBUTION SYSTEM TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS IN ZONE-V AT MANDIRBAZAR BLOCK WITHIN ' MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR, DISTRICT- SOUTH 24 PGNS' UNDER SOUTH-24 PGNS W/S DIVN- | SM/18715 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000047/2022-2023 | 3016/SWD-I | 20/02/2023 |  | Resource Division | 58.22 | 0 | 0 | 0
Total | [13 empty] | 867.76 | 25.41 | 2.93