## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Ground water based SANKHARIPUR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 parganas district for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 | SM/18870 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 for Sankharipur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Baruipur] | Assistant Engineer | Junior Engineer | ORD/000224/2024-2025 | 2455/SMD | 01/08/2024 | 30/10/2024 | A.G.ENTERPRISE | 12.47 | 0 | 0 | 0
2 | SOUTH 24 PARAGANAS |  | S24 Pgns Mechanical | Ground water based SANKHARIPUR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 parganas district for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 | SM/18870 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 2 for Sankharipur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Baruipur] | Assistant Engineer | Junior Engineer | ORD/000347/2024-2025 | 2125/SMD | 12/07/2024 | 10/10/2024 | SHRESTHA | 12.59 | 0 | 0 | 0
3 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Ground water based SANKHARIPUR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 parganas district for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 | SM/18870 | Augmentation | Construction of platform for FHTC, pipeline protection work, development of land and other allied works for "Ground Water Based SANKHARIPUR PWSS Piped Water Supply Scheme to Accommodate FHTC in BARUIPUR Block Under South 24 Parganas W/S Division-I, South 24 Parganas District For Augmentation of Surface Water Based Water Supply Scheme In Arsenic Affected Areas of South 24 Parganas District." (SM/18870) |  |  | ORD/000358/2024-2025 | 3458/SWD-I | 02/08/2024 | 16/09/2024 | MOUMITA ENTERPRISE | 58.31 | 0 | 0 | 0
4 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Ground water based SANKHARIPUR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 parganas district for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 | SM/18870 | Augmentation | Construction of Boundary Wall, Chlorine Room along with Laying Distribution, Rising Main, Functional Household Tap Connection (FHTC) for Augmentation of SANKHARIPUR of Baruipur Block of Surface Water based Water Supply Scheme in the arsenic affected areas of South 24-Parganas District [No. of FHTC = 917] | AE BSD | JE RWS | ORD/000565/2023-2024 | 2611/SWD-I | 17/10/2023 | 15/01/2024 | MOUMITA ENTERPRISE | 139.7 | 43.46 | 31.11 | 80
5 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Ground water based SANKHARIPUR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 parganas district for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 | SM/18870 | Augmentation | Sinking of 02 (two) nos. of Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method for SANKHARIPUR PWSS to accommodate FHTC in Baruipur Block under South 24-Parganas W/S Division-I, P.H.E. Dte. for Augmentation of Surface Water Based Water Supply in the Arsenic Affected areas of South 24 Pgns. Dist. [SM/18870] | AE BSD | JE RWS | ORD/000715/2023-2024 | 3431/SWD-I | 29/12/2023 | 12/02/2024 | DEV & COMPANY | 31.8 | 14.3 | 44.96 | 100
6 | SOUTH 24 PARAGANAS |  | South 24 Pgs W/S Division I | Ground water based SANKHARIPUR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 parganas district for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 | SM/18870 | Augmentation | Preparation and submission of Detailed Project Report of Ground Water Based Sankharipur Piped Water Supply Scheme to accommodate FHTC in Baruipuri Block under South 24-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district.. |  |  | ORD/000987/2022-2023 | 1484/SWD-I | 27/09/2022 | 27/10/2022 | GEO SOLUTION | 2.46 | 1.23 | 49.89 | 100
Total | [13 empty] | 257.32 | 58.98 | 22.92