## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Chakmakrampur Piped Water Supply Scheme. | SM/06912 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Chakmakrampur W/S Scheme, Block: - Kharagpur-II, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | AE Kharagpur Sub-division | JE3 Kharagpur Sub-division | ORD/000238/2020-2021 | 1442/MD | 26/11/2020 | 25/05/2021 | M/S. CARE | 89.58 | 84.95 | 94.84 | 0
2 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Chakmakrampur Piped Water Supply Scheme. | SM/06912 | Retrofitting | Retrofitting to accommodate balance FHTC under JJM in Chakmakrampur PWSS in Kharagpur-II Block in the District of Paschim Medinipur. | AE Kharagpur Sub-division | JE3 Kharagpur Sub-division | ORD/000435/2020-2021 | 306/MD | 22/02/2021 | 08/04/2021 | M/S. EL-CON | 32.11 | 0 | 0 | 0
Total | [13 empty] | 121.69 | 84.95 | 69.81