## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Debhog Piped Water Supply Scheme. | SM/06915 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Debhog W/S Scheme, Block: - Sabang, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | AE Kharagpur Sub-division | JE RWS Kharagpur Sub-Division( Sabang) | ORD/000265/2020-2021 | 1461/MD | 26/11/2020 | 25/05/2021 | MIDNAPUR PIPE CONCERN | 67.06 | 58.97 | 87.93 | 100
2 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Debhog Piped Water Supply Scheme. | SM/06915 | Retrofitting | Continuation Work Order for the work of Retrofitting to accommodate additional FHTC under JJM in Debhog W/S Scheme, Block :- Sabang, District :- Paschim Medinipur within Midnapore Division, PHE Dte. | AE Kharagpur Sub-division |  | ORD/000515/2022-2023 | 2533/MD | 12/12/2022 | 26/12/2022 | MIDNAPUR PIPE CONCERN | 13.69 | 6.83 | 49.88 | 50
3 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Debhog Piped Water Supply Scheme. | SM/06915 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Debhog W/S Scheme, Block: - Sabang, District: - Paschim Medinipur within Midnapore Division, PHE Dte. |  |  | VCH/000722/2020-2021 | null | 15/12/2020 |  | MIDNAPUR PIPE CONCERN | 30 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Debhog Piped Water Supply Scheme. | SM/06915 | Retrofitting | FHTC DATA ENTRY |  |  | VCH/000765/2021-2022 | 8443211 | 27/09/2021 |  | SHRABONTI BERA | 0.2 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Debhog Piped Water Supply Scheme. | SM/06915 | Retrofitting | FHTC DATA ENTRY |  |  | VCH/000766/2021-2022 | 8443211 | 27/09/2021 |  | TANMOY BERA | 0.17 | 0 | 0 | 0
6 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Debhog Piped Water Supply Scheme. | SM/06915 | Retrofitting | For FHTC Data Entry. |  |  | VCH/000853/2021-2022 | 844375 | 10/09/2021 |  | SHRABONTI BERA | 0.17 | 0 | 0 | 0
7 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Debhog Piped Water Supply Scheme. | SM/06915 | Retrofitting | For FHTC Data Entry. |  |  | VCH/000854/2021-2022 | 844375 | 08/09/2021 |  | SUBHAJIT GANGULY | 0.01 | 0 | 0 | 0
8 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Debhog Piped Water Supply Scheme. | SM/06915 | Retrofitting | FHTC data entry. |  |  | VCH/001212/2021-2022 | 844336 | 08/12/2021 |  | RINTU SAMANTA | 0.07 | 0 | 0 | 0
9 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Debhog Piped Water Supply Scheme. | SM/06915 | Retrofitting | FHTC data entry. |  |  | VCH/001213/2021-2022 | 844336 | 08/12/2021 |  | SANDIP MANNA | 0.06 | 0 | 0 | 0
10 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Debhog Piped Water Supply Scheme. | SM/06915 | Retrofitting | FHTC data entry. |  |  | VCH/001214/2021-2022 | 844336 | 08/12/2021 |  | PRATHA PRATIM PAL | 0.07 | 0 | 0 | 0
11 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Debhog Piped Water Supply Scheme. | SM/06915 | Retrofitting | FHTC data entry. |  |  | VCH/001215/2021-2022 | 844336 | 03/12/2021 |  | NABOGOPAL ADHIKARI | 0.06 | 0 | 0 | 0
12 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Debhog Piped Water Supply Scheme. | SM/06915 | Retrofitting | FHTC data entry. |  |  | VCH/001282/2021-2022 | 844362 | 18/01/2022 |  | MANABENDAN DAS | 0.2 | 0 | 0 | 0
13 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Debhog Piped Water Supply Scheme. | SM/06915 | Retrofitting | FHTC data entry. |  |  | VCH/001283/2021-2022 | 844362 | 18/01/2022 |  | SHRABONTI BERA | 0.2 | 0 | 0 | 0
Total | [13 empty] | 111.97 | 65.8 | 58.76