## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Jamna PWSS Block-Pingla District Paschim Medinipur | SM/08212 | Retrofitting | Accomdation of FHTC under JJM for the leftout Portion of Jamna Water Supply Scheme catchment area as per site reconnaissance, Block: - Pingla , within Midnapore Division, P.H.E. Dte. District: - Paschim Midnapore. | AE Kharagpur Sub-division,Assistant Engineer (HQ) | JE RWS Kharagpur Sub-Division( Sabang),JE1 Kharagpur Sub-division | ORD/000007/2022-2023 | 217/AE/KSD | 29/04/2022 | 29/05/2022 | GOBINDA MAITY | 4.57 | 2.26 | 49.36 | 90
2 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Jamna PWSS Block-Pingla District Paschim Medinipur | SM/08212 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Jamna PWSS, Block - Pingla in the district of Paschim Medinipur. | AE Kharagpur Sub-division | JE RWS Kharagpur Sub-Division( Sabang) | ORD/000642/2020-2021 | 445/MD | 26/02/2021 | 19/03/2021 | GOBINDA MAITY | 41.65 | 25.06 | 60.15 | 0
Total | [13 empty] | 46.22 | 27.31 | 59.08