## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Kharika PWSS Block Sabang District Paschim Medinipur | SM/08214 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Kharika PWSS, Block :- Sabang in the District of Paschim Medinipur. | AE Kharagpur Sub-division | JE RWS Kharagpur Sub-Division( Sabang) | ORD/000450/2020-2021 | 340/MD | 24/02/2021 | 05/04/2021 | BANERJEE CONSTRUCTION | 99.91 | 54.28 | 54.33 | 0
2 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Kharika PWSS Block Sabang District Paschim Medinipur | SM/08214 | Retrofitting | Retrofitting to accomodate FHTC under JJM in Kharika PWSS Block Sabang District Paschim Medinipur. |  |  | VCH/001381/2021-2022 | BP-2021-22-410 | 23/02/2022 |  | BANERJEE CONSTRUCTION | 15 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accomodate FHTC under JJM in Kharika PWSS Block Sabang District Paschim Medinipur | SM/08214 | Retrofitting | Retrofitting to accomodate FHTC under JJM in Kharika PWSS Block Sabang District Paschim Medinipur. |  |  | VCH/001601/2021-2022 | BP-2021-22-410 | 23/02/2022 |  | BANERJEE CONSTRUCTION | 0.21 | 0 | 0 | 0
Total | [13 empty] | 115.12 | 54.28 | 47.15