## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Nabin Mahespur PWSS, Block - Daspur-I, District - Paschim Medinipur. | SM/09081 | Retrofitting | Laying distribution pipe line, Construction of R.C.C. Over Head Reservoir of capacity 250 Cum and staging height 20.00 mtr, FHTC with allied work for Nabin Maheshpur & its adjoining mouzas W/S Scheme in Daspur-I Block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE1 Ghatal Sub-division | ORD/000011/2022-2023 | 608/MD | 04/04/2022 | 01/10/2022 | DIPAK KUMAR DOLAI | 210.12 | 50 | 23.8 | 0
Total | [13 empty] | 210.12 | 50 | 23.8