## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in KASANDA W/S Scheme, Block: - Chandrokona-I, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | SM/09082 | Retrofitting | Laying interconnection in between Rising main pipe line and distribution pipe line with OHR and allied works of KASANDA W/S Scheme within Candrakona-I Block, under Midnapore Division, PHE Dte. |  |  | BILL/00232/2023-2024 | BP-2023-24-16 | 28/04/2023 |  | M/S. A.R. ENTERPRISE. | 0.55 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in KASANDA W/S Scheme, Block: - Chandrokona-I, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | SM/09082 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Kasanda PWSS under Chandrakona-I block in Paschim Medinipur district (Phase-II). | AE Ghatal Sub-division | JE1 Ghatal Sub-division | ORD/000014/2022-2023 | 611/MD | 04/04/2022 | 19/04/2022 | DEVJYOTI BERA | 7.67 | 6.18 | 80.55 | 0
3 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in KASANDA W/S Scheme, Block: - Chandrokona-I, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | SM/09082 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Kasanda W/S Scheme, Block: - Chandrakona-I, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE1 Ghatal Sub-division | ORD/000287/2020-2021 | 1585/MD | 11/12/2020 | 09/06/2021 | DEVJYOTI BERA | 24.31 | 21.65 | 89.06 | 0
Total | [13 empty] | 32.53 | 27.83 | 85.55