## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Khasbar PWSS, Block - Ghatal, District - Paschim Medinipur. | SM/09086 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Khasbar (Zone-I) PWSS under Ghatal Block in Paschim Medinipur District. | AE Ghatal Sub-division | JE1 Ghatal Sub-division | ORD/000494/2021-2022 | 2187/MD | 17/12/2021 | 31/01/2022 | M/S. D.K.H.CONSTRUCTION | 75.89 | 47.79 | 62.97 | 0
2 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Khasbar PWSS, Block - Ghatal, District - Paschim Medinipur. | SM/09086 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Khasbar (Zone-II) PWSS under Ghatal Block in Paschim Medinipur District. | AE Ghatal Sub-division | JE1 Ghatal Sub-division | ORD/000529/2021-2022 | 29/MD | 07/01/2022 | 06/02/2022 | S.T. ENTERPRISE | 37.86 | 31.99 | 84.5 | 0
3 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Khasbar PWSS, Block - Ghatal, District - Paschim Medinipur. | SM/09086 | Retrofitting | Continuation Work Order for the work of Additional retrofitting to accommodate FHTC under JJM for Khasbar (Zone-II) PWSS within Ghatal Block under Ghatal Sub-Division of Midnapore Division PHE Dte. | AE Ghatal Sub-division | JE1 Ghatal Sub-division | ORD/000740/2022-2023 | 753/MD | 13/03/2023 | 27/04/2023 | S.T. ENTERPRISE | 11.47 | 0 | 0 | 0
Total | [13 empty] | 125.22 | 79.78 | 63.71