## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting of Ground Water Based Balichak Pipe Water Supply Scheme to accommodate FHTC under Jal Jeevan Mission under Debra block in Paschim Medinipur district under Midnapore Division, PHE Dte. | SM/09420 | Retrofitting | Accommodate FHTC (3,350 Nos.) including supplying, laying, fitting, fixing of 15mm dia. NB PVC(Sch-80)/20mm dia. HDPE (PE-100, PN-16) Pipe with all necessary specials, saddle piece etc. all complete including cost of all materials under JJM of Balichak W/S Scheme within Debra Dev. block under Kharagpur Sub-Division of Midnapore Division PHE Dte. in the District of Paschim Medinipur. | AE/RWS Midnapore Sub Division |  | ORD/000040/2024-2025 | 2220/MD | 19/07/2024 | 17/09/2024 | ASHIM KUMAR DEY | 144.99 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting of Ground Water Based Balichak Pipe Water Supply Scheme to accommodate FHTC under Jal Jeevan Mission under Debra block in Paschim Medinipur district under Midnapore Division, PHE Dte. | SM/09420 | Retrofitting | Preparation of D.P.R. (Consultancy work) in connection with the Functional Household Tap Connection of existing PWSS (Balichak, Block - Debra) to be Retrofitting under Midnapore Division, PHE Dte. | AE Kharagpur Sub-division | JE RWS Kharagpur Sub-Division(Debra) | ORD/000117/2021-2022 | 996/MD | 23/06/2021 | 03/07/2021 | RISHAN ENGINEERING CONSULTANCY | 3.59 | 3.08 | 85.61 | 0
Total | [13 empty] | 148.58 | 3.08 | 2.07