## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Sabang | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Lachhmi Chak & its adjoining mouzas, Block - Sabang, District - Paschim Medinipur | SM/09675 | New | Construction & Commissioning including FHTC (Civil Part) with 3 (three) months trial run for proposed Mini Pipe W/S Scheme for Mouza - Lachhmi Chak (Zone-I), Block - Sabang, District - Paschim Medinipur under Midnapore Division, PHE Dte. | AE Kharagpur Sub-division | JE RWS Kharagpur Sub-Division( Sabang) | ORD/000622/2021-2022 | 175/MD | 01/02/2022 | 01/07/2022 | BIDHAN CHANDRA PATRA | 22.21 | 17.47 | 78.65 | 80
2 | PASCHIM MEDINIPUR | Sabang | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Lachhmi Chak & its adjoining mouzas, Block - Sabang, District - Paschim Medinipur | SM/09675 | New | Construction & Commissioning including FHTC (Civil Part) with 3 (three) months trial run for proposed Mini Pipe W/S Scheme for Mouza - Lachhmi Chak (Zone-II), Block - Sabang, District - Paschim Medinipur under Midnapore Division, PHE Dte. | AE Kharagpur Sub-division | JE RWS Kharagpur Sub-Division( Sabang) | ORD/000623/2021-2022 | 176/MD | 01/02/2022 | 01/07/2022 | BIDHAN CHANDRA PATRA | 21.5 | 18.48 | 85.96 | 90
3 | PASCHIM MEDINIPUR | Sabang | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Lachhmi Chak & its adjoining mouzas, Block - Sabang, District - Paschim Medinipur | SM/09675 | New | Material Requisition To Resource Division |  |  | RTOR000011/2021-2022 | 2127/MD | 14/12/2021 |  | Resource Division | 1.3 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Sabang | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Lachhmi Chak & its adjoining mouzas, Block - Sabang, District - Paschim Medinipur | SM/09675 | New | Sinking of (1 St) mniX 100 mm.X 150rnir) RBCM by Rnla.ry method at lJaspnr writes *«mix scheme. tube we11 no. I of Sabang i3lock of Paschim Midnapur District under Midtidpur Mechanical Division P.II.E Eite. |  |  | VCH/000383/2022-2023 | null | 03/08/2022 |  | DEBJYOTI BASU | 3.95 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR | Sabang | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Lachhmi Chak & its adjoining mouzas, Block - Sabang, District - Paschim Medinipur | SM/09675 | New | Purchasing of materials for the ground Based Mini Piped Water Supply Scheme for Lachhmi Chak & its adjoining mouzas. Block - Sabang, District - Paschim Medinipur |  |  | VCH/000458/2022-2023 | null | 11/08/2022 |  | EXECUTIVE ENGINEER,RESOURCES DIVISION PHE DTE. | 1.3 | 0 | 0 | 0
6 | PASCHIM MEDINIPUR | Sabang | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Lachhmi Chak & its adjoining mouzas, Block - Sabang, District - Paschim Medinipur | SM/09675 | New | Purchasing of materials. |  |  | VCH/001689/2021-2022 | BP-2021-22-445 | 08/03/2022 |  | EXECUTIVE ENGINEER,RESOURCES DIVISION PHE DTE. | 1.3 | 0 | 0 | 0
7 | PASCHIM MEDINIPUR | Sabang | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Lachhmi Chak & its adjoining mouzas, Block - Sabang, District - Paschim Medinipur | SM/09675 | New | Sinking of different dis T/W under mentioned Scheme of Sabang Block. |  |  | VCH/001823/2021-2022 | BP-2021-22-505 | 25/03/2022 |  | EXECUTIVE ENGINEER,MIDNAPORE MECHANICAL DIVISION, PHE DTE. | 3.9 | 0 | 0 | 0
8 | PASCHIM MEDINIPUR | Sabang | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Lachhmi Chak & its adjoining mouzas, Block - Sabang, District - Paschim Medinipur | SM/09675 | New | Sinking of (150 mmX 100mmX 150 mtr) RBTW by Rotary Method at Lachmi Chak water supply scheme, tube well no. 1 of Sabang Block of Paschim Midnapur Dist under MMD. P.H.E. Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/001136/2021-2022 | 2512/W/MMD | 30/11/2021 | 04/12/2021 | DEBJYOTI BASU | 4.47 | 0 | 0 | 100
9 | PASCHIM MEDINIPUR | Sabang | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Lachhmi Chak & its adjoining mouzas, Block - Sabang, District - Paschim Medinipur | SM/09675 | New | Sinking of (150 mmX 100mmX 150 mtr) RBTW by Rotary Method at Lachmi Chak water supply scheme, tube well no. 2 of Sabang Block of Paschim Midnapur Dist under MMD. P.H.E. Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/001142/2021-2022 | 2514/W/MMD | 30/11/2021 | 04/12/2021 | DEBJYOTI BASU | 4.47 | 3.95 | 88.27 | 0
10 | PASCHIM MEDINIPUR | Sabang | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Lachhmi Chak & its adjoining mouzas, Block - Sabang, District - Paschim Medinipur | SM/09675 | New | Providing and installation of pumping machinery and other electromechanical equipment at newly sunk Tube well -I at Lachhmi Chak, Block- Sabang under ground water based mini piped water supply scheme Dist. Paschim Medinipur under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/001188/2021-2022 | 147/W/MMD | 31/01/2022 | 31/05/2022 | P.P.CONCERN | 6.5 | 2.09 | 32.17 | 0
11 | PASCHIM MEDINIPUR | Sabang | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Lachhmi Chak & its adjoining mouzas, Block - Sabang, District - Paschim Medinipur | SM/09675 | New | Providing and installation of pumping machinery and other electromechanical equipment at newly sunk Tube well -II at Lachhmi Chak, Block- Sabang under ground water based mini piped water supply scheme Dist. Paschim Medinipur under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/001189/2021-2022 | 148/W/MMD | 31/01/2022 | 31/05/2022 | SUJOY RANJAN BHOWMICK | 6.51 | 4.32 | 66.35 | 0
12 | PASCHIM MEDINIPUR | Sabang | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Lachhmi Chak & its adjoining mouzas, Block - Sabang, District - Paschim Medinipur | SM/09675 | New | Additional work in connection with sinking of (150mmX100mmX150mtr) RBTW by Rotary method at Lachmi Chak water supply scheme , tube well no. 2 of Sabang Block of Paschim Midnapur Dist. under MMD PHE Dte. |  |  | ORD/001557/2021-2022 | 43/MMSD-I | 19/01/2022 | 26/01/2022 | DEBJYOTI BASU | 0.19 | 0.19 | 100 | 0
13 | PASCHIM MEDINIPUR | Sabang | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Lachhmi Chak & its adjoining mouzas, Block - Sabang, District - Paschim Medinipur | SM/09675 | New | Additional work in connection with sinking of (150mmX100mmX150mtr) RBTW by Rotary method at Lachmi Chak water supply scheme , tube well no. I of Sabang Block of Paschim Midnapur Dist. under MMD PHE Dte. |  |  | ORD/001558/2021-2022 | 44/MMSD-I | 19/01/2022 | 26/01/2022 | DEBJYOTI BASU | 0.19 | 0.19 | 100 | 0
14 | PASCHIM MEDINIPUR | Sabang | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Lachhmi Chak & its adjoining mouzas, Block - Sabang, District - Paschim Medinipur | SM/09675 | New | Providing and installation of pumping machinery and other electromechanical equipment at newly sunk Tube well -I at Lachhmi Chak, Block- Sabang under ground water based mini piped water supply scheme Dist. Paschim Medinipur under MMD PHE Dte. (W/O-147/W/MMD, DT-31/01/2022) |  |  | VCH/005602/2021-2022 | BP-2021-22-120 | 17/03/2022 |  | P.P.CONCERN | 3.68 | 0 | 0 | 0
Total | [13 empty] | 81.48 | 46.69 | 57.29