## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Sabang | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Nilhat mouzas, Block - Sabang, District - Paschim Medinipur. | SM/09676 | New | Preparation of D.P.Rs. (Consultancy work) in connection with Proposed Mini Pipe W/S Scheme for mouza (i) Nilhat, (ii) Mirjapur & (iii) Lachhmi Chak & its adj. Mouzas of non-cover mouzas within Sabang Block under Midnapore Division, PHE Dte. | AE Kharagpur Sub-division |  | ORD/000423/2021-2022 | 1337/MD | 18/08/2021 | 28/08/2021 | GOBINDA MAITY | 4.39 | 4.24 | 96.57 | 0
2 | PASCHIM MEDINIPUR | Sabang | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Nilhat mouzas, Block - Sabang, District - Paschim Medinipur. | SM/09676 | New | Construction & Commissioning including FHTC (Civil Part) with 3 (three) months trial run for proposed Mini Pipe W/S Scheme for Mouza - Nilhat, Block - Sabang, District - Paschim Medinipur under Midnapore Division, PHE Dte. | AE Kharagpur Sub-division,Assistant Engineer (HQ) | JE RWS Kharagpur Sub-Division( Sabang),JE3 Kharagpur Sub-division | ORD/000627/2021-2022 | 180/MD | 01/02/2022 | 01/07/2022 | MASUM ALI KHAN | 36.44 | 31.46 | 86.35 | 80
3 | PASCHIM MEDINIPUR | Sabang | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Nilhat mouzas, Block - Sabang, District - Paschim Medinipur. | SM/09676 | New | Material Requisition To Resource Division |  |  | RTOR000006/2021-2022 | 2115/MD | 13/12/2021 |  | Resource Division | 1.39 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Sabang | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Nilhat mouzas, Block - Sabang, District - Paschim Medinipur. | SM/09676 | New | Purchasing of materials for the ground Based Mini Piped Water Supply Scheme for Nilhat mouzas, Block - Sabang, District - Paschim Medinipur. |  |  | VCH/000456/2022-2023 | null | 11/08/2022 |  | EXECUTIVE ENGINEER,RESOURCES DIVISION PHE DTE. | 1.39 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR | Sabang | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Nilhat mouzas, Block - Sabang, District - Paschim Medinipur. | SM/09676 | New | For payment of liabilities. |  |  | VCH/001691/2021-2022 | BP-2021-22-445 | 08/03/2022 |  | EXECUTIVE ENGINEER,RESOURCES DIVISION PHE DTE. | 1.39 | 0 | 0 | 0
6 | PASCHIM MEDINIPUR | Sabang | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Nilhat mouzas, Block - Sabang, District - Paschim Medinipur. | SM/09676 | New | Sinking of different dis T/W under mentioned Scheme of Sabang Block. |  |  | VCH/001825/2021-2022 | BP-2021-22-505 | 22/03/2022 |  | EXECUTIVE ENGINEER,MIDNAPORE MECHANICAL DIVISION, PHE DTE. | 4.19 | 0 | 0 | 0
7 | PASCHIM MEDINIPUR | Sabang | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Nilhat mouzas, Block - Sabang, District - Paschim Medinipur. | SM/09676 | New | Sinking of (150 mmX 100mmX 150 mtr) RBTW by Rotary Method at Nilhat water supply scheme of Sabang Block of Paschim Midnapur Dist under MMD. P.H.E. Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/001184/2021-2022 | 2524/W/MMD | 30/11/2021 | 04/12/2021 | MENAKA ENTERPRISE | 4.48 | 0 | 0 | 100
8 | PASCHIM MEDINIPUR | Sabang | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Nilhat mouzas, Block - Sabang, District - Paschim Medinipur. | SM/09676 | New | Providing and installation of pumping machinery and other electromechanical equipment at newly sunk Tube well at Nilhat, Block- Sabang under ground water based mini piped water supply scheme Dist. Paschim Medinipur under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/001196/2021-2022 | 155/W/MMD | 31/01/2022 | 31/05/2022 | DEY ENTERPRISE | 6.81 | 4 | 58.71 | 0
Total | [13 empty] | 60.47 | 39.7 | 65.66