## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Kurul PWSS under Datan-II Block in Paschim Medinipur District | SM/09710 | Retrofitting | Extension of Distribution pipeline at Mouza Kural(Adibasipara near Hutpara) & Satpukuria within Kurul PWSS under Kharagpur Sub-Division within Midnapore Division, P.H.E. Dte. | AE/RWS Midnapore Sub Division |  | ORD/000064/2022-2023 | 236/AE/KSD | 12/05/2022 | 11/06/2022 | RELIABLE ENTERPRISES | 3.3 | 3.3 | 100 | 0
2 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Kurul PWSS under Datan-II Block in Paschim Medinipur District | SM/09710 | Retrofitting | Extension of Distribution pipeline at Mouza Santoshpur & Piling work near pond within Kurul PWSS under Kharagpur Sub-Division Within Midnapore Division, P.H.E. Dte. | AE/RWS Midnapore Sub Division |  | ORD/000136/2022-2023 | 382/AE/KSD | 30/06/2022 | 30/07/2022 | RELIABLE ENTERPRISES | 3.4 | 3.3 | 97.06 | 0
3 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Kurul PWSS under Datan-II Block in Paschim Medinipur District | SM/09710 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Kurul PWSS under Dantan-II Block in Paschim Medinipur District. | Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Dantan-II) | ORD/000402/2021-2022 | 2001/MD | 01/12/2021 | 31/12/2021 | M/S. EL-CON | 59.12 | 51.8 | 87.61 | 0
Total | [13 empty] | 65.83 | 58.4 | 88.72