## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting of ground water based Dharma PWSS to accommodate FHTC under JJM under Daspur-I block in Paschim Medinipur District under medinipur Division,PHE DTE. | SM/09721 | Retrofitting | Laying pipe line to provide balance FHTC under JJM in DHARMA PWSS under Ghatal Sub-Division in the District of Paschim Medinipur | AE Ghatal Sub-division | JE1 Ghatal Sub-division | ORD/000465/2023-2024 | 5359/MD | 30/11/2023 | 25/12/2023 | SK REAJUL HOSSAIN | 6.49 | 3.25 | 50 | 100
2 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting of ground water based Dharma PWSS to accommodate FHTC under JJM under Daspur-I block in Paschim Medinipur District under medinipur Division,PHE DTE. | SM/09721 | Retrofitting | Sinking of 1 (One) No. Replacement tube well including allied works for Retrofitting of Ground Water Based Dharma PWSS to accommodate FHTC under JJM under Daspur-I block in Paschim Medinipur District under Midnapore Division, P.H.E. Dte. | AE Ghatal Sub-division | JE1 Ghatal Sub-division | ORD/000495/2021-2022 | 2188/MD | 17/12/2021 | 15/02/2022 | M/S. D.K.H.CONSTRUCTION | 85.4 | 81.49 | 95.42 | 100
3 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting of ground water based Dharma PWSS to accommodate FHTC under JJM under Daspur-I block in Paschim Medinipur District under medinipur Division,PHE DTE. | SM/09721 | Retrofitting | Retrofitting to accommodate FHTC under JJM at Dolai Para in Dharma PWSS within Daspur-I Block under Ghatal Sub-Division of Midnapore Division P.H.E.Dte. (Phase-I) | AE Ghatal Sub-division | JE1 Ghatal Sub-division | ORD/000717/2020-2021 | 99/AE/GSD | 25/02/2021 | 04/03/2021 | PBA INFRASTRUCTURE | 4.72 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting of ground water based Dharma PWSS to accommodate FHTC under JJM under Daspur-I block in Paschim Medinipur District under medinipur Division,PHE DTE. | SM/09721 | Retrofitting | Retrofitting to accommodate FHTC under JJM at Nandanpur-II in Dharma PWSS within Daspur-I Block under Ghatal Sub-Division of Midnapore Division P.H.E.Dte. (Phase-I) | AE Ghatal Sub-division | JE1 Ghatal Sub-division | ORD/000719/2020-2021 | 100/AE/GSD | 25/02/2021 | 04/03/2021 | PBA INFRASTRUCTURE | 4.76 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting of ground water based Dharma PWSS to accommodate FHTC under JJM under Daspur-I block in Paschim Medinipur District under medinipur Division,PHE DTE. | SM/09721 | Retrofitting | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS (Dharma, Block - Ghatal) to be Retrofitting under Midnapore Division P.H.E. Dte. |  |  | VCH/001404/2021-2022 | BP-2021-22-380 | 17/02/2022 |  | SIRCON ENGINEERING SERVICES | 3.09 | 0 | 0 | 0
Total | [13 empty] | 104.47 | 84.74 | 81.11